## Abstract 1
fcgkj fpfdRlk lsok,¡ ,oa vk/kkjHkwr lajpuk fuxe- fy-
ekuuh; eq[;ea=h ds 7& fu'p; ds varxZr izLrkfor ifj;kstukvksa dk v¦ru ¼04twuZ½ 2019 rd izxfr izfrosnu
Øe la[;k | ;kstuk dk uke |  | dqy Lohd`r ;kstukvksa dh la[;k | iz'kklfud Lohd`fr dh jkf'k ¼:0 djksM+ esa½ | vkoaVu dh jkf'k ¼:0 djksM+ esa½ | ekpZ 2019 rd dk O;; dh jkf'k ¼:0 djksM+ esa½ | Hkwfe miyC/k | fufonk vkeaf=r | fufonk fu"ikfnr | fufonk izfdz;k/khu | dqy LOA fuxZr | dk;kZns'k fuxZr | fuekZ.kk/khu ;kstukvksa dh la[;k | iw.kZ | dk;Z izkjaHk ugha | dk;kZns'k dh jkf'k | vfHk;qfDr
1 | ,0,u0,e0 Vssªfuax laLFkku ,oa Nk=kokl dk fuekZ.k dk;Z ¼izfr ;wfuV 6-30 djksM+½ |  | 54 | 340.58 | 80 | 106.25 | 54 | 53 | 52 | 1 | 51 | 49 | 27 | 16 | 6 | 308.7 | txnh'kiqj] Qkjfclxat] efugkjh] >a>kjiqj]t;uxj]uhepd cFkkuh]lksuiqj]ujdfV;kxat] fldjguk]rkjkiqj]iVksjh] nyflagljk;] cueu[kh] ohjiqj]csuhiqj]pfd;k&iw.kZ
2 | th0,u0,e0 Vssªfuax laLFkku ,oa Nk=kokl dk fuekZ.k dk;Z ¼izfr ;wfuV 13-35 djksM+½ |  | 23 | 307.13 | 150 | 56.81 | 22 | 22 | 21 | 1 | 21 | 19 | 18 | 0 | 1 | 253.65
3 | ikjk esfMdy laLFkku dk fuekZ.k dk;Z ¼izfr ;wfuV 9-98 djksM+½ |  | 33 | 329.34 | 165 | 65 | 31 | 31 | 31 | 0 | 31 | 28 | 24 | 3 | 1 | 279.44 | jksgrkl]cDlj]ckadk&iw.kZ
4 | ch-,l-lh- uflZax dkWyst dk fuekZ.k dk;Z ¼izfr ;wfuV 26-49 djksM+½ |  | 16 | 423.96 | 180 | 71.14 | 12 | 9 | 9 | 0 | 9 | 9 | 5 | 2 | 2 | 238.41 | PMCH Dropped and Chapra to be started
5 | fpfdRlk egkfo¦ky; dk fuekZ.k dk;Z | egqvk] oS'kkyh | 3 | 500 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tender to be invited
|  | csxqljk; |  | 515 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tender to be invited
|  | vkjk] Hkkstiqj |  | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Land not available
| dqy |  | 129 | 2816.01 | 575 | 299.2 | 121 | 115 | 113 | 2 | 112 | 105 | 74 | 21 | 10 | 1080.2

## ANM
PROJECT UNDER 7-Commitement
Construction of Auxiliary Nurse Midwifery Training Institute (A.N.M) (As on 04 June 2019)
S.N | Name of Places | District | A.A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | TENDER REFRENCE | Date of Receipt of Tender | Tender decided | LOA ISSUED | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Farbisganj | Araria | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Topline Infra, Katihar | yes | Yes | 24/07/2017 | 2017-11-11 | 2018-10-11 | 100% | Completed | Handed Over
2 | Jainagar | Madhubani | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Maa Tara Construction, Darbhanga | yes | Yes | 28/06/2017 | 28/6/2017 | 27/06/2018 | 100% | Completed
3 | Tarapur | Munger | 630.72 | Decoarch | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Lalan Kumar,Bhagalpur | Yes | Yes | 16/06/2017 | 2017-07-12 | 2018-06-12 | 100% | Completed | Handed Over
4 | Sonpur | Saran | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | kaushal buildcon,patna | Yes | Yes | 20/07/2017 | 2018-05-01 | 2019-04-01 | 100% | Completed | Handed over
5 | Neemchak Bathani | Gaya | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Anil Kumar Singh, Sasaram | Yes | yes | 2018-04-01 | 2018-04-01 | 2019-03-01 | 100% | Completed
6 | Manihari | Katihar | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Sudesh Kumar Singh, Jamui | Yes | Yes | 21/09/2017 | 21/9/2017 | 20/09/2018 | 100% | Completed
7 | Jagdispur | Bhojpur | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | YES | Ramesh kumar pandey | Yes | Yes | 2017-06-09 | 2017-06-09 | 2018-05-09 | 100% | Completed | Handed over
8 | Jhanjharpur | Madhubani | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Girdhari Lal Poddar,Darbhanga | Yes | Yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 100% | Completed | Handed over
9 | Narkatiyaganj | West Champaran | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Rama & Sons, Patna | Yes | yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 100% | Completed
10 | Sikarhana | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | B.K.Chaudhary | Yes | yes | 2018-01-02 | 2018-01-02 | 31/01/2019 | 100% | Completed
11 | Patori | Samastipur | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | YES | Binod Kumar Singh,Samastipur | Yes | Yes | 2017-09-10 | 13/1/2018 | 2019-12-01 | 100% | Completed
12 | Dalsinghsarai | Samastipur | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Binod Kumar Singh,Samastipur | Yes | yes | 2017-09-10 | 2018-12-01 | 2019-11-01 | 100% | Completed
13 | Banmankhi | Purnea | 630.72 | Decoarch | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Bambam Kumar Singh | Yes | Yes | 29/01/2018 | 29/1/2018 | 28/01/2019 | 100% | Completed
14 | Virpur | Supaul | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Kunal Kush, Araria | Yes | Yes | 20/07/2017 | 20/07/2017 | 19/07/2018 | 100% | Completed
15 | Benipur | Darbhanga | 630.72 | EDMAC | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | Yes | 17/05/2018 | 15/7/2018 | 14/7/2019 | 100% | Completed
16 | Chakia | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Asiana Contract Pvt. Ltd. | Yes | yes | 31/03/2018 | 31/03/2018 | 30/03/2019 | 100% | Completed
17 | Araria | Araria | 630.72 | Arch-En-Design | Submitted | Nit-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | Yes | Shrinath builder,PATNA | Yes | yes | 24/03/2017 | 2018-02-04 | 2020-01-04 | 13% | Academic block- G.F (Column casted) Hostel Block- Layout
18 | Uda Kishanganj | Madhepura | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | C S CONSTRUCTION, Arariya | Yes | Yes | 2017-05-05 | 2017-03-06 | 2018-02-06 | 72% | Finishing work
19 | Simri Bakhtiyarpur | Saharsa | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | SHANTOSH KUMAR SINGH,SAHARSA | yes | Yes | 14/07/2017 | 2018-10-02 | 2019-09-02 | 80% | Finishing work
20 | Nirmali | Supaul | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | SHANTOSH KUMAR SINGH,SAHARSA | Yes | Yes | 16/06/2017 | 2018-01-02 | 31/1/2019 | 70% | Plaster work is in progress
21 | Bagha | West Champaran | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Shiva Infra Solution, New Delhi | Yes | Yes | 17/05/2017 | 17/05/2017 | 16/05/2018 | 95% | Finishing work | For delay, Letter sent to contractor & consultant dated on 11.02.2019
22 | Biraul | Darbhanga | 630.72 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 2017-02-11 | 25/02/2019 | 24/02/2020 | 15% | Plinth Level
23 | Tekari | Gaya | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Mukesh Kumar, Gaya | Yes | Yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 80% | Finishing work is in progress
24 | Gogari | Khagaria | 630.72 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Arvind Kumar singh, Danapur | Yes | Yes | 2018-12-01 | 2018-12-01 | 2019-11-01 | 65% | Finishing work is in progress
25 | Mahnar | Vaishali | 630.72 | M/S Kapoor & Associates | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | YES | Kunwar Construction, Darbhanga | Yes | yes | 28/12/2017 | 28/12/2017 | 27/12/2018 | 88% | Finishing work is in progress
26 | Piro | Bhojpur | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Anil kumar,Rohtas | Yes | Yes | 2018-10-07 | 2018-10-07 | 2019-09-07 | 98% | Finishing work is in progress
27 | Sherghati | Gaya | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Ambey infra,patna | Yes | yes | 2017-02-11 | 30/12/2017 | 29/12/2018 | 72% | Finishing work is in progress
28 | Bikramganj | Rohtas | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Rambabu Prasad,Patna | Yes | Yes | 27/02/2018 | 27/2/2018 | 25/02/2019 | 95% | Finishing work is in progress
29 | Sukhpur | Supaul | 630.72 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Arvind Kumar singh, Danapur | Yes | yes | 22/10/2017 | 15/02/2019 | 14/02/2020 | 20% | Roof shuttering (G.F)
30 | Mahua (CHC Rajapakar) | Vaishali | 630.72 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Indra Narayan Singh,Patna | Yes | Yes | 25/09/2018 | 25/9/2018 | 24/09/2020 | 30% | Hostel- Column work (3rd Floor), Academic- Roof Shuttering (F.F)
31 | Areraj | East Champaran | 630.72 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | S.K. Enterprises, Sitamarhi | Yes | Yes | 2017-02-12 | 2017-02-12 | 2018-01-12 | 88% | Finishing work | Letter issued to consultant & contractor dated on 11.02.2019
32 | Pakri Dayal | East Champaran | 630.72 | Mass-N-Void | Submitted | Retender Nit-39, Dated-02/12/2016 | 2018-05-01 | Yes | Yes | M/s Hariom Construction, East Champaran | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 15% | Plinth Level
33 | Arwal Sadar | Arwal | 630.72 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Ray, Dhanbad | Yes | Yes | 28/02/2018 | 28/2/2018 | 27/02/2020 | 65% | Finishing work is in progress
34 | Kahalgaon | Bhagalpur | 630.72 | Decoarch | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Ramesh Kumar, Patna | Yes | Yes | 15/03/2018 | 15/03/2018 | 14/03/2019 | 98% | Almost Completed
35 | Benipatti | Madhubani | 630.72 | M/s Mass N Void | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 17/05/2018 | 17/5/2018 | 16/05/2019 | 80% | Finishing work
36 | Bakhri | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | yes | 13/02/2018 | 2018-02-11 | 2019-01-11 | 40% | Brick work is going on (G.F)
37 | Baliya | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | yes | 2018-12-02 | 20/07/2018 | 19/07/2019 | 40% | Brick work is going on (G.F)
38 | Raxaul | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2018-01-05 | Yes | Yes | M/s Hariom Construction, East Champaran | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 15% | Plinth Level
39 | Rosara | Samastipur | 630.72 | Archline Designs pvt ltd | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | yes | 29/06/2018 | 2018-01-07 | 30/06/2019 | 75% | Finishing work
40 | Gopalganj ( APHC Baikunthpur) | Gopalganj | 630.72 | Kapoor & Associates | in process | TENDER Nit-18/2017 | 2017-09-04 | Yes | Yes | Baranwala Contractor Pvt.Ltd. | Yes | Yes | 15/03/2018 | 18/5/2018 | 17/5/2019 | 70% | Finishing work is in progress
41 | Madhepura | Madhepura | 630.72 | Suresh Goel & Associates | in process | TENDER Nit-18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 31/03/2018 | 20/5/2018 | 19/11/2019 | 15% | Girl's Hostel- Roof casted (G.F), Boys Hostel- Foundation work
42 | Belsand | Sitamarhi | 630.72 | Archline Designs pvt ltd | in process | Nit-39/2017 | 2018-01-05 | Yes | Yes | Kabbu Khirhar, Sitamarhi | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 20% | Hostel block- Roof shuttering (G.F) Academic Block- Column work (G.F)
43 | Barsoi ( SDH Campus) | Katihar | 630.72 | Kapoor & Associates | in process | Retender Nit-39/2017 | 2018-01-05 | Yes | Yes | Krishnakant Thakur | Yes | Yes | 2019-06-03 | 2019-06-03 | 2020-05-03 | 8% | Foundation work
44 | Teghra | Begusarai | 630.72 | EDMAC | Submitted | Nit-39/2017 | 2018-01-05 | Yes | Yes | Satyanarayan Singh | Yes | No | 2019-08-03 | NS | 2020-07-03 |  | Work to be started
45 | Navgachia | Bhagalpur | 630.72 | Sen & Lall | in process | Retender Nit-39/2017 | 2018-01-05 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | No | 2019-08-03 | NS | 2020-07-03 |  | Work to be started
46 | Pupari | Sitamarhi | 630.72 | Archline Designs pvt ltd | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | No | 17/05/2018 | NS | 16/05/2019 |  | Old building need to be dismentled as advised by E.E building division Sitamarhi. Letter given to E.E building division Sitamarhi for providing estimate of demolition.
47 | Dhamdaha | Purnea | 630.72 | Decoarch | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | YES | C.S. Construction, Araria | Yes | No | 18/08/2017 | NS | 17/08/2018 | 0% | Tree cutting is to be done to start the work
48 | Phulparas | Madhubani | 630.72 | M/s Mass N Void | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | No | 28/04/2018 | NS | 27/04/2019 | 0% | Old structure to be demolished, Letter already issued to Hospital administration
49 | Manjhaul | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | No | 13/02/2018 | NS | 2019-12-02 |  | Land is disputed
50 | Baisi | Purnea | 630.72 | Decoarch | Submitted | RE TENDER Nit-18/2017 | 2017-09-04 | Yes | Yes | Umakant Singh | No | [5 empty] | Old building need to dismentled as advised by E.E building division Purnea
51 | Haveli Khargpur | Munger | 630.72 | Decoarch | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Naushad Ali | No | [6 empty] | Agreement in process
52 | Paliganj | Patna | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | No |  | No |  |  |  |  | -
53 | Madhaura | Saran | 630.72 | M/S Kapoor & Associates | Submitted | Retender Nit-03/2018 | 23.09.2016 | No | No |  | No | [5 empty] | In Tender
54 | Dumrao | Buxar | 630.72 | Kapoor & Associates | in process | - | - | No | No |  | No | [5 empty] | Land is of labour deptt. And to be transffered
|  | Total | 34058.88
Sl. No. | Abstract
1 | Tender Invited |  | 53
2 | Tender to be invited |  | 1 |  |  | Dumraon (Land made available on 5.01.2018)
3 | Tender under process |  | 1 |  |  | Madhaura (Saran)
4 | Tender Decided |  | 52
5 | LOA issued |  | 51
6 | LOA to be issued |  | 1 |  |  | Paliganj
7 | Work order issued |  | 49
8 | Work order to be issued |  | 2 |  |  | Baisi, Haveli Kharagpur
9 | Work not started |  | 6 |  |  | Pupri, Teghra, Dhamdaha, Phulparas, Manjhaul and Navgachia
| Total no. of Places |  | 54

## GNM
PROJECT UNDER 7-Commitement
Construction of General Nurse Midwifery Institute (G.N.M) (As on 04 June 2019)
S.N | District | Place of construction | A. A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Date of Receipt of Tender | Tender decided | LOA ISSUED | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Araria | Araria | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | SRINATH BUILDER | Yes | Yes | 24/03/2017 | 2018-02-04 | 2020-01-04 | 13% | Academic block- G.F (Column casted) Hostel Block- Layout
2 | Katihar | Ward no-04, | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | ADYARAJ DEVELOPER | Yes | Yes | 26/04/2017 | 25/11/2018 | 24/05/2020 | 15% | Plinth Level | Electric pole available in proposed site. Letter to be issued to E.E electric division, Katihar
3 | Khagaria | Old Sub divisional Hospital | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | MACRO RANJAN | Yes | Yes | 24/3/2017 | 24/03/2017 | 23/9/2018 | 80% | Finishing work
4 | Munger | Leprosy Hospital Munger | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | LALAN KUMAR | Yes | Yes | 24/3/2017 | 24/03/2017 | 23/9/2018 | 98% | Finishing work
5 | Jamui | Vill-Mahuli | 1335.38 | Arch-N-Design | In Process | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | SUDESH KUMAR SINGH | Yes | Yes | 2018-12-02 | 2018-12-02 | 2019-11-08 | 70% | Finishing work
6 | Vaishali | CHC Rajapakar | 1335.38 | Arch-N-Design | In Process | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | INDRA NARAIN SINGH | Yes | Yes | 25/09/2018 | 25/09/2018 | 24/09/2020 | 30% | Hostel- Column work (3rd Floor), Academic- Roof Shuttering (F.F)
7 | Gopalganj | SDH, Hathua | 1335.38 | Design Associates | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | AIPLGMC, JOINT VENTURE | Yes | Yes | 2018-01-02 | 2018-01-02 | 31/8/2019 | 70% | Finishing work is in progress
8 | Lakhisarai | Noongarh | 1335.38 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | KANHAIYA CONTRCTOR, BEGUSARAI | Yes | Yes | 2018-07-12 | 2018-07-12 | 2019-06-12 | 30% | Academic block- Roof shuttering (G.F), Hostel block- Roof shuttering(F.F)
9 | Nawada | Budhaul | 1335.38 | Arch-N-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | Dhanpat prasad | Yes | Yes | 29/01/2018 | 29/1/2018 | 28/07/2019 | 30% | Roof shuttering (F.F)
10 | Arwal | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Ray, Dhanbad | Yes | Yes | 28/02/2018 | 28/02/2018 | 27/02/2020 | 65% | Finishing work is in progress
11 | Bhabhua | Barka Katra | 1335.38 | DDF | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Yashaswi Infrastructure, Ranchi | Yes | Yes | 2018-04-05 | 2018-04-05 | 2019-03-11 | 45% | Roof shuttering (Terrace.F)
12 | Bhojpur | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Siemens Construction | Yes | Yes | 29/05/2018 | 29/05/2018 | 28/11/2019 | 35% | Hostel-Plinth Level, Academic- Roof shuttering (1st Floor)
13 | Supaul | VILL -Sukhpur | 1335.38 | EDMAC | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Ashok Kumar | Yes | Yes | 29/05/2018 | 29/05/2018 | 28/11/2019 | 80% | Finishing work
14 | Madhubani | Raghopur Balath | 1335.38 | Sen & Lall consultants pvt ltd | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | SKS-KKT JV | Yes | Yes | 17/07/2018 | 17/07/2018 | 16/01/2020 | 55% | Plaster work is going on.
15 | Sitamarhi | Madhuban | 1335.38 | Mass-N-Void | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | Shashikant Singh | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-09 | 1% | Layout
16 | Siwan | SDH Mahrajganj | 1335.38 | Mass-N-Void | In Process | RETENDER NIT-18/2017 | 2017-09-04 | Yes | Yes | B. Prasad | Yes | Yes | 2018-08-05 | 2018-08-05 | 2019-07-11 | 62% | Plaster work
17 | East Champaran | Sadar Hospital | 1335.38 | Design Associates | Submitted | RETENDER NIT-18/2017 | 2017-09-04 | Yes | Yes | Rama Construction | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 19% | Academic-Roof shuttering (G.F) Boys Hostel-Column work (F.F). Girls Hostel Block- Pile cap Completedk
18 | Nalanda | Pavapuri Medical College Campus | 1335.38 | Arch-N-Design | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 28/04/2018 | 28/04/2018 | 27/10/2019 | 39% | Academic Block- Roof casted (F.F). Hostel Block- Roof shuttering (4th Floor)
19 | Kishanganj | - | 1335.38 | Arch-N-Design | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | Shafique Alam | Yes | No | 31/03/2018 | NS | 30/09/2019 | 0% | Old land changed.Detail of new land is awaited
20 | Aurangabad | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Raj Construction | No | No | - | - | - | 0% | Stay from High Court | LOA issued on 27/02/2018. IA filed for stay vaccation
21 | Sheohar | - | 1335.38 | DDF Consultant pvt ltd | Submitted | Retender NIT 5/2018 | - | Yes | Yes | Birendra Kumar Chaudhary | No | No | - | - | - |  | Approach road not available
22 | Begusarai | Vill-Mirzapur,Khata no.-251 | 1335.38 | DDF | Submitted | NIT-18/2017 | 2017-09-04 | No | No | - | No | No | - | - | - |  | In Tender
23 | Samastipur | - | 1335.38 | DDF Consultant pvt ltd | In Process | - | - | No | No | - | No | No | - | - | - |  | Land not available
|  | Total | 30713.74
Sl. No. | Abstract
1 | Total no. of Places |  |  | 23 |  | 23
2 | Tender Invited |  |  | 22 |  | 22
3 | Tender to be invited |  |  | 0 |  | 1 |  | Samastipur
4 | Tender Decided |  |  | 21 |  | 21
5 | Tender Under process |  |  | 1 |  | 1 |  | Begusarai
6 | LOA issued |  |  | 21 |  | 21
7 | Work order issued |  |  | 17 |  | 19
8 | Work order to be issued |  |  |  |  | 2 |  | Aurangabad, Sheohar
9 | Work is going on |  |  |  |  | 18
10 | Work not started |  |  |  |  | 1 |  | Kishanganj

## Para Medical
PROJECT UNDER 7-Commitement
Construction of Para Medical Institute (As on 04 June 2019)
S.N | District | Place of construction | A. A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Date of Receipt of Tender | Tender decided | LOA ISSUED | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Banka | Sadar Hospital (Old Campus) | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | RANA CONSTRUCTION | YES | Yes | 2017-05-05 | 2017-05-05 | 2018-04-06 | 100% | Completed | Handed over
2 | Buxar | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | B PRASAD &COMPANY | YES | Yes | 2017-07-08 | 25/11/2017 | 24/2/2019 | 100% | Completed
3 | Rohtas | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | RAMESH PANDEY | YES | Yes | 2017-05-08 | 2017-05-08 | 2018-04-11 | 100% | Completed | Handed over
4 | Araria | Araria | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | SRINATH BUILDER | YES | Yes | 24/03/2017 | 2018-02-04 | 2020-01-04 | 13% | Academic block- G.F (Column casted) Hostel Block- Layout | On Schedule
5 | Gopalganj | SDH Hathwa | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | Yes | G M CONSTRUCTION | YES | Yes | 31/3/2017 | 15/1/2018 | 14/4/2019 | 90% | Finishing work
6 | Katihar | Sadar Hospital | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | ADYARAJ DEVELOPER | YES | Yes | 26/4/2017 | 25/11/2018 | 24/05/2020 | 15% | Plinth Level | Electric pole available in proposed site. Letter to be issued to E.E electric division, Katihar
7 | Khagaria | Old Subdivisional Hospital | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | MACRO RANJAN | YES | Yes | 24/3/2017 | 24/3/2017 | 23/09/2018 | 80% | Finishing work
8 | Madhubani | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | SANJAY KUMAR | YES | Yes | 2017-09-05 | 2018-01-11 | 28/02/2020 | 18% | Roof shuttering (G.F)
9 | Munger | Leprosy Hospital Munger | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | LALAN KUMAR | YES | Yes | 24/3/2017 | 24/3/2017 | 23/09/2018 | 98% | Finishing work
10 | Purnea | Sadar Hospital Purnea | 998 | Design Associates Inc. | Submitted | Nit-26, Dated-03/08/2016 | 2016-09-19 | Yes | YES | UMAKANT SINGH | YES | Yes | 31/3/2017 | 2017-01-11 | 31/05/2020 | 62% | Finishing work
11 | Saharsa | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | C S CONSTRUCTION | YES | Yes | 31/3/2017 | 2018-12-03 | 2019-11-08 | 75% | Finishing work
12 | West Champaran | Sadar Hospital | 998 | DDF | Submitted | Nit-15, Dated-10/06/2016 | 15/7/2016 | Yes | YES | L& T CONSTRUCTION | YES | Yes | 2017-10-07 | 2017-10-07 | 2020-09-07 | 25% | work is going on
13 | Jamui | Vill-Mahuli | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | SUDESH KUMAR SINGH | Yes | Yes | 2018-12-02 | 2018-12-02 | 2019-11-08 | 70% | Finishing work
14 | Vaishali | Rajapakar | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | INDRA NARAIN SINGH | Yes | Yes | 25/09/2018 | 25/09/2018 | 24/09/2020 | 30% | Hostel- Column work (3rd Floor), Academic- Roof Shuttering (F.F)
15 | Jehanabad | Referral Hospital Ghosi | 998 | Designer's Wing | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | KAUSHLENDRA KUMAR | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-06 | 10% | Foundation work is going on
16 | Saran | Sadar Hospital Chhapra | 998 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | G M CONSTRUCTION, SIWAN | Yes | Yes | 2018-04-05 | 20/7/2018 | 19/10/2019 | 45% | Brick work
17 | Lakhisarai | Nungarh | 998 | Designer's Wing | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | KANHAIYA CONSTRCION, BEGUSARAI | Yes | Yes | 2018-12-09 | 2018-12-09 | 2019-11-06 | 50% | Finishing work is going on
18 | Supaul | Supaul | 998 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | YES | YES | INDRA NARAIN SINGH, PATNA | YES | Yes | 28/11/2018 | 28/11/2018 | 27/02/2020 | 15% | Plinth Level
19 | Nawada | Budhaul | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | DHANPAT PRASAD | Yes | Yes | 29/01/2017 | 29/01/2017 | 28/07/2019 | 30% | Roof shuttering (F.F)
20 | Arwal | Sadar Hospital | 998 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Rai, Dhanbad | Yes | Yes | 28/02/2018 | 28/02/2018 | 27/02/2020 | 65% | Finishing work is in progress
21 | Bhojpur | Sadar Hospital | 998 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | YES | Siemens Construction | Yes | Yes | 29/05/2018 | 29/5/2018 | 28/11/2019 | 35% | Hostel-Plinth Level, Academic- Roof shuttering (1st Floor)
22 | Nalanda | Pavapuri Medical College Campus | 998 | Arch-En-Design | Submitted | TENDER NIT 18/2017 | 2017-09-04 | Yes | YES | M/s Satyanarayan Singh | Yes | Yes | 28/04/2018 | 28/04/2018 | 27/10/2019 | 39% | Academic Block- Roof casted (F.F). Hostel Block- Roof shuttering (4th Floor)
23 | East Champaran | Sadar Hospital | 998 | Design Associates Inc. | Submitted | RETENDER NIT 18/2017 | 2017-09-04 | Yes | YES | Rama Construction | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 19% | Academic-Roof shuttering (G.F) Boys Hostel-Column work (F.F). Girls Hostel Block- Pile cap Completedk
24 | Madhepura | Parariya | 998 | Suresh Goel & Associates | in process | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 31/03/2018 | 20/5/2018 | 24/11/2019 | 15% | Girl's Hostel- Roof casted (G.F), Boys Hostel- Foundation work
25 | Siwan | Sub-Divisional hospital, Maharajganj | 998 | Mass-N-Void | Submitted | RE TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | B. Prasad | Yes | Yes | 2018-08-05 | 2018-08-05 | 2019-07-11 | 62% | Plaster work
26 | Bhabhua | Sarangpur | 998 | DDF | Submitted | RE TENDER NIT 39/2017 | 2018-01-05 | Yes | Yes | Ajay Kumar Singh | Yes | Yes | 26/10/2018 | 26/10/2018 | 25/01/2020 | 18% | Column work (G.F)
27 | Sheikhpura | Makhdumpur PHC | 998 | Designer's Wing | Submitted | NIT 39/2017 | 2018-01-05 | Yes | YES | Sanjay Kumar Technocrat | Yes | Yes | 2018-07-12 | 2018-07-12 | 2020-06-03 | 20% | Roof shuttering (G.F)
28 | Kishanganj | - | 998 | Arch-En-Design | in process | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | Shafique Alam | Yes | No | 31/03/2018 | NS | 30/09/2019 |  | Land to be changed
29 | Sitamarhi | Madhuban | 998 | Designer's Wing | Submitted | TENDER NIT 18/2017 | 2017-09-04 | Yes | YES | Shashikant Singh | No | No |  |  |  |  | Encrochment available on proposed site.
30 | Aurangabad | Sadar Hospital | 998 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Raj Construction | No | No |  |  |  |  | Stay from High Court
31 | Sheohar | Sadar Hospital | 998 | DDF Consultant pvt ltd | Submitted | RE TENDER NIT 5/2018 | 2018-01-05 | Yes | YES | Birendra Kumar Chaudhary | No | No |  |  |  |  | Approach road not available
32 | Begusarai | - | 998 | DDF | NOT SUBMITTED | - | - | No | No |  | No | No |  |  |  |  | Land not available
33 | Samastipur | - | 998 | DDF | NOT SUBMITTED | - | - | No | No |  | No | No |  |  |  |  | Land not available
|  | Total | 29940
Sl. No. |  | Abstract
1 |  | Tender Invited |  | 31
2 |  | Tender Decided |  | 31
3 |  | LOA issued |  | 31
4 |  | Work order issued |  | 28
5 |  | Work order to be issued |  | 3 |  | Sitamarhi, Aurangabad, Sheohar
6 |  | Work not started |  | 0 |  | Kishanganj
7 |  | DPR under process |  | 1 |  | Begusarai

## B.SC
PROJECT UNDER 7-Commitement
B.Sc Nursing College (As on 04 June 2019)
S.N | Name of Places | District | Land available or not | Administrative Approval Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress in Percentage | Remarks
1 | PMCH, Patna | Patna | No | 2649.76 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | No | 18/08/2017 | NS | 17/08/2019 | - | Work is kept on hold because of PMCH redevelopment
2 | JLNMCH, Bhagalpur | Bhagalpur | Yes | 2649.76 | Arch-En-Design | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed
3 | Vardhaman Ayurvigyan Sansthan, Pawapuri | Nalanda | Yes | 2649.76 | Arch-En-Design | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed
4 | DMCH, Laheriasarai | Darbhanga | Yes | 2649.76 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 90%
5 | SKMCH, Muzaffarpur | Muzaffarpur | Yes | 2649.76 | DDF | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 62%
6 | ANMMCH, Gaya | Gaya | Yes | 2649.76 | Design Associate Inc. | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 2017-05-05 | 2017-05-05 | 2019-04-05 | 70%
7 | Govt. Medical College, Bettiah | Bettiah | Yes | 2649.76 | DDF | Submitted | Nit-15, Dated-10/06/2016 | Yes | Yes | 2017-10-07 | 2017-10-07 | 2020-09-07 | 25%
8 | Govt. Medical College, Purnea (Sadar Hospital Campus) | Purnea | Yes | 2649.76 | Design Associate Inc. | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 2017-01-11 | 31/05/2020 | 60%
9 | Govt. Medical College, Chhapra | Chhapra | Yes | 2649.76 | Suresh Goel & Associates | In Process | Nit-24/2018, Dated-14/07/2018 | Yes | Yes | 28/2/2019 | 28/2/2019 | 27/02/2022 |  | work to be started
10 | Govt. Medical College, Samastipur | Samastipur | Yes | 2649.76 | DDF | Submitted | - | No | No
11 | Govt. Medical College, Madhepura | Madhepura | No | 2649.76 | EDMAC | In Process | - | - | - | - | - | - | - | Land not available
12 | Govt. Medical College, Mahua | Vaishali | Yes | 2649.76 | - | - | - | - | - | - | - | - | - | Tender to be invited
13 | Govt. Medical College, Begusarai | Begusarai | Yes | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
14 | Govt. Medical College, Ara | Bhojpur | No | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
15 | Govt. Medical College, Sitamarhi | Sitamarhi | Yes | 2649.76 | - | - | - | - | - | - | - | - | - | DPR under process
16 | Govt. Medical College, Madhubani | Madhubani | Yes | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
|  | Total |  | 42396.16 | - | - | - | - | - | - | - | - | -
Sl. No. | Abstract
1 | Tender Invited |  |  |  |  | 9
2 | Tender Decided |  |  |  |  | 9 |  | Bhagalpur, Patna, Gaya, Purnia, Darbhanga, Pawapuri, Muzaffarpur, Chhapra & Bettiah
3 | Work order issued |  |  |  |  | 9 |  | Do
4 | Work order to be issued |  |  |  |  | 0
5 | Land to be decided |  |  |  |  | 5 |  | Madhepura, Begusarai, Bhojpur, Madhubani & Samastipur

## Medical College
PROJECT UNDER 7-Commitement
Medical Colleges (As on 04 June 2019)
S.N | Name of Places | District | Land available or not | Administrative Approval Amount (In Rs.cr) | Name of Consultant | Status of DPR | Status of Tender | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress in Percentage | Remarks
1 | Mahua | Vaishali | Yes | 500 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | No | 18/08/2017 | NS | 17/08/2019 | - | Tender to be Invited
2 | Begusarai | Begusarai | Yes | 515 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 85% | Tender to be Invited
3 | Ara | Bhojpur | No | 400 | DDF | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 55% | Land not available
|  |  | Total | 1415