## Abstract
fcgkj fpfdRlk lsok,¡ ,oa vk/kkjHkwr lajpuk fuxe- fy-
ekuuh; eq[;ea=h ds 7& fu'p; ds varxZr izLrkfor ifj;kstukvksa dk v¦ru ¼30 सितंबर 2021½ rd izxfr izfrosnu
Øela[;k | ;kstuk dk uke |  | dqy Lohd`r ;kstukvksa dh la[;k | iz'kklfud Lohd`fr dh jkf'k ¼:0 djksM+ esa½ | vkoaVu dh jkf'k ¼:0 djksM+ esa½ | अगस्त 2021 rd dk O;; dh jkf'k ¼:0 djksM+ esa½ | Hkwfe miyC/k | fufonk vkeaf=r | fufonk fu"ikfnr | fufonk izfdz;k/khu | dqy LOA fuxZr | dk;kZns'k fuxZr | fuekZ.kk/khu ;kstukvksa dh la[;k | iw.kZ | dk;Z izkjaHk ugha | vfHk;qfDr
1 | ,0,u0,e0 Vssªfuax laLFkku ,oa Nk=kokl dk fuekZ.k dk;Z ¼izfr ;wfuV 6-30 djksM+½ |  | 54 | 340.58 | 219.75 | 259.67 | 53 | 53 | 52 | 1 | 52 | 52 | 12 | 39 | 1 | dk;Z izkjaHk ugha&iqijh] Hkwfe vuqiyC/k&rs?kM+k
2 | th0,u0,e0 Vssªfuax laLFkku ,oa Nk=kokl dk fuekZ.k dk;Z ¼izfr ;wfuV 13-35 djksM+½ |  | 23 | 307.13 | 185.68 | 217.84 | 22 | 22 | 22 | 0 | 22 | 21 | 7 | 13 | 1 | dk;Z izkjaHk ugha&vkSjaxkckn Hkwfe vuqiyC/k&csxwljk;
3 | ikjk esfMdy laLFkku dk fuekZ.k dk;Z ¼izfr ;wfuV 9-98 djksM+½ |  | 33 | 329.34 | 185 | 222.22 | 32 | 32 | 32 | 0 | 32 | 31 | 10 | 20 | 1 | dk;Z izkjaHk ugha&vkSjaxkckn Hkwfe vuqiyC/k&csxwljk;
4 | ch-,l-lh- uflZax dkWyst dk fuekZ.k dk;Z ¼izfr ;wfuV 26-49 djksM+½ |  | 16 | 423.96 | 188.44 | 136.14 | 14 | 12 | 12 | 0 | 12 | 12 | 7 | 4 | 1 | dk;Z izkjaHk ugha&PMCH(Dropped) Hkwfe vuqiyC/k&e/kqqcuh] csxwljk;
5 | fpfdRlk egkfo¦ky; dk fuekZ.k dk;Z | egqvk] oS'kkyh | 3 | 500 | 1 | 15.95 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Work Started
|  | csxqljk; |  | 515 | 40.7 | 1.29 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Financial bid to be opened
|  | vkjk] Hkkstiqj |  | 543.99 | 115.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Land available
| dqy |  | 129 | 2960 | 936.07 | 853.11 | 124 | 121 | 119 | 2 | 119 | 117 | 37 | 76 | 4

## ANM
PROJECT UNDER 7-Commitement
Construction of Auxiliary Nurse Midwifery Training Institute (A.N.M) (As on 30 Sep 2021)
S.N | Name of Places | District | A.A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | TENDER REFRENCE | Date of Receipt of Tender | Tender decided | LOA issued | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Farbisganj | Araria | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Topline Infra, Katihar | Yes | Yes | 24/07/2017 | 2017-11-11 | 2018-10-11 | 100% | Completed | Handed Over
2 | Jainagar | Madhubani | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Maa Tara Construction, Darbhanga | Yes | Yes | 28/06/2017 | 28/6/2017 | 27/06/2018 | 100% | Completed | Handed over
3 | Tarapur | Munger | 630.72 | Decoarch | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Lalan Kumar,Bhagalpur | Yes | Yes | 16/06/2017 | 2017-07-12 | 2018-06-12 | 100% | Completed | Handed Over
4 | Sonpur | Saran | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Kaushal buildcon,patna | Yes | Yes | 20/07/2017 | 2018-05-01 | 2019-04-01 | 100% | Completed | Handed over
5 | Neemchak Bathani | Gaya | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Anil Kumar Singh, Sasaram | Yes | yes | 2018-04-01 | 2018-04-01 | 2019-03-01 | 100% | Completed | Handed Over
6 | Manihari | Katihar | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Sudesh Kumar Singh, Jamui | Yes | Yes | 21/09/2017 | 21/9/2017 | 20/09/2018 | 100% | Completed | Handed Over
7 | Jagdispur | Bhojpur | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | YES | Ramesh kumar pandey | Yes | Yes | 2017-06-09 | 2017-06-09 | 2018-05-09 | 100% | Completed | Handed over
8 | Jhanjharpur | Madhubani | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Girdhari Lal Poddar,Darbhanga | Yes | Yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 100% | Completed | Handed over
9 | Narkatiyaganj | West Champaran | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Rama & Sons, Patna | Yes | yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 100% | Completed | Handed over
10 | Sikarhana | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | B.K.Chaudhary | Yes | yes | 2018-01-02 | 2018-01-02 | 31/01/2019 | 100% | Completed | Handed over
11 | Patori | Samastipur | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | YES | Binod Kumar Singh,Samastipur | Yes | Yes | 2017-09-10 | 13/1/2018 | 2019-12-01 | 100% | Completed | Handed over
12 | Dalsinghsarai | Samastipur | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Binod Kumar Singh,Samastipur | Yes | yes | 2017-09-10 | 2018-12-01 | 2019-11-01 | 100% | Completed | Handed over
13 | Banmankhi | Purnea | 630.72 | Decoarch | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Bambam Kumar Singh | Yes | Yes | 29/01/2018 | 29/1/2018 | 28/01/2019 | 100% | Completed | Handed Over
14 | Virpur | Supaul | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Kunal Kush, Araria | Yes | Yes | 20/07/2017 | 20/07/2017 | 19/07/2018 | 100% | Completed | Handed over
15 | Benipur | Darbhanga | 630.72 | EDMAC | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | Yes | 17/05/2018 | 15/7/2018 | 14/7/2019 | 100% | Completed | Handed over
16 | Chakia | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Asiana Contract Pvt. Ltd. | Yes | yes | 31/03/2018 | 31/03/2018 | 30/03/2019 | 100% | Completed | Handed over
17 | Bagha | West Champaran | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Shiva Infra Solution, New Delhi | Yes | Yes | 17/05/2017 | 17/05/2017 | 16/05/2018 | 100% | Completed | Handed over
18 | Benipatti | Madhubani | 630.72 | M/s Mass N Void | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 17/05/2018 | 17/5/2018 | 16/05/2019 | 100% | Completed | Handed Over
19 | Kahalgaon | Bhagalpur | 630.72 | Decoarch | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Ramesh Kumar, Patna | Yes | Yes | 15/03/2018 | 15/03/2018 | 14/03/2019 | 100% | Completed | Handed Over
20 | Mahnar | Vaishali | 630.72 | M/S Kapoor & Associates | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 28/12/2017 | 28/12/2017 | 27/12/2018 | 100% | Completed | Handed Over
21 | Bikramganj | Rohtas | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Rambabu Prasad,Patna | Yes | Yes | 27/02/2018 | 27/2/2018 | 25/02/2019 | 100% | Completed | Handed over
22 | Areraj | East Champaran | 630.72 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | S.K. Enterprises, Sitamarhi | Yes | Yes | 2017-02-12 | 2017-02-12 | 2018-01-12 | 100% | Completed | Handed Over
23 | Rosara | Samastipur | 630.72 | Archline Designs pvt ltd | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | yes | 29/06/2018 | 2018-01-07 | 30/06/2019 | 100% | Completed | Handed Over
24 | Gopalganj (APHC Baikunthpur) | Gopalganj | 630.72 | Kapoor & Associates | in process | TENDER Nit-18/2017 | 2017-09-04 | Yes | Yes | Baranwala Contractor Pvt.Ltd. | Yes | Yes | 15/03/2018 | 18/5/2018 | 17/5/2019 | 100% | Completed | Handed Over
25 | Arwal Sadar | Arwal | 630.72 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Ray, Dhanbad | Yes | Yes | 28/02/2018 | 28/2/2018 | 27/02/2020 | 100% | Completed | Handed Over
26 | Piro | Bhojpur | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Anil kumar,Rohtas | Yes | Yes | 2018-10-07 | 2018-10-07 | 2019-09-07 | 100% | Completed | Handed Over
27 | Biraul | Darbhanga | 630.72 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 2017-02-11 | 25/02/2019 | 24/02/2020 | 100% | Completed | Handed over
28 | Belsand | Sitamarhi | 630.72 | Archline Designs pvt ltd | in process | Nit-39/2017 | 2018-01-05 | Yes | Yes | Kabbu Khirhar, Sitamarhi | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 100% | Completed | Handed Over
29 | Simri Bakhtiyarpur | Saharsa | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | SHANTOSH KUMAR SINGH,SAHARSA | yes | Yes | 14/07/2017 | 2018-10-02 | 2019-09-02 | 100% | Completed | Handed over
30 | Nirmali | Supaul | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | SHANTOSH KUMAR SINGH,SAHARSA | Yes | Yes | 16/06/2017 | 2018-01-02 | 31/1/2019 | 100% | Completed | Handed over
31 | Barsoi (SDH Campus) | Katihar | 630.72 | Kapoor & Associates | in process | Retender Nit-39/2017 | 2018-01-05 | Yes | Yes | Krishnakant Thakur | Yes | Yes | 2019-06-03 | 2019-06-03 | 2020-05-03 | 100% | Completed | Handed Over
32 | Sherghati | Gaya | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Ambey infra,patna | Yes | yes | 2017-02-11 | 30/12/2017 | 29/12/2018 | 100% | Completed | Handed Over
33 | Mahua (CHC Rajapakar) | Vaishali | 630.72 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Indra Narayan Singh,Patna | Yes | Yes | 25/09/2018 | 25/9/2018 | 24/09/2020 | 100% | Completed | Handed Over
34 | Tekari | Gaya | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Mukesh Kumar, Gaya | Yes | Yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 100% | Completed | Used for quarantine
35 | Uda Kishanganj | Madhepura | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | C S CONSTRUCTION, Arariya | Yes | Yes | 2017-05-05 | 2017-03-06 | 2018-02-06 | 100% | Completed | Handed over
36 | Haveli Khargpur | Munger | 630.72 | Decoarch | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Naushad Ali | yes | Yes | 22/06/2019 | 22/06/2019 | 21/06/2020 | 100% | Completed | Handed Over | Wapcos
37 | Madhaura | Saran | 630.72 | M/S Kapoor & Associates | Submitted | Retender Nit-03/2019 | 23.09.2016 | Yes | Yes | Ramesh kumar pandey | yes | Yes | 28/05/2020 | 28/05/2020 | 27/05/2021 | 100% | Completed | Handed Over
38 | Paliganj | Patna | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Sanjeev Kumar | Yes | yes | 2020-10-01 | 2020-10-05 | 2021-09-05 | 100% | Completed | Handed Over
39 | Pakri Dayal | East Champaran | 630.72 | Mass-N-Void | Submitted | Retender Nit-39, Dated-02/12/2016 | 2018-05-01 | Yes | Yes | M/s Hariom Construction, East Champaran | Yes | Yes | 2019-02-03 | 2019-02-03 | 31/12/2020 | 100% | Completed
40 | Bakhri | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | yes | 13/02/2018 | 2018-02-11 | 2019-01-11 | 98% | Finishing work is in progress | Contractor debarred, Work stopped | Wapcos
41 | Baliya | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | yes | 2018-12-02 | 20/07/2018 | 19/07/2019 | 98% | Finishing work is in progress | Contractor debarred Work stopped | Wapcos
42 | Gogari | Khagaria | 630.72 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Arvind Kumar singh, Danapur | Yes | Yes | 2018-12-01 | 2018-12-01 | 2019-11-01 | 95% | Finishing work is in progress | Contractor debarred
43 | Sukhpur | Supaul | 630.72 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Arvind Kumar singh, Danapur | Yes | yes | 22/10/2017 | 15/02/2019 | 31/12/2020 | 98% | Finishing work
44 | Raxaul | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2018-01-05 | Yes | Yes | M/s Hariom Construction, East Champaran | Yes | Yes | 2019-02-03 | 2019-02-03 | 31/12/2020 | 92% | Finishing work is going on | Contractor has been debarred
45 | Madhepura | Madhepura | 630.72 | Suresh Goel & Associates | in process | TENDER Nit-18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 31/03/2018 | 20/5/2018 | 25/08/2021 | 86% | Hostel-Finishing work, Academic Block-Finishing work | Contractor debarred
46 | Manjhaul | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | Yes | 13/02/2018 | 26/11/2019 | 25/11/2020 | 90% | Finishing work is in progress | Contractor debarred Work stopped | Wapcos
47 | Navgachia | Bhagalpur | 630.72 | Sen & Lall | in process | Retender Nit-39/2017 | 2018-01-05 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | Yes | 2019-08-03 | 2020-04-01 | 2021-03-01 | 70% | Finishing work is going on | Contractor Debarred
48 | Araria | Araria | 630.72 | Arch-En-Design | Submitted | Nit-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | Yes | Shrinath builder,Patna | Yes | yes | 24/03/2017 | 2018-02-04 | 2021-02-10 | 42% | Academic Block: Roof casted (3rd.F) Hostel Block: Roof Shuttering (G.F) | Contractor debarred vide Letter no-971, Dated-16/07/2019
49 | Phulparas | Madhubani | 630.72 | M/s Mass N Void | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | Yes | 28/04/2018 | 24/03/2020 | 19/07/2021 | 90% | Academic Block: -Finishing work Hostel work- -Finishing work
50 | Dhamdaha | Purnea | 630.72 | Decoarch | Submitted | Retender Nit-35/2019 | - | Yes | Yes | Krishnakant Thakur | Yes | Yes | 21/09/2020 | 21/09/2020 | 20/12/2021 | 50% | Academic Block: Column work (F.F) Hostel work- Brick work | EOT granted upto 04.04.2022
51 | Baisi | Purnea | 630.72 | Decoarch | Submitted | Retender Nit-35/2019 | - | Yes | Yes | Krishnakant Thakur | Yes | Yes | 21/09/2020 | 21/09/2020 | 20/12/2021 | 70% | Academic Block: Finishing work Hostel Block- Finishing work | EOT granted upto 17.02.2022
52 | Pupri | Sitamarhi | 630.72 | Archline Designs pvt ltd | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | No | 17/05/2018 | NS | 16/05/2019 |  |  | Land available on 01.04.2021, Water logging
53 | Dumrao | Buxar | 630.72 | Kapoor & Associates | in process | - | - | No | No | - | No | - | - | - | - | - |  | In Tender
54 | Teghra | Begusarai | 630.72 | EDMAC | Submitted | - | - | - | - | - | - | - | - | - | - | - | Many tree available on proposed site
|  | Total | 34058.88
Sl. No. | Abstract
1 | Land not available |  | 1 |  |  | Teghra
2 | Work not started |  | 6 |  |  | Pupri

## GNM
PROJECT UNDER 7-Commitement
Construction of General Nurse Midwifery Institute (G.N.M) (As on 30 Sep 2021)
S.N | District | Place of construction | A. A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Date of Receipt of Tender | Tender decided | LOA ISSUED | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Munger | Leprosy Hospital Munger | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | LALAN KUMAR | Yes | Yes | 24/3/2017 | 24/03/2017 | 23/9/2018 | 100% | Completed | Handed Over
2 | Jamui | Vill-Mahuli | 1335.38 | Arch-N-Design | In Process | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | SUDESH KUMAR SINGH | Yes | Yes | 2018-12-02 | 2018-12-02 | 2019-11-08 | 100% | Completed | Handed Over
3 | Arwal | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Ray, Dhanbad | Yes | Yes | 28/02/2018 | 28/02/2018 | 27/02/2020 | 100% | Completed | Handed Over
4 | Bhabhua | Barka Katra | 1335.38 | DDF | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Yashaswi Infrastructure, Ranchi | Yes | Yes | 2018-04-05 | 2018-04-05 | 2019-03-08 | 100% | Completed | Handed Over
5 | Madhubani | Raghopur Balath | 1335.38 | Sen & Lall consultants pvt ltd | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | SKS-KKT JV | Yes | Yes | 17/07/2018 | 17/07/2018 | 16/01/2020 | 100% | Completed | Handed Over
6 | Gopalganj | SDH, Hathua | 1335.38 | Design Associates | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | AIPLGMC, JOINT VENTURE | Yes | Yes | 2018-01-02 | 2018-01-02 | 31/8/2019 | 100% | Completed | Handing Over
7 | Siwan | SDH Mahrajganj | 1335.38 | Mass-N-Void | In Process | RETENDER NIT-18/2017 | 2017-09-04 | Yes | Yes | B. Prasad | Yes | Yes | 2018-08-05 | 2018-08-05 | 2019-07-11 | 100% | Completed | Handing Over
8 | Khagaria | Old Sub divisional Hospital | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | MACRO RANJAN | Yes | Yes | 24/3/2017 | 24/03/2017 | 23/9/2018 | 100% | Completed | Letter send for Handing over
9 | Supaul | VILL -Sukhpur | 1335.38 | EDMAC | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Ashok Kumar | Yes | Yes | 29/05/2018 | 29/05/2018 | 28/11/2019 | 100% | Completed | Handed Over
10 | Vaishali | CHC Rajapakar | 1335.38 | Arch-N-Design | In Process | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | INDRA NARAIN SINGH | Yes | Yes | 25/09/2018 | 25/09/2018 | 24/09/2020 | 100% | Completed | Handed Over
11 | Lakhisarai | Noongarh | 1335.38 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | KANHAIYA CONTRACTOR, BEGUSARAI | Yes | Yes | 2018-07-12 | 2018-07-12 | 2019-06-12 | 100% | Completed | Handed Over
12 | East Champaran | Sadar Hospital | 1335.38 | Design Associates | Submitted | RETENDER NIT-18/2017 | 2017-09-04 | Yes | Yes | Rama Construction | Yes | Yes | 2019-02-03 | 2019-02-03 | 31/12/2020 | 100% | Completed | Handing Over
13 | Katihar | Ward no-04, | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | ADYARAJ DEVELOPER | Yes | Yes | 26/04/2017 | 25/11/2018 | 31/07/2021 | 100% | Completed
14 | Nalanda | Pavapuri Medical College Campus | 1335.38 | Arch-N-Design | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 28/04/2018 | 28/04/2018 | 31/03/2021 | 85% | Finishing work is in progress | Contractor debarred
15 | Nawada | Budhaul | 1335.38 | Arch-N-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | Dhanpat prasad | Yes | Yes | 29/01/2018 | 29/1/2018 | 25/03/2021 | 60% | Plaster work is going on | Contractor debar from 10.06.2019
16 | Bhojpur | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Siemens Construction | Yes | Yes | 29/05/2018 | 29/05/2018 | 30/04/2021 | 55% | Hostel-Roof shuttering (2nd.F), Academic- Finishing work is going on | Contractor Debarred
17 | Sitamarhi | Madhuban | 1335.38 | Mass-N-Void | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | Shashikant Singh | Yes | Yes | 2019-02-03 | 2019-02-03 | 17/10/2021 | 95% | Finishing work
18 | Kishanganj | Motihara | 1335.38 | Arch-N-Design | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | Shafique Alam | Yes | Yes | 2018-03-04 | 17/11/2019 | 28/06/2021 | 95% | Finishing work
19 | Araria | Araria | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | SRINATH BUILDER | Yes | Yes | 24/03/2017 | 2018-02-04 | 2021-02-10 | 42% | Academic Block: Roof casted (3rd.F) Hostel Block: Roof Shuttering (G.F) | Contractor debar vide Letter no-971, Dated-16/07/2019
20 | Samastipur | Sarairanjan | 1335.38 | DDF Consultant pvt ltd | In Process | Tender Nit-06/2020 | - | Yes | Yes | Arun Kumar | Yes | Yes | 28.05.2021 | 28.05.2021 | 27.05.2023 | 4% | Foundation work is going on | Work rescind
21 | Aurangabad | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | Retender Nit-35/2019 | 2017-07-05 | Yes | Yes | Prasad Associate | Yes | No | 2021-06-01 | 2022-05-07 | - | 0% | Not Started | Water Logging
22 | Sheohar | - | 1335.38 | DDF Consultant pvt ltd | Submitted | - | - | Yes | Yes | - | No | No | - | - | - |  | Not Started | Retender to be invited
23 | Begusarai |  | 1335.38 | DDF | Submitted |  | 2017-09-04 | No | No | - | No | No | - | - | - |  | Land not available
|  | Total | 30713.74
Sl. No. | Abstract
1 | Land not available |  |  | 0 |  | 1 |  | Begusarai
2 | Work order to be issued |  |  |  |  | 2 |  | Sheohar

## Para Medical
PROJECT UNDER 7-Commitement
Construction of Para Medical Institute (As on 30 Sep 2021)
S.N | District | Place of construction | A. A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Date of Receipt of Tender | Tender decided | LOA Issued | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Banka | Sadar Hospital (Old Campus) | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | RANA CONSTRUCTION | YES | Yes | 2017-05-05 | 2017-05-05 | 2018-04-06 | 100% | Completed | Handed over
2 | Buxar | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | B PRASAD &COMPANY | YES | Yes | 2017-07-08 | 25/11/2017 | 24/2/2019 | 100% | Completed | Handed over
3 | Rohtas | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | RAMESH PANDEY | YES | Yes | 2017-05-08 | 2017-05-08 | 2018-04-11 | 100% | Completed | Handed over
4 | Gopalganj | SDH Hathwa | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | Yes | G M CONSTRUCTION | YES | Yes | 31/3/2017 | 15/1/2018 | 14/4/2019 | 100% | Completed | Handed over
5 | Munger | Leprosy Hospital Munger | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | LALAN KUMAR | YES | Yes | 24/3/2017 | 24/3/2017 | 23/09/2018 | 100% | Completed | Handed Over
6 | Saharsa | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | C S CONSTRUCTION | YES | Yes | 31/3/2017 | 2018-12-03 | 2019-11-08 | 100% | Completed | Handed over
7 | Lakhisarai | Nungarh | 998 | Designer's Wing | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | KANHAIYA CONSTRUCTION, BEGUSARAI | Yes | Yes | 2018-12-09 | 2018-12-09 | 2019-11-06 | 100% | Completed
8 | Jamui | Vill-Mahuli | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | SUDESH KUMAR SINGH | Yes | Yes | 2018-12-02 | 2018-12-02 | 2019-11-08 | 100% | Completed | Handed Over
9 | Arwal | Sadar Hospital | 998 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Rai, Dhanbad | Yes | Yes | 28/02/2018 | 28/02/2018 | 27/02/2020 | 100% | Completed | Handed over
10 | Saran | Sadar Hospital Chhapra | 998 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | G M CONSTRUCTION, SIWAN | Yes | Yes | 2018-04-05 | 20/7/2018 | 19/10/2019 | 100% | Completed | Handed over
11 | Siwan | Sub-Divisional hospital, Maharajganj | 998 | Mass-N-Void | Submitted | RE TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | B. Prasad | Yes | Yes | 2018-08-05 | 2018-08-05 | 2019-07-11 | 100% | Completed | Handed over
12 | Khagaria | Old Subdivisional Hospital | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | MACRO RANJAN | YES | Yes | 24/3/2017 | 24/3/2017 | 23/09/2018 | 100% | Completed | Letter send for Handing over
13 | Madhubani | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | SANJAY KUMAR | YES | Yes | 2017-09-05 | 2018-01-11 | 28/02/2020 | 100% | Completed | Handed over
14 | Vaishali | Rajapakar | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | INDRA NARAIN SINGH | Yes | Yes | 25/09/2018 | 25/09/2018 | 24/09/2020 | 100% | Completed | Handed over
15 | East Champaran | Sadar Hospital | 998 | Design Associates Inc. | Submitted | RETENDER NIT 18/2017 | 2017-09-04 | Yes | YES | Rama Construction | Yes | Yes | 2019-02-03 | 2019-02-03 | 31/12/2020 | 100% | Completed | Handing Over
16 | Supaul | Supaul | 998 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | YES | YES | INDRA NARAIN SINGH, PATNA | Yes | Yes | 28/11/2018 | 28/11/2018 | 30/10/2020 | 100% | Completed | Handed over
17 | Bhabhua | Sarangpur | 998 | DDF | Submitted | RE TENDER NIT 39/2017 | 2018-01-05 | Yes | Yes | Ajay Kumar Singh | Yes | Yes | 26/10/2018 | 20/01/2019 | 30/11/2020 | 100% | Completed
18 | Jehanabad | Referral Hospital Ghosi | 998 | Designer's Wing | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | KAUSHLENDRA KUMAR | Yes | Yes | 2019-02-03 | 2019-02-03 | 30/12/2020 | 100% | Completed | Handed over
19 | Sheikhpura | Makhdumpur PHC | 998 | Designer's Wing | Submitted | NIT 39/2017 | 2018-01-05 | Yes | YES | Sanjay Kumar Technocrat | Yes | Yes | 2018-07-12 | 2018-07-12 | 31/12/2020 | 100% | Completed
20 | Katihar | Sadar Hospital | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | ADYARAJ DEVELOPER | Yes | Yes | 26/4/2017 | 25/11/2018 | 31/07/2021 | 100% | Completed
21 | West Champaran | Sadar Hospital | 998 | DDF | Submitted | Nit-15, Dated-10/06/2016 | 15/7/2016 | Yes | YES | L& T CONSTRUCTION | YES | Yes | 2017-10-07 | 2017-10-07 | 2021-09-03 | 95% | Academic- Completed Hostel-Finishing work is going on
22 | Purnea | Sadar Hospital Purnea | 998 | Design Associates Inc. | Submitted | Nit-26, Dated-03/08/2016 | 2016-09-19 | Yes | YES | UMAKANT SINGH | YES | Yes | 31/3/2017 | 2017-01-11 | 30/3/2021 | 95% | Academic Block: Finishing work Hostel Block: Completed
23 | Nawada | Budhaul | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | DHANPAT PRASAD | Yes | Yes | 29/01/2017 | 29/01/2017 | 25/03/2021 | 60% | Plaster work is going on | Contractor debar from 10.06.2019
24 | Bhojpur | Sadar Hospital | 998 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | YES | Siemens Construction | Yes | Yes | 29/05/2018 | 29/5/2018 | 30/04/2021 | 55% | Hostel-Roof shuttering (2nd.F), Academic- Finishing work is going on | Contractor Debarred
25 | Nalanda | Pavapuri Medical College Campus | 998 | Arch-En-Design | Submitted | TENDER NIT 18/2017 | 2017-09-04 | Yes | YES | M/s Satyanarayan Singh | Yes | Yes | 28/04/2018 | 28/04/2018 | 31/03/2021 | 85% | Finishing work is in progress | Contractor has been debarred
26 | Madhepura | Parariya | 998 | Suresh Goel & Associates | in process | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 31/03/2018 | 20/5/2018 | 25/08/2021 | 86% | Hostel-Finishing work, Academic Block-Finishing work | Contractor debarred
27 | Kishanganj | Motihara | 998 | Arch-En-Design | in process | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | Shafique Alam | Yes | Yes | 31/03/2018 | 17/11/2019 | 28/06/2021 | 95% | Finishing work
28 | Araria | Araria | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | SRINATH BUILDER | YES | Yes | 24/03/2017 | 2018-02-04 | 2021-02-10 | 42% | Academic Block: Roof casted (3rd.F) Hostel Block: Roof Shuttering (G.F) | Contractor debar vide Letter no-971, Dated-16/07/2019
29 | Samastipur | Sarairanjan | 998 | DDF | NOT SUBMITTED | - | - | No | yes | Arun Kumar | yes | yes | 28.05.2021 | 28.05.2021 | 27.05.2023 | 4% | Foundation work is going on | Work rescind
30 | Sitamarhi | Padri | 998 | Designer's Wing | Submitted | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | Shashikant Singh | Yes | Yes | 2020-08-01 | 2020-08-01 | 30/04/2022 | 10% | Work is going on | work stopped due to Water Logging
31 | Aurangabad | Sadar Hospital | 998 | Arch-En-Design | Submitted |  | 2017-07-05 | No | YES | Prasad Associate | YES | No | 2021-06-01 | 2022-05-07 | - | - | Not Started | Water Logging
32 | Sheohar | Sadar Hospital | 998 | DDF Consultant pvt ltd | Submitted | RE TENDER NIT 5/2018 | 2018-01-05 | Yes | Yes | Birendra Kumar Chaudhary | No | No |  |  |  |  | Not Started | Retender to be invited
33 | Begusarai | - | 998 | DDF | NOT SUBMITTED | - | - | No | No |  | No | No |  |  |  |  | Land not available
|  | Total | 20958
Sl. No. |  | Abstract
1 |  | Work order to be issued |  | 2 |  | Sheohar
2 |  | Land not available |  | 2 |  | Begusarai

## B.SC
PROJECT UNDER 7-Commitement
B.Sc Nursing College (As on 30 Sep 2021)
S.N | Name of Places | District | Land available or not | Administrative Approval Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress in Percentage | Remarks
1 | PMCH, Patna | Patna | No | 2649.76 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | No | 18/08/2017 | NS | 17/08/2019 | - | Work is kept on hold because of PMCH redevelopment
2 | JLNMCH, Bhagalpur | Bhagalpur | Yes | 2649.76 | Arch-En-Design | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed & Handed Over
3 | Vardhaman Ayurvigyan Sansthan, Pawapuri | Nalanda | Yes | 2649.76 | Arch-En-Design | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed & Handed Over
4 | DMCH, Laheriasarai | Darbhanga | Yes | 2649.76 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed & Handed Over
5 | ANMMCH, Gaya | Gaya | Yes | 2649.76 | Design Associate Inc. | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 2017-05-05 | 2017-05-05 | 30/12/2020 | 100% | Completed & Handed Over
6 | SKMCH, Muzaffarpur | Muzaffarpur | Yes | 2649.76 | DDF | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 31/12/2020 | 92% | Finishing work is in progress
7 | Govt. Medical College, Bettiah | Bettiah | Yes | 2649.76 | DDF | Submitted | Nit-15, Dated-10/06/2016 | Yes | Yes | 2017-10-07 | 2017-10-07 | 2021-09-03 | 82% | Hostel- Completed, Academic-Finishing work
8 | Govt. Medical College, Purnea (Sadar Hospital Campus) | Purnea | Yes | 2649.76 | Design Associate Inc. | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 2017-01-11 | 30/3/2021 | 95% | Academic Block: Finishing work Hostel Block: Completed
9 | Govt. Medical College, Chhapra | Chhapra | Yes | 2649.76 | Suresh Goel & Associates | In Process | . | Yes | Yes | 28/2/2019 | 28/2/2019 | 27/02/2022 | 55% | Column work (7th Floor)
10 | Govt. Medical College, Samastipur | Samastipur | Yes | 2649.76 | DDF | Submitted | Nit-06/2020 | Yes | Yes | 28.05.2021 | 28.05.2021 | 27.05.2023 | 4% | Work rescind
11 | Govt. Medical College, Mahua | Vaishali | Yes | 2649.76 | - | - | Nit-22/2019 | yes | Yes | 22/09/2020 | - | 21/09/2023 | - | Work is going on (10%)
12 | Govt. Medical College, Sitamarhi | Sitamarhi | Yes | 2649.76 | - | - | Nit-22/2019 | Yes | Yes | 18/07/2020 | - | 17/07/2023 | - | Work started
13 | Govt. Medical College, Madhepura | Madhepura | Yes | 2649.76 | EDMAC | In Process | - | - | - | - | - | - | - | Tender to be invited
14 | Govt. Medical College, Ara | Bhojpur | Yes | 2649.76 | - | - | - | - | - | - | - | - | - | will be tender along with GMCH
15 | Govt. Medical College, Begusarai | Begusarai | No | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
16 | Govt. Medical College, Madhubani | Madhubani | No | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
|  | Total |  | 42396.16 | - | - | - | - | - | - | - | - | -
Sl. No. | Abstract
1 | Land to be decided |  |  |  |  | 2 |  | Begusarai & Madhubani