## Abstract
fcgkj fpfdRlk lsok,¡ ,oa vk/kkjHkwr lajpuk fuxe- fy-
ekuuh; eq[;ea=h ds 7& fu'p; ds varxZr izLrkfor ifj;kstukvksa dk v¦ru ¼31tuojh 2020½ rd izxfr izfrosnu
Øe la[;k | ;kstuk dk uke |  | dqy Lohd`r ;kstukvksa dh la[;k | iz'kklfud Lohd`fr dh jkf'k ¼:0 djksM+ esa½ | vkoaVu dh jkf'k ¼:0 djksM+ esa½ | दिसम्बर 2019 rd dk O;; dh jkf'k¼:0 djksM+ esa½ | Hkwfe miyC/k | fufonk vkeaf=r | fufonk fu"ikfnr | fufonk izfdz;k/khu | dqy LOA fuxZr | dk;kZns'k fuxZr | fuekZ.kk/khu ;kstukvksa dh la[;k | iw.kZ | dk;Z izkjaHk ugha | vfHk;qfDr
1 | ,0,u0,e0 Vssªfuax laLFkku ,oa Nk=kokl dk fuekZ.k dk;¼izfr ;wfuV 6-30 djksM+½ |  | 54 | 340.58 | 219.75 | 186.05 | 52 | 52 | 50 | 2 | 50 | 49 | 23 | 24 | 1 | ok;lh ,oa /kenkgk gsrq fufonk izfØ;k/khu
2 | th0,u0,e0 Vssªfuax laLFkku ,oa Nk=kokl dk fuekZ.k dk; ¼izfr ;wfuV 13-35 djksM+½ |  | 23 | 307.13 | 170 | 135.75 | 22 | 21 | 20 | 1 | 20 | 19 | 17 | 2 | 0 | vkSjaxkckn& fufonk izfØ;k/khu
3 | ikjk esfMdy laLFkku dk fuekZ.k dk;Z ¼izfr ;wfuV 9-98 djksM+½ |  | 33 | 329.34 | 185 | 137.87 | 32 | 31 | 30 | 1 | 30 | 29 | 21 | 8 | 0 | vkSjaxkckn& fufonk izfØ;k/khu
4 | ch-,l-lh- uflZax dkWyst dk fuekZ.k dk;Z ¼izfr ;wfuV 26-49 djksM+½ |  | 16 | 423.96 | 180 | 96.54 | 12 | 11 | 10 | 1 | 10 | 9 | 5 | 3 | 1 | 1. Tender under process- Sitamarhi 2. PMCH Dropped
5 | fpfdRlk egkfo¦ky; dk fuekZ.k dk;Z | egqvk] oS'kkyh | 3 | 500 | 1 | 1.19 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | LOA issued
|  | csxqljk; |  | 515 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial bid to be opened
|  | vkjk] Hkkstiqj |  | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Land not available
| dqy |  | 129 | 2816.01 | 755.75 | 557.4 | 120 | 117 | 111 | 5 | 111 | 106 | 66 | 37 | 2

## ANM
PROJECT UNDER 7-Commitement
Construction of Auxiliary Nurse Midwifery Training Institute (A.N.M) (As on 31st Jan 2020)
S.N | Name of Places | District | A.A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | TENDER REFRENCE | Date of Receipt of Tender | Tender decided | LOA ISSUED | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Farbisganj | Araria | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Topline Infra, Katihar | yes | Yes | 24/07/2017 | 2017-11-11 | 2018-10-11 | 100% | Completed | Handed Over
2 | Jainagar | Madhubani | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Maa Tara Construction, Darbhanga | yes | Yes | 28/06/2017 | 28/6/2017 | 27/06/2018 | 100% | Completed | Handed over
3 | Tarapur | Munger | 630.72 | Decoarch | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Lalan Kumar,Bhagalpur | Yes | Yes | 16/06/2017 | 2017-07-12 | 2018-06-12 | 100% | Completed | Handed Over
4 | Sonpur | Saran | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Kaushal buildcon,patna | Yes | Yes | 20/07/2017 | 2018-05-01 | 2019-04-01 | 100% | Completed | Handed over
5 | Neemchak Bathani | Gaya | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Anil Kumar Singh, Sasaram | Yes | yes | 2018-04-01 | 2018-04-01 | 2019-03-01 | 100% | Completed | Handed over
6 | Manihari | Katihar | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Sudesh Kumar Singh, Jamui | Yes | Yes | 21/09/2017 | 21/9/2017 | 20/09/2018 | 100% | Completed | Handed Over
7 | Jagdispur | Bhojpur | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | YES | Ramesh kumar pandey | Yes | Yes | 2017-06-09 | 2017-06-09 | 2018-05-09 | 100% | Completed | Handed over
8 | Jhanjharpur | Madhubani | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Girdhari Lal Poddar,Darbhanga | Yes | Yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 100% | Completed | Handed over
9 | Narkatiyaganj | West Champaran | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Rama & Sons, Patna | Yes | yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 100% | Completed | Handed over
10 | Sikarhana | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | B.K.Chaudhary | Yes | yes | 2018-01-02 | 2018-01-02 | 31/01/2019 | 100% | Completed | Handed over
11 | Patori | Samastipur | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | YES | Binod Kumar Singh,Samastipur | Yes | Yes | 2017-09-10 | 13/1/2018 | 2019-12-01 | 100% | Completed | Handed over
12 | Dalsinghsarai | Samastipur | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Binod Kumar Singh,Samastipur | Yes | yes | 2017-09-10 | 2018-12-01 | 2019-11-01 | 100% | Completed | Handed over
13 | Banmankhi | Purnea | 630.72 | Decoarch | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Bambam Kumar Singh | Yes | Yes | 29/01/2018 | 29/1/2018 | 28/01/2019 | 100% | Completed
14 | Virpur | Supaul | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Kunal Kush, Araria | Yes | Yes | 20/07/2017 | 20/07/2017 | 19/07/2018 | 100% | Completed | Handed over
15 | Benipur | Darbhanga | 630.72 | EDMAC | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | Yes | 17/05/2018 | 15/7/2018 | 14/7/2019 | 100% | Completed | Handed over
16 | Chakia | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Asiana Contract Pvt. Ltd. | Yes | yes | 31/03/2018 | 31/03/2018 | 30/03/2019 | 100% | Completed
17 | Bagha | West Champaran | 630.72 | M/s Mass N Void | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Shiva Infra Solution, New Delhi | Yes | Yes | 17/05/2017 | 17/05/2017 | 16/05/2018 | 100% | Completed
18 | Benipatti | Madhubani | 630.72 | M/s Mass N Void | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 17/05/2018 | 17/5/2018 | 16/05/2019 | 100% | Completed | Handed Over
19 | Kahalgaon | Bhagalpur | 630.72 | Decoarch | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Ramesh Kumar, Patna | Yes | Yes | 15/03/2018 | 15/03/2018 | 14/03/2019 | 100% | Completed | Handed Over
20 | Mahnar | Vaishali | 630.72 | M/S Kapoor & Associates | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 28/12/2017 | 28/12/2017 | 27/12/2018 | 100% | Completed | Handed Over
21 | Bikramganj | Rohtas | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Rambabu Prasad,Patna | Yes | Yes | 27/02/2018 | 27/2/2018 | 25/02/2019 | 100% | Completed
22 | Areraj | East Champaran | 630.72 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | S.K. Enterprises, Sitamarhi | Yes | Yes | 2017-02-12 | 2017-02-12 | 2018-01-12 | 100% | Completed | Handed Over
23 | Rosara | Samastipur | 630.72 | Archline Designs pvt ltd | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | yes | 29/06/2018 | 2018-01-07 | 30/06/2019 | 100% | Completed | Handed Over
24 | Gopalganj (APHC Baikunthpur) | Gopalganj | 630.72 | Kapoor & Associates | in process | TENDER Nit-18/2017 | 2017-09-04 | Yes | Yes | Baranwala Contractor Pvt.Ltd. | Yes | Yes | 15/03/2018 | 18/5/2018 | 17/5/2019 | 100% | Completed | Handed Over
25 | Araria | Araria | 630.72 | Arch-En-Design | Submitted | Nit-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | Yes | Shrinath builder,Patna | Yes | yes | 24/03/2017 | 2018-02-04 | 2020-01-04 | 13% | Academic block- G.F (Column casted) Hostel Block- Layout | Contractor debar vide Letter no-971, Dated-16/07/2019
26 | Uda Kishanganj | Madhepura | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | C S CONSTRUCTION, Arariya | Yes | Yes | 2017-05-05 | 2017-03-06 | 2018-02-06 | 80% | Finishing work
27 | Simri Bakhtiyarpur | Saharsa | 630.72 | EDMAC | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | SHANTOSH KUMAR SINGH,SAHARSA | yes | Yes | 14/07/2017 | 2018-10-02 | 2019-09-02 | 96% | Finishing work
28 | Nirmali | Supaul | 630.72 | M/S Kapoor & Associates | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | SHANTOSH KUMAR SINGH,SAHARSA | Yes | Yes | 16/06/2017 | 2018-01-02 | 31/1/2019 | 85% | Finishing work
29 | Biraul | Darbhanga | 630.72 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Kunwar Construction, Darbhanga | Yes | yes | 2017-02-11 | 25/02/2019 | 24/02/2020 | 85% | Finishing work is in progress
30 | Tekari | Gaya | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Mukesh Kumar, Gaya | Yes | Yes | 2017-07-11 | 2017-07-11 | 2018-06-11 | 88% | Finishing work is in progress | Contractor debbared vide letter no 5214, Dated-03.12.2019
31 | Gogari | Khagaria | 630.72 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Arvind Kumar singh, Danapur | Yes | Yes | 2018-12-01 | 2018-12-01 | 2019-11-01 | 80% | Finishing work is in progress
32 | Piro | Bhojpur | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Anil kumar,Rohtas | Yes | Yes | 2018-10-07 | 2018-10-07 | 2019-09-07 | 95% | Finishing work is in progress
33 | Sherghati | Gaya | 630.72 | Sen & Lall | Submitted | Nit-28, Dated-03/08/2016 | 23.09.2016 | Yes | Yes | Ambey infra,patna | Yes | yes | 2017-02-11 | 30/12/2017 | 29/12/2018 | 95% | Finishing work is in progress
34 | Sukhpur | Supaul | 630.72 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Arvind Kumar singh, Danapur | Yes | yes | 22/10/2017 | 15/02/2019 | 14/02/2020 | 40% | Brick work (F.F)
35 | Mahua (CHC Rajapakar) | Vaishali | 630.72 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Indra Narayan Singh,Patna | Yes | Yes | 25/09/2018 | 25/9/2018 | 24/09/2020 | 75% | Finishing work is in progress
36 | Pakri Dayal | East Champaran | 630.72 | Mass-N-Void | Submitted | Retender Nit-39, Dated-02/12/2016 | 2018-05-01 | Yes | Yes | M/s Hariom Construction, East Champaran | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 40% | Brick work is going on
37 | Arwal Sadar | Arwal | 630.72 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Ray, Dhanbad | Yes | Yes | 28/02/2018 | 28/2/2018 | 27/02/2020 | 98% | Finishing work is in progress
38 | Bakhri | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | yes | 13/02/2018 | 2018-02-11 | 2019-01-11 | 85% | Finishing work is in progress
39 | Baliya | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | yes | 2018-12-02 | 20/07/2018 | 19/07/2019 | 85% | Finishing work is in progress
40 | Raxaul | East Champaran | 630.72 | Mass-N-Void | in process | Nit-17/2017 | 2018-01-05 | Yes | Yes | M/s Hariom Construction, East Champaran | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 40% | Brick work is going on
41 | Madhepura | Madhepura | 630.72 | Suresh Goel & Associates | in process | TENDER Nit-18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 31/03/2018 | 20/5/2018 | 19/11/2019 | 25% | Girl's Hostel-Brick work, Boys Hostel- Roof shuttering (Terrace.F)
42 | Belsand | Sitamarhi | 630.72 | Archline Designs pvt ltd | in process | Nit-39/2017 | 2018-01-05 | Yes | Yes | Kabbu Khirhar, Sitamarhi | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 65% | Hostel block-Finishing work Academic Block-Plaster work
43 | Barsoi (SDH Campus) | Katihar | 630.72 | Kapoor & Associates | in process | Retender Nit-39/2017 | 2018-01-05 | Yes | Yes | Krishnakant Thakur | Yes | Yes | 2019-06-03 | 2019-06-03 | 2020-05-03 | 46% | Brick work is going on
44 | Haveli Khargpur | Munger | 630.72 | Decoarch | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Naushad Ali | yes | Yes | 22/06/2019 | 22/06/2019 | 21/06/2020 | 35% | Hostel Block-Finishing work
45 | Navgachia | Bhagalpur | 630.72 | Sen & Lall | in process | Retender Nit-39/2017 | 2018-01-05 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | Yes | 2019-08-03 | 2020-04-01 | 2021-03-01 | 10% | Foundation work
46 | Phulparas | Madhubani | 630.72 | M/s Mass N Void | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | Yes | 28/04/2018 | 2019-08-09 | 2020-07-09 | 1% | Work started | Work stopped due to water logged
47 | Manjhaul | Begusarai | 630.72 | Decoarch | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Satyanarayan Singh, Deoghar | Yes | Yes | 13/02/2018 | 26/11/2019 | 25/11/2020 | 20% | Column Work (G.F)
48 | Pupri | Sitamarhi | 630.72 | Archline Designs pvt ltd | in process | Nit-17/2017 | 2017-08-04 | Yes | Yes | Sanjay Kumar, Darbhanga | Yes | No | 17/05/2018 | NS | 16/05/2019 |  |  | Permission of District council is requierd
49 | Paliganj | Patna | 630.72 | Sen & Lall | Submitted | Nit-38, Dated-27/10/2016 | 2016-12-29 | Yes | Yes | Sanjeev Kumar | Yes | No | 2020-10-01 | NS | 2021-09-01 | - |  | Land clearence is in process
50 | Madhaura | Saran | 630.72 | M/S Kapoor & Associates | Submitted | Retender Nit-03/2019 | 23.09.2016 | Yes | Yes | Ramesh kumar pandey | No | No | - | - | - | - | - | W.O is in process
51 | Dhamdaha | Purnea | 630.72 | Decoarch | Submitted | Retender Nit-35/2019 | - | No | No | - | No | No | - | NS | - | - | - | NIT no-35/2019, Dated-04.11.2019, Technical evaluation under process
52 | Baisi | Purnea | 630.72 | Decoarch | Submitted | Retender Nit-35/2019 | - | No | No | - | No | - | - |  | - | - | - | NIT no-35/2019, Dated-04.11.2019, Technical evaluation under process
53 | Teghra | Begusarai | 630.72 | EDMAC | Submitted | [11 empty] | Land not available
54 | Dumrao | Buxar | 630.72 | Kapoor & Associates | in process | - | - | No | No | - | No | - | - |  | - | - | New alloted Land suitable for construction.Land is of labour deptt. to be transffered
|  | Total | 34058.88
Sl. No. | Abstract
1 | Tender invited |  | 2 |  |  | Vaysi and Dhamdaha
2 | Work order to be issued |  | 1 |  |  | Madhaura
3 | Land not available |  | 1 |  |  | Teghra, Dumraon
4 | Work not started |  | 6 |  |  | Pupri

## GNM
PROJECT UNDER 7-Commitement
Construction of General Nurse Midwifery Institute (G.N.M) (As on 31st Jan 2020)
S.N | District | Place of construction | A. A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Date of Receipt of Tender | Tender decided | LOA ISSUED | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Munger | Leprosy Hospital Munger | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | LALAN KUMAR | Yes | Yes | 24/3/2017 | 24/03/2017 | 23/9/2018 | 100% | Completed
2 | Jamui | Vill-Mahuli | 1335.38 | Arch-N-Design | In Process | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | SUDESH KUMAR SINGH | Yes | Yes | 2018-12-02 | 2018-12-02 | 2019-11-08 | 100% | Completed
3 | Araria | Araria | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | SRINATH BUILDER | Yes | Yes | 24/03/2017 | 2018-02-04 | 2020-01-04 | 13% | Academic block- G.F (Column casted) Hostel Block- Layout | Contractor debar vide Letter no-971, Dated-16/07/2019
4 | Katihar | Ward no-04, | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | ADYARAJ DEVELOPER | Yes | Yes | 26/04/2017 | 25/11/2018 | 24/05/2020 | 45% | Academic Block: Roof Shuteering (3rd.F) Hostel Block: Brick work is going on | Electric pole available in proposed site. Letter to be issued to E.E electric division, Katihar
5 | Khagaria | Old Sub divisional Hospital | 1335.38 | Arch-N-Design | Submitted | NIT-25, Dated-3/8/2016 | 8 Sep. 2016 | Yes | Yes | MACRO RANJAN | Yes | Yes | 24/3/2017 | 24/03/2017 | 23/9/2018 | 94% | Finishing work
6 | Vaishali | CHC Rajapakar | 1335.38 | Arch-N-Design | In Process | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | INDRA NARAIN SINGH | Yes | Yes | 25/09/2018 | 25/09/2018 | 24/09/2020 | 75% | Finishing work is in progress
7 | Gopalganj | SDH, Hathua | 1335.38 | Design Associates | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | AIPLGMC, JOINT VENTURE | Yes | Yes | 2018-01-02 | 2018-01-02 | 31/8/2019 | 95% | Finishing work is in progress
8 | Lakhisarai | Noongarh | 1335.38 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | KANHAIYA CONTRACTOR, BEGUSARAI | Yes | Yes | 2018-07-12 | 2018-07-12 | 2019-06-12 | 70% | Finishing work
9 | Nawada | Budhaul | 1335.38 | Arch-N-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | Dhanpat prasad | Yes | Yes | 29/01/2018 | 29/1/2018 | 28/07/2019 | 38% | Roof casted (F.F) | Contractor debar from 10.06.2019
10 | Arwal | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Ray, Dhanbad | Yes | Yes | 28/02/2018 | 28/02/2018 | 27/02/2020 | 98% | Finishing work is in progress
11 | Bhabhua | Barka Katra | 1335.38 | DDF | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Yashaswi Infrastructure, Ranchi | Yes | Yes | 2018-04-05 | 2018-04-05 | 2019-03-08 | 95% | Finishing work is going on.
12 | Bhojpur | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Siemens Construction | Yes | Yes | 29/05/2018 | 29/05/2018 | 28/11/2019 | 36% | Hostel-Plinth Level, Academic- structural work is in progress (Half Portion 3rd Floor casted)
13 | Supaul | VILL -Sukhpur | 1335.38 | EDMAC | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | Ashok Kumar | Yes | Yes | 29/05/2018 | 29/05/2018 | 28/11/2019 | 95% | Finishing work
14 | Madhubani | Raghopur Balath | 1335.38 | Sen & Lall consultants pvt ltd | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | SKS-KKT JV | Yes | Yes | 17/07/2018 | 17/07/2018 | 16/01/2020 | 85% | Finishing work is in progress
15 | Sitamarhi | Madhuban | 1335.38 | Mass-N-Void | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | Shashikant Singh | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-09 | 25% | Roof shuttering (G.F)
16 | Siwan | SDH Mahrajganj | 1335.38 | Mass-N-Void | In Process | RETENDER NIT-18/2017 | 2017-09-04 | Yes | Yes | B. Prasad | Yes | Yes | 2018-08-05 | 2018-08-05 | 2019-07-11 | 95% | Finishing work is in progress
17 | East Champaran | Sadar Hospital | 1335.38 | Design Associates | Submitted | RETENDER NIT-18/2017 | 2017-09-04 | Yes | Yes | Rama Construction | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 65% | Finishing work is in progress
18 | Nalanda | Pavapuri Medical College Campus | 1335.38 | Arch-N-Design | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 28/04/2018 | 28/04/2018 | 27/10/2019 | 70% | Finishing work is in progress
19 | Kishanganj | Halamala | 1335.38 | Arch-N-Design | Submitted | NIT-18/2017 | 2017-09-04 | Yes | Yes | Shafique Alam | Yes | Yes | 31/03/2018 | 17/11/2019 | 16/05/2021 | 15% | Column work (G.F)
20 | Sheohar | - | 1335.38 | DDF Consultant pvt ltd | Submitted | Retender NIT 5/2018 | - | Yes | Yes | Birendra Kumar Chaudhary | No | No | - | - | - |  | Approach road not available
21 | Aurangabad | Sadar Hospital | 1335.38 | Arch-N-Design | Submitted | Retender Nit-35/2019 | 2017-07-05 | No | No |  | No | No | - | - | - | 0% |  | Retender invited vide NIT no-35/2019, Technical evaluation under process
22 | Begusarai |  | 1335.38 | DDF | Submitted |  | 2017-09-04 | No | No | - | No | No | - | - | - |  | Land not available
23 | Samastipur | - | 1335.38 | DDF Consultant pvt ltd | In Process | - | - | No | No | - | No | No | - | - | - |  | Land available | DPR under process
|  | Total | 28042.98
Sl. No. | Abstract
1 | Total no. of Places |  |  | 23 |  | 23
2 | Tender Invited |  |  | 22 |  | 21
3 | Land not available |  |  | 0 |  | 2 |  | Begusarai
4 | Tender Decided |  |  | 21 |  | 20
5 | Tender Under process |  |  | 1 |  | 1 |  | Aurangabad
6 | LOA issued |  |  | 21 |  | 20
7 | Work order issued |  |  | 17 |  | 19
8 | Work order to be issued |  |  |  |  | 1 |  | Sheohar
9 | Work is going on |  |  |  |  | 19

## Para Medical
PROJECT UNDER 7-Commitement
Construction of Para Medical Institute (As on 31st Jan 2020)
S.N | District | Place of construction | A. A. Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Date of Receipt of Tender | Tender decided | LOA ISSUED | NAME OF CONTRACTOR | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress |  | Remarks
[16 empty] | in % | Stage
1 | Banka | Sadar Hospital (Old Campus) | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | RANA CONSTRUCTION | YES | Yes | 2017-05-05 | 2017-05-05 | 2018-04-06 | 100% | Completed | Handed over
2 | Buxar | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | B PRASAD &COMPANY | YES | Yes | 2017-07-08 | 25/11/2017 | 24/2/2019 | 100% | Completed | Handed over
3 | Rohtas | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | RAMESH PANDEY | YES | Yes | 2017-05-08 | 2017-05-08 | 2018-04-11 | 100% | Completed | Handed over
4 | Gopalganj | SDH Hathwa | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | Yes | G M CONSTRUCTION | YES | Yes | 31/3/2017 | 15/1/2018 | 14/4/2019 | 100% | Completed | Letter sent for handing over on 17.07.19
5 | Munger | Leprosy Hospital Munger | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | LALAN KUMAR | YES | Yes | 24/3/2017 | 24/3/2017 | 23/09/2018 | 100% | Completed
6 | Saharsa | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | C S CONSTRUCTION | YES | Yes | 31/3/2017 | 2018-12-03 | 2019-11-08 | 100% | Completed | Handed over
7 | Lakhisarai | Nungarh | 998 | Designer's Wing | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | KANHAIYA CONSTRCION, BEGUSARAI | Yes | Yes | 2018-12-09 | 2018-12-09 | 2019-11-06 | 100% | Completed
8 | Jamui | Vill-Mahuli | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | SUDESH KUMAR SINGH | Yes | Yes | 2018-12-02 | 2018-12-02 | 2019-11-08 | 100% | Completed
9 | Araria | Araria | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | SRINATH BUILDER | YES | Yes | 24/03/2017 | 2018-02-04 | 2020-01-04 | 13% | Academic block- G.F (Column casted) Hostel Block- Layout | Contractor debar vide Letter no-971, Dated-16/07/2019
10 | Katihar | Sadar Hospital | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | ADYARAJ DEVELOPER | YES | Yes | 26/4/2017 | 25/11/2018 | 24/05/2020 | 45% | Academic Block: Roof Shuteering (3rd.F) Hostel Block: Brick work is going on | Electric pole available in proposed site. Letter to be issued to E.E electric division, Katihar
11 | Khagaria | Old Subdivisional Hospital | 998 | Arch-En-Design | Submitted | NIT-25, Dated-03/08/2016 | 8 Sep. 2016 | Yes | YES | MACRO RANJAN | YES | Yes | 24/3/2017 | 24/3/2017 | 23/09/2018 | 94% | Finishing work
12 | Madhubani | Sadar Hospital | 998 | Designer's Wing | Submitted | NIT-27, Dated-03/08/2016 | 16 Sep. 2016 | Yes | YES | SANJAY KUMAR | YES | Yes | 2017-09-05 | 2018-01-11 | 28/02/2020 | 40% | Roof shuttering (2nd Floor)
13 | Purnea | Sadar Hospital Purnea | 998 | Design Associates Inc. | Submitted | Nit-26, Dated-03/08/2016 | 2016-09-19 | Yes | YES | UMAKANT SINGH | YES | Yes | 31/3/2017 | 2017-01-11 | 31/05/2020 | 68% | Finishing work
14 | West Champaran | Sadar Hospital | 998 | DDF | Submitted | Nit-15, Dated-10/06/2016 | 15/7/2016 | Yes | YES | L& T CONSTRUCTION | YES | Yes | 2017-10-07 | 2017-10-07 | 2020-09-07 | 50% | work is going on
15 | Vaishali | Rajapakar | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | INDRA NARAIN SINGH | Yes | Yes | 25/09/2018 | 25/09/2018 | 24/09/2020 | 75% | Finishing work is going on
16 | Jehanabad | Referral Hospital Ghosi | 998 | Designer's Wing | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | KAUSHLENDRA KUMAR | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-06 | 60% | Hostel- Finishing work, Academic-Roof shuttering (F.F)
17 | Saran | Sadar Hospital Chhapra | 998 | EDMAC | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | Yes | G M CONSTRUCTION, SIWAN | Yes | Yes | 2018-04-05 | 20/7/2018 | 19/10/2019 | 85% | Finishing work is in progress
18 | Supaul | Supaul | 998 | Mass-N-Void | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | YES | YES | INDRA NARAIN SINGH, PATNA | YES | Yes | 28/11/2018 | 28/11/2018 | 27/02/2020 | 55% | Brick work is going on
19 | Nawada | Budhaul | 998 | Arch-En-Design | Submitted | Nit-38, Dated-27/10/2016 | 29-12-2016 | Yes | YES | DHANPAT PRASAD | Yes | Yes | 29/01/2017 | 29/01/2017 | 28/07/2019 | 38% | Roof casted (F.F) | Contractor debar from 10.06.2019
20 | Arwal | Sadar Hospital | 998 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | Yes | B. Rai, Dhanbad | Yes | Yes | 28/02/2018 | 28/02/2018 | 27/02/2020 | 98% | Finishing work is in progress
21 | Bhojpur | Sadar Hospital | 998 | Arch-En-Design | Submitted | RETENDER NIT-13, Dated-15/05/2017 | 2017-07-05 | Yes | YES | Siemens Construction | Yes | Yes | 29/05/2018 | 29/5/2018 | 28/11/2019 | 36% | Hostel-Plinth Level, Academic- structural work is in progress (Half Portion 3rd Floor casted)
22 | Nalanda | Pavapuri Medical College Campus | 998 | Arch-En-Design | Submitted | TENDER NIT 18/2017 | 2017-09-04 | Yes | YES | M/s Satyanarayan Singh | Yes | Yes | 28/04/2018 | 28/04/2018 | 27/10/2019 | 70% | Finishing work is in progress
23 | East Champaran | Sadar Hospital | 998 | Design Associates Inc. | Submitted | RETENDER NIT 18/2017 | 2017-09-04 | Yes | YES | Rama Construction | Yes | Yes | 2019-02-03 | 2019-02-03 | 2020-01-03 | 65% | Finishing work is in progress
24 | Madhepura | Parariya | 998 | Suresh Goel & Associates | in process | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | M/s Satyanarayan Singh | Yes | Yes | 31/03/2018 | 20/5/2018 | 24/11/2019 | 25% | Girl's Hostel-Brick work, Boys Hostel- Roof shuttering (Terrace.F)
25 | Siwan | Sub-Divisional hospital, Maharajganj | 998 | Mass-N-Void | Submitted | RE TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | B. Prasad | Yes | Yes | 2018-08-05 | 2018-08-05 | 2019-07-11 | 95% | Finishing work is in progress
26 | Bhabhua | Sarangpur | 998 | DDF | Submitted | RE TENDER NIT 39/2017 | 2018-01-05 | Yes | Yes | Ajay Kumar Singh | Yes | Yes | 26/10/2018 | 20/01/2019 | 19/04/2020 | 30% | Roof casted (2nd.F)
27 | Sheikhpura | Makhdumpur PHC | 998 | Designer's Wing | Submitted | NIT 39/2017 | 2018-01-05 | Yes | YES | Sanjay Kumar Technocrat | Yes | Yes | 2018-07-12 | 2018-07-12 | 2020-06-03 | 60% | Finishing work
28 | Kishanganj | Halamala | 998 | Arch-En-Design | in process | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | Shafique Alam | Yes | Yes | 31/03/2018 | 17/11/2019 | 16/05/2021 | 15% | Column work (G.F)
29 | Sitamarhi | Padri | 998 | Designer's Wing | Submitted | TENDER NIT 18/2017 | 2017-09-04 | Yes | Yes | Shashikant Singh | Yes | Yes | 2020-08-01 | 2020-08-01 | 2021-07-04 |  | Work started
30 | Sheohar | Sadar Hospital | 998 | DDF Consultant pvt ltd | Submitted | RE TENDER NIT 5/2018 | 2018-01-05 | Yes | Yes | Birendra Kumar Chaudhary | No | No |  |  |  |  | Approach road not available
31 | Aurangabad | Sadar Hospital | 998 | Arch-En-Design | Submitted |  | 2017-07-05 | No | No |  | No | No |  |  |  |  | - | Retender invited vide NIT no-35/2019, Dated-04.11.2019
32 | Begusarai | - | 998 | DDF | NOT SUBMITTED | - | - | No | No |  | No | No |  |  |  |  | Land not available
33 | Samastipur | - | 998 | DDF | NOT SUBMITTED | - | - | No | No |  | No | No |  |  |  |  | Land available | DPR under process
|  | Total | 24950
Sl. No. |  | Abstract
1 |  | Tender Invited |  | 30
2 |  | Tender Decided |  | 30
3 |  | LOA issued |  | 30
4 |  | Work order issued |  | 28
5 |  | Work order to be issued |  | 2 |  | Sheohar
6 |  | Land not available |  | 2 |  | Begusarai

## B.SC
PROJECT UNDER 7-Commitement
B.Sc Nursing College (As on 31st Jan 2020)
S.N | Name of Places | District | Land available or not | Administrative Approval Amount (In Rs. Lakh) | Name of Consultant | Status of DPR | Status of Tender | Work order issued | Whether work started | Date of Work Order | Date of Actual Start | Date of completion | Physical progress in Percentage | Remarks
1 | PMCH, Patna | Patna | No | 2649.76 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | No | 18/08/2017 | NS | 17/08/2019 | - | Work is kept on hold because of PMCH redevelopment
2 | JLNMCH, Bhagalpur | Bhagalpur | Yes | 2649.76 | Arch-En-Design | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed & Handed Over
3 | Vardhaman Ayurvigyan Sansthan, Pawapuri | Nalanda | Yes | 2649.76 | Arch-En-Design | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed & Handed Over
4 | DMCH, Laheriasarai | Darbhanga | Yes | 2649.76 | Suresh Goel & Associates | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 100% | Completed & Handed Over
5 | SKMCH, Muzaffarpur | Muzaffarpur | Yes | 2649.76 | DDF | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 31/3/2017 | 30/03/2019 | 75%
6 | ANMMCH, Gaya | Gaya | Yes | 2649.76 | Design Associate Inc. | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 2017-05-05 | 2017-05-05 | 2019-04-05 | 80% | Contractor debbared vide letter no 5207, Dated-03.12.2019
7 | Govt. Medical College, Bettiah | Bettiah | Yes | 2649.76 | DDF | Submitted | Nit-15, Dated-10/06/2016 | Yes | Yes | 2017-10-07 | 2017-10-07 | 2020-09-07 | 50%
8 | Govt. Medical College, Purnea (Sadar Hospital Campus) | Purnea | Yes | 2649.76 | Design Associate Inc. | Submitted | Nit-26, Dated-03/08/2016 | Yes | Yes | 31/3/2017 | 2017-01-11 | 31/05/2020 | 68%
9 | Govt. Medical College, Chhapra | Chhapra | Yes | 2649.76 | Suresh Goel & Associates | In Process | Nit-24/2018, Dated-14/07/2018 | Yes | Yes | 28/2/2019 | 28/2/2019 | 27/02/2022 | 25%
10 | Govt. Medical College, Mahua | Vaishali | Yes | 2649.76 | - | - | Nit-22/2019 | - | - | - | - | - | - | LOA issued on 06.01.20120 & the bidder is KCI-CCEL JV
11 | Govt. Medical College, Sitamarhi | Sitamarhi | Yes | 2649.76 | - | - | Nit-22/2019 | - | - | - | - | - | - | Financial bid opened on 30.12.2019
12 | Govt. Medical College, Samastipur | Samastipur | Yes | 2649.76 | DDF | Submitted | - | No | No |  |  |  |  | DPR under process
13 | Govt. Medical College, Madhepura | Madhepura | No | 2649.76 | EDMAC | In Process | - | - | - | - | - | - | - | Land not available
14 | Govt. Medical College, Begusarai | Begusarai | Yes | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
15 | Govt. Medical College, Ara | Bhojpur | No | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
16 | Govt. Medical College, Madhubani | Madhubani | Yes | 2649.76 | - | - | - | - | - | - | - | - | - | Land not available
|  | Total |  | 42396.16 | - | - | - | - | - | - | - | - | -
Sl. No. | Abstract
1 | Tender Invited |  |  |  |  | 11
2 | Tender Decided |  |  |  |  | 9 |  | Bhagalpur, Patna, Gaya, Purnia, Darbhanga, Pawapuri, Muzaffarpur, Chhapra, Mahua & Bettiah
3 | In Tender | [5 empty] | 2 | Sitamarhi
4 | Work order issued |  |  |  |  | 9 |  | Bhagalpur, Patna, Gaya, Purnia, Darbhanga, Pawapuri, Muzaffarpur, Chhapra & Bettiah
5 | Land to be decided |  |  |  |  | 5 |  | Madhepura, Begusarai, Bhojpur & Madhubani