## GNM (3)
CONSTRUCTION OF GENERAL NURSE MIDWIFERY (G.N.M) under GOI schemes
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date with centage (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of GNM training school & hostel |  | 10772.98 | 3625 | 7526.37 |  | 11 | 9 | 2 | 0
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | EXPENDITURE WITH CENTAGE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Rohtas | Construction of G.N.M Training school & hostels in Sadar hospital, Sasaram (Rohtas) | 1220.1724 | 2013-10-03 | M/S B Prasad & co. Anishabad, Patna | 894.3811 | 2014-06-11 | 2015-12-10 | Completed | 100% | 1047.27 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | Banka | Construction of G.N.M at Sadar Hospital Banka | 1222.3616 | 2013-10-03 | M/S Lalan Kumar | 969.1582 | 2014-11-26 | 2016-05-25 | Completed | 100% | 982.35 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
3 | Jahanabad | Construction of G.N.M at Sadar Hospital Jahanabad | 963.5628 | 2013-10-03 | M/S Yashaswi construction, Anishabad (Patna) | 941.7381 | 2015-11-27 | 2017-05-26 | Completed | 100% | 1089.49 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
4 | Saharsa | Construction of G.N.M at Sadar Hospital Saharsa | 1038.9261 | 2013-10-03 | Baba Hans construction Pvt. Ltd | 973.0374 | 2014-12-26 | 2016-06-25 | Completed | 100% | 835.12 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
5 | Buxar | Construction of G.N.M at Sadar Hospital Buxar | 1004.8402 | 2013-10-03 | Rajesh Kumar | 845.0891 | 2017-05-09 | 2018-11-08 | Completed | 100% | 741.47 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
6 | Sheikhpura | Construction of G.N.M at Sadar Hospital Sheikhpura | 983.4306 | 2013-10-03 | Arun Deo Kumar | 828.358 | 2015-12-31 | 2017-06-30 | Completed | 100% | 1024.55 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
7 | West Champaran | Construction of G.N.M at Bettiah, West Champaran | 1022.1539 | 2013-10-03 | Rama & Sons | 855.7345 | 2017-05-11 | 2018-11-10 | Completed | 100% | 685.12 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
8 | Saran | Construction of G.N.M at Sadar Hospital Chapra (Saran) | 1255.9296 | 2013-10-03 | M/S Harishankar Prasad | 1019.7473 | 2014-12-26 | 2016-06-25 | Completed | 100% | 837.88 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
9 | Purnea | Construction of G.N.M at Sadar Hospital Purnea | 1020.6944 | 2013-10-03 | M/S Satyanarayan Singh | 894.0844 | 2015-12-15 | 2017-06-14 | Academic Block-Almost completed | 50% | 283.12 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land available for Hostel block, Letter sent to contractor to start the work vide Letter no-1431,2876 Date-22.06.2019, 26.08.2019 Respectively
10 | Madhepura | Construction of G.N.M at Medical College & Hospital Madhepura | 1040.9035 | 2013-10-03 | - | - | - | - | Completed | 100% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | constructed with Medical College. Hence separate expenditure not given.
11 | Gaya | Construction of G.N.M at ANMMCH, Gaya | 1330.42 | 2017-12-14 | Prasad Associates | 1110.8 | 2019-03-02 | 2020-09-01 | Academic Block-Roof casted (1st slab) | 10% | 0
| Total |  | 12103.3951 |  |  | 9332.128 |  |  |  |  | 7526.37

## ANM (3)
CONSTRUCTION OF AUXILIARY NURSE MIDWIFERY (A.N under GOI schemes
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date with centage (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of ANM training school & hostel |  | 5120.94 | 1376 | 0 |  | 11 | 10 | 0 | - |  | -
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | EXPENDITURE WITH CENTAGE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Darbhanga | Construction of A.N.M school & hostel at refferal hospital Jale, Darbhanga | 584.9925 | 2013-09-24 | Avaneesh Enterprises, Ghaziabad | 436.89 | 2014-07-19 | 2015-07-18 | Completed | 100% | 315.09 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
2 | Nawada | Construction of A.N.M school & hostel at refferal hospital Rajauli, Nawada | 448.7312 | 2013-09-24 | Bipin Kumar, Nawada | 380.7919 | 2014-08-29 | 2015-08-28 | Completed | 100% | 418.34 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
3 | Siwan | Construction of A.N.M Training school & Hostel in Referral hospital, Mairwa (Siwan) | 593.2551 | 2013-09-24 | G.M Construction, Ahmedabad | 408.9828 | 2014-07-26 | 2015-07-25 | Completed | 100% | 385.54 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
4 | Aurangabad | Construction of A.N.M Training school & Hostel in Referral hospital, Daudnagar (Aurangabad) | 468.4109 | 2013-09-24 | Yashswi Infrastructure pvt. Ltd., Ranchi | 385.9641 | 2015-01-19 | 2016-01-18 | Completed | 100% | 416.89 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
5 | Kaimur | Construction of A.N.M Training school & Hostel in Sadar hospital, Bhabhua (Kaimur) | 484.7357 | 2013-09-24 | Anil Kumar, Rohtas | 409.0411 | 2014-08-25 | 24-08-2015 | Completed | 100% | 460.58 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
6 | Khagaria | Construction of A.N.M Training school & Hostel in Sadar hospital, Khagaria | 580.1198 | 2013-09-24 | Surendra Prasad Singh, Begusarai | 400.964 | 2015-01-09 | 2016-01-08 | Completed | 100% | 429.02 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
7 | Lakhisarai | Construction of A.N.M Training school & Hostel in Sadar hospital, Lakhisarai | 472.2124 | 2013-09-24 | Rama construction, Patna | 406.7411 | 2014-07-19 | 2015-07-18 | Completed | 100% | 459.35 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
8 | Supaul | Construction of A.N.M school & hostel at Sub-divisional hospital Triveniganj, Supaul | 502.7791 | 2013-09-24 | Avaneesh Enterprises, Ghaziabad | 426.5652 | 2014-07-18 | 2015-07-17 | Completed | 100% | 364.59 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
9 | Sheohar | Construction of A.N.M school & hostel at sadar hospital, sheohar | 501.5786 | 2013-09-24 | Virendra Kumar Chaudhary | 401.3985 | 2014-12-29 | 2015-12-28 | Completed | 100% | 447.94 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
10 | Jamui | Construction of A.N.M at Refferal Hospital Lakshmipur (Jamui) | 484.1236 | 2013-09-24 | M/S Balkrishan Dholakiya construction pvt ltd | 396.8122 | 2015-08-19 | 2016-05-18 | Completed | 100% | 424.58 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
11 | Sitamarhi | Construction of A.N.M at Sitamarhi |  |  | Arun Kumar, Patna | 509.8862 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | W.O is in process
| Total |  | 5120.9389 |  |  | 4564.0372 |  |  |  |  | 4121.92

## DFID (2)
PROJECTS IN MEDICAL COLLEGES {UNDER DFID (Department for International Development, U.K.) FUNDING}
SL NO | Name of work |  | A.A. RECEIVED FROM | A.A Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Expenditure in Percentage (%) against agrrement | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects | REMARKS
1 | Construction of various project in Medical colleges of Bihar |  | Health Dept. | 16345.42 | 16345.42 | 10929.0271 | 80.76% | 21 | 20 | - |  | 1 (Diagnostic Centre)
Detailed Report (DFID)
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE EXPENDITURE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS IN LAKH) |  |  | STAGE | % | (RS IN LAKH)
NMCH, Patna
1 | Patna | CONSTRUCTION OF CENTRE OF EXCELLENCE AT NMCH, PATNA | 4211.7 | 2014-11-08 | M/S B. Rai | 3711.8095 | 2015-11-27 | 2017-05-26 | Completed | 100% | 4070.49 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
2 |  | CONSTRUCTION OF B.SC NURSING AT NMCH, PATNA | 2762.26 | 2015-03-25 | Indra Narayan Singh contractors pvt ltd, Patna | 2350.1997 | 2015-12-09 | 2017-06-08 | Completed | 100% | 24 77.12 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
3 |  | CONSTRUCTION OF VACCINE CENTRE AT NMCH, PATNA | 1094.24 | 2015-09-01 | M/S B. Prasad | 887.3434 | 2016-04-13 | 2017-10-12 | Completed | 100% | 875.83 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
4 |  | CONSTRUCTION OF MODEL RECORD ROOM AT NMCH, PATNA | 170.98 | 2015-04-28 | R.K infra services pvt ltd, Patna | 122.4525 | 2016-02-05 | 2016-11-04 | Completed | 100% | 101.1487 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
|  | Sub Total of NMCH | 8239.18 |  |  | 7071.805
PMCH, Patna
5 | Patna | CONSTRUCTION OF LECTURE THEATRE (250 seater) AT PMCH, PATNA | 275.08 | 2015-03-27 | Ramesh Kumar Pandey | 342.361 | 2015-12-09 | 2017-06-08 | Completed | 100% | 227.29 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
6 |  | CONSTRUCTION OF MODEL RECORD ROOM AT PMCH, PATNA | 170.98 | 2015-04-28 | Ramesh Kumar Pandey |  | 2015-12-09 | 2017-06-08 | Completed | 100% | 155.28 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
7 |  | CONSTRUCTION OF 150 BEDDED HOSTEL AT PMCH, PATNA | 1029.78 | 2015-04-28 | Sudhesh Kumar Singh & company pvt ltd | 812.0747 | 2015-12-09 | 2017-06-08 | Completed | 100% | 787.13 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
|  | Sub Total of PMCH | 1475.84 |  |  | 1154.4356
ANMMCH, Gaya
8 | Gaya | CONSTRUCTION OF CENTRAL LIBRARY AT ANMMCH, GAYA | 584.55 | 2015-04-28 | Simens construction corporation, Patna | 2703.6702 | 2015-12-31 | 2017-12-30 | Completed | 100% | 588.98 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
9 |  | CONSTRUCTION OF MODEL RECORD ROOM AT ANMMCH, GAYA (Above central library) | 170.98 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
10 |  | CONSTRUCTION OF EMERGENCY WARD AT ANMMCH, GAYA | 1294.74 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% | 639.6097 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 |  | CONSTRUCTION OF 136 BEDDED GIRLS HOSTEL AT ANMMCH, GAYA | 1109 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% | 903.1949 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
12 |  | CONSTRUCTION OF 250 SEATER LECTURE THEATRE (2 units) ANMMCH, GAYA | 550.16 | 2015-03-27 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% | 382.6237 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
|  | Sub Total of ANMMCH, Gaya | 3709.43 |  |  | 2703.6702
SKMCH, Muzaffarpur
13 | Muzaffarpur | CONSTRUCTION OF 75 BEDDED GIRLS HOSTELAT SKMCH, MUZAFFARPUR | 499.12 | 2015-03-27 | Mother India pvt ltd | 972.9731 | 2015-12-15 | 2017-06-14 | Completed | 100% | 375.5403 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
14 |  | CONSTRUCTION OF 250 CAPACITY LECTURE THEATRE (2 units) AT SKMCH, MUZAFFARPUR | 550.16 | 2015-03-27 |  |  | 2015-12-15 | 2017-06-14 | Completed | 100% | 373.2826 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
15 |  | CONSTRUCTION OF MODEL RECORD ROOM AT SKMCH, MUZAFFARPUR | 170.98 | 2015-04-28 |  |  | 2015-12-15 | 2017-06-14 | Completed | 100% | 135.5105 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
|  | Sub Total of SKMCH, Muzaffarpur | 1220.26 |  |  | 972.9731
JLNMCH, Bhagalpur
16 | Bhagalpur | CONSTRUCTION OF CENTRAL LIBRARY AT JLNMCH, BHAGALPUR | 584.55 | 2015-04-28 | Nandlal & Company | 1199.64 | 2015-09-09 | 2017-03-08 | Completed | 100% | 465.44 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
17 |  | CONSTRUCTION OF GIRL'S HOSTEL (75 capacity) AT JLNMCH, BHAGALPUR | 499.12 | 2015-03-27 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% | 400 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
18 |  | CONSTRUCTION OF 250 CAPACITY LECTURE THEATRE (1 units) JLNMCH, BHAGALPUR | 275.08 | 2015-03-27 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% | 334.2 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
19 |  | CONSTRUCTION OF MODEL RECORD ROOM AT JLNMCH, BHAGALPUR | 170.98 | 2015-04-28 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% |  | Sri Anil Kumar | Sri Sanjeev Ranjan
|  | Sub Total of JLNMCH, Bhagalpur | 1529.73 |  |  | 1199.64
DMCH, Darbhanga
20 | Darbhanga | CONSTRUCTION OF MODEL RECORD ROOM AT DMCH, DARBHANGA | 170.98 | 2015-04-28 | Shaurya Premier Infrastructure Pvt ltd | 125.0267 | 2016-08-30 | 2017-08-29 | Completed | 100% | 113.4767 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
|  | Total | 16345.42 |  |  | 13227.5508 |  |  |  |  | 10929.0271

## Sub-Divisional
SUB-DIVISIONAL HOSPITAL
As on 05.08.2019
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
Phase- I
1 | SITAMARHI | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT BELSAND, DIST-SITAMARHI | 1374.23 | 2017-03-06 | Kamalpura Construction Pvt Ltd, Muzaffarpur | 1155.6773 | 2018-12-19 | 2020-06-18 | Plaster work is in progress (F.F) | 45% | 412 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
2 | VAISHALI | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT MAHNAR, DIST-VAISHALI | 1238.64 | 2017-03-06 | M/S Satyanarayan Singh | 1040.07 | 2019-03-02 | 2020-09-01 | Not Started | - | - | Sri Sandeep Kumar | Sri Sanjeev Ranjan | Land not available. Letter sent to D.M vide Letter no2094-, Dated-19.07.2019
3 | MADHUBANI | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT BENIPATTI, DIST-MADHUBANI | 1310.11 | 2017-03-06 | - | - | - | - | Not Started | - | - | Sri Sunil Kumar | Md. Shamim Ahmad | Financial bid opened, Lottery to be done
4 | MUNGER | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT HAWELI KHARAGPUR, DIST-MUNGER | 1180.34 | 2017-03-06 | M/S Satyanarayan Singh | 991.8986 | 2019-03-08 | 2020-09-07 | Work started | 2% | - | Sri Anil Kumar | Md. Shamim Ahmad | Old building demolishion work is in progress
5 | BEGUSARAI | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT TEGHRA, DIST-BEGUSARAI | 1305.04 | 2017-03-06 | Kaushal Buildcon Pvt Ltd | 1097.67 | 2019-03-08 | 2020-09-07 | Column work (G.F) | 18% | 96 | Sri Anil Kumar | Md. Shamim Ahmad
6 | BEGUSARAI | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT BAKHRI, DIST-BEGUSARAI | 1409.22 | 2017-03-06 | M/s Surendra Prasad Singh | 1185.18 | - | - | Not Started | - | - | Sri Anil Kumar | Md. Shamim Ahmad | Land not available. Letter sent to D.M vide Letter no-4631,1860 Dated-31/12/2018 &11.07.2019
7 | SARAN | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT MADHAURA, DIST-SARAN | 1314.58 | 2017-03-06 | M/s Highway Construction co, Jharkhand | 1105.4011 | - | - | Not Started | - | - | Sri Sagar Jaiswal | Md. Shamim Ahmad | Land available on 29.05.2019 (Work started after demolished the old building)
|  | Total | 9132.16 |  |  | 6575.897
Phase- II
8 | EAST CHAMPARAN | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT RAXAUL, DIST-E.CHAMPARAN | 1705 | 2019-02-05 | - | - | - | - | - | - | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Tender Invited Vide NIT no-21/2019 & Dated- 07/06/2019.
9 | EAST CHAMPARAN | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT SIKRAHANA (DHAKA), DIST-E.CHAMPARAN | 1672 | 2019-02-05 | - | - | - | - | - | - | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan
10 | DARBHANGA | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT BIRAUL, DIST-DARBHANGA | 1835 | 2019-02-05 | - | - | - | - | - | - | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 | KHAGARIA | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT GOGRI, DIST-KHAGARIA | 1806 | 2019-02-05 | - | - | - | - | - | - | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan
12 | SUPAUL | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT VIRPUR, DIST-SUPAUL | 1802 | 2019-02-05 | - | - | - | - | - | - | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan
13 | SUPAUL | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT TRIVENIGANJ, DIST-SUPAUL | 1702 | 2019-02-05 | - | - | - | - | - | - | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan
14 | PATNA | CONSTRUCTION OF SUB-DIVISIONAL HOSPITAL AT PALIGANJ, DIST-PATNA | 1326 | 2017-03-09 | - | - | - | - | - | - | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan
|  | Total | 11848

## PHC TO CHC (Health) (2)
PHC TO CHC (30 BEDDED) {Health deptt-38 nos}
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects |  |  | REMARKS
1 | Construction of PHC to CHC (Health deptt.) |  | 14036.06 | 24433.92 | 10586.5857 | 38 | 27 | 11 |  | 0
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | Furniture supplied or No | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % |  | (Rs in lakh)
1 | JAMUI | CHC AT PHC GIDHAURE (JAMUI) | 369.37 | 2014-09-03 | Ashok & co niwas pvt ltd, Jamui | 338.9408 | 2015-08-31 | 2016-08-30 | Completed | 100% | Sent to Health Dept. for A.A | 338.94 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
2 | VAISHALI | CHC AT PHC RAJAPAKAR (VAISHALI) | 369.37 | 2014-09-03 | Rana construction, Kadamkuan (Patna) | 318.9036 | 2015-08-31 | 2016-08-30 | Completed | 100% | Sent to Health Dept. for A.A | 330.65 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
3 | EAST CHAMPARAN | CHC AT PHC SANGRAMPUR (EAST CHAMPARAN) | 369.37 | 2014-09-03 | Nagendra Mishra, Muzaffarpur | 311.077 | 2015-08-31 | 2016-08-30 | Completed | 100% | Sent to Health Dept. for A.A | 300.51 | Md Nasim Akhtar Ansari | Md. Shamim Ahmad | Handed over
4 | NAWADA | CHC AT PHC NARDIGANJ (NAWADA) | 369.37 | 2014-09-03 | Arun Deo Kumar, Nalanda | 343.2544 | 2015-09-09 | 2016-09-08 | Completed | 100% | Sent to Health Dept. for A.A | 336.0447 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
5 | JEHANABAD | CHC AT PHC HULASGANJ (JEHANABAD) | 369.37 | 2014-09-03 | M/S Om Sai construction, Jehanabad | 316.8986 | 2015-08-31 | 2016-08-30 | Completed | 100% | Sent to Health Dept. for A.A | 336.0447 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
6 | SUPAUL | CHC AT SARAIGARH BHAPTIYAHI (SUPAUL) | 369.37 | 2014-09-03 | Indra Narayan Singh Contract pvt ltd, Patna | 352.8981 | 2016-04-28 | 2017-04-27 | Completed | 100% | Sent to Health Dept. for A.A | 370.72 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
7 | BHAGALPUR | CHC AT ISMAILPUR (BHAGALPUR) | 369.37 | 2014-09-03 | Pankaj construction | 404.5614 | 2016-06-08 | 2017-06-07 | Completed | 100% | Sent to Health Dept. for A.A | 356.49 | Sri Anil Kumar | Sri Sanjeev Ranjan
8 | SITAMARHI | CHC AT BOKHRA (SITAMARHI) | 369.37 | 2014-09-03 | Sanjay Kumar | 336.2289 | 2016-05-12 | 2017-05-11 | Completed | 100% | Sent to Health Dept. for A.A | 310.84 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
9 | SAMASTIPUR | CHC AT MOHANPUR (SAMASTIPUR) | 369.37 | 2014-09-03 | Vinesh Kumar | 324.5352 | 2016-05-12 | 2017-05-11 | Completed | 100% | Sent to Health Dept. for A.A | 230.29 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
10 | SAMASTIPUR | CHC AT KHANPUR (SAMASTIPUR) | 369.37 | 2014-09-03 | M/S Shyam babu Chaudhary | 322.4152 | 2016-05-12 | 2017-05-11 | Completed | 100% | Sent to Health Dept. for A.A | 165.8 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
11 | VAISHALI | CHC AT PHC BHAGWANPUR (VAISHALI) | 369.37 | 2014-09-03 | Nagendra Mishra, Muzaffarpur | 327.0614 | 2016-08-22 | 2017-08-21 | Completed | 100% | Sent to Health Dept. for A.A | 282.18 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
12 | SIWAN | CHC AT PHC HASANPURA (SIWAN) | 369.37 | 2014-09-03 | Asiana contract pvt ltd, Gopalganj | 310.537 | 2015-08-31 | 2016-08-30 | Completed | 100% | Sent to Health Dept. for A.A | 159.71 | Sri Sagar Jaiswal | Md. Shamim Ahmad | Handed over
13 | GOPALGANJ | CHC AT PHC THAWE (GOPALGANJ) | 369.37 | 2014-09-03 | G.M Construction, Siwan | 330.1727 | 2015-08-31 | 2016-08-30 | Completed | 100% | Sent to Health Dept. for A.A | 265.2 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
14 | GAYA | CHC AT PHC MOHRA (GAYA) | 369.37 | 2014-09-03 | Mohan Sharma, Gaya | 315.1639 | 2016-11-14 | 2017-11-13 | Completed | 100% | Sent to Health Dept. for A.A | 315.1639 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
15 | SAMASTIPUR | CHC AT BITHAN (SAMASTIPUR) | 369.37 | 2014-09-03 | M/S Surendra Prasad Singh, Begusarai | 341.2774 | 2017-03-06 | 2018-03-05 | Completed | 100% | Sent to Health Dept. for A.A | 341.27 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
16 | MADHUBANI | CHC AT KALUAHI (MADHUBANI) | 369.37 | 2014-09-03 | Abhay kumar Singh, Sitamarhi | 323.463 | 2017-02-17 | 2018-02-16 | Completed | 100% | Sent to Health Dept. for A.A | 161.23 | Sri Sunil Kumar | Md. Shamim Ahmad
17 | ARWAL | CHC AT KALER (ARWAL) | 369.37 | 2014-09-03 | B.M Construction, Jehanabad | 330.5846 | 2017-10-16 | 2018-10-15 | Plaster work is in progress | 60% | Sent to Health Dept. for A.A | 264.35 | Sri Sandeep Kumar | Sri Sanjeev Ranjan
18 | SAHARSA | CHC AT SATAR KATAIYA (SAHARSA) | 369.37 | 2014-09-03 | M/S R. K. Construction, Begusarai | 382.8534 | 2016-10-31 | 2017-10-30 | Completed | 100% | Sent to Health Dept. for A.A | 335 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
19 | NAWADA | CHC AT KASHICHAK (NAWADA) | 369.37 | 2014-09-03 | Avani Devcon pvt ltd, Patna | 300.6933 | 2017-02-13 | 2018-02-12 | Completed | 100% | Sent to Health Dept. for A.A | 194.92 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
20 | MUZAFFARPUR | CHC AT BANDRA (MUZAFFARPUR) | 369.37 | 2014-09-03 | Nalin Ranjan | 297.0852 | 2016-12-27 | 2017-12-26 | Finishing work is in progrerss | 80% | Sent to Health Dept. for A.A | 297.0852 | Sri Vikash Jha | Sri Sanjeev Ranjan | Land available on Aug'18
21 | SIWAN | CHC AT LAKRI NABIGANJ (SIWAN) | 369.37 | 2014-09-03 | Asiana contract pvt ltd, Gopalganj | 316.7612 | 2016-08-11 | 2017-08-10 | Completed | 100% | Sent to Health Dept. for A.A | 235.43 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
22 | JAMUI | CHC AT HARLALNAGAR,ALIGANJ (JAMUI) | 369.37 | 2014-09-03 | A.K Construction | 289.6844 | 2016-06-08 | 2017-06-07 | Finishing work is in progrerss | 95% | Sent to Health Dept. for A.A | 240.29 | Sri Anil Kumar | Sri Rajendra Prasad Singh
23 | DARBHANGA | CHC AT HANUMAN NAGAR (DARBHANGA) | 369.37 | 2014-09-03 | Sanjay Kumar | 335.7558 | 2017-03-06 | 2018-03-05 | Completed | 100% | Sent to Health Dept. for A.A | 236.09 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
24 | KATIHAR | CHC AT SAMAILI (KATIHAR) | 369.37 | 2014-09-03 | M/S C.S Construction | 350.8302 | 2016-09-08 | 2017-09-07 | Finishing work is in progrerss | 80% | Sent to Health Dept. for A.A | 233.74 | Sri Shashi Shekhar | Md. Shamim Ahmad | Work stopped
25 | KATIHAR | CHC AT MANSAHI (KATIHAR) | 369.37 | 2014-09-03 | M/S C.S Construction | 339.4581 | 2016-09-08 | 2017-09-07 | Finishing work is in progrerss | 75% | Sent to Health Dept. for A.A | 260.04 | Sri Shashi Shekhar | Md. Shamim Ahmad | Work stopped
26 | SHEOHAR | CHC AT DUGRI KATHSARI (SHEOHAR) | 369.37 | 2014-09-03 | Sri Ashok Kumar Singh, Sitamarhi | 337.1786 | 2017-02-17 | 2018-02-16 | Brick work is going on | 55% | Sent to Health Dept. for A.A | 190 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
27 | GAYA | CHC AT BANKEBAZAR (GAYA) | 369.37 | 2014-09-03 | Kishor Kumar Singh, Aurangabad | 354.3128 | 2016-10-07 | 2017-10-06 | Completed | 100% | Sent to Health Dept. for A.A | 354.3128 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
28 | MADHEPURA | CHC AT PURAINI (MADHEPURA) | 369.37 | 2014-09-03 | Topline Infra Projects pvt ltd, Kolkata | 357.3348 | 2016-12-27 | 2017-12-26 | Completed | 100% | Sent to Health Dept. for A.A | 434.66 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
29 | SITAMARHI | CHC AT SUPPI (SITAMARHI) | 369.37 | 2014-09-03 | Sri Sanjeev Kumar, Patna | 326.8855 | 2018-05-17 | 2019-05-16 | Finishing work is in progress | 65% | Sent to Health Dept. for A.A | 290 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
30 | JEHANABAD | CHC AT RATNIFARIDPUR (JAHANABAD) | 369.37 | 2014-09-03 | Sri Nripendra Kumar Sinha, Patna | 289.928 | 2017-08-18 | 2018-08-17 | Completed | 100% | Sent to Health Dept. for A.A | 313.2278 | Sri Sandeep Kumar | Sri Sanjeev Ranjan
31 | MADHEPURA | CHC AT GWALPARA (MADHEPURA) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 385.2323 | 2017-02-17 | 2018-02-16 | Completed | 100% | Sent to Health Dept. for A.A | 398.25 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
32 | SUPAUL | CHC AT PRATAPGANJ (SUPAUL) | 369.37 | 2014-09-03 | Indra Narayan Singh Contract pvt ltd, Patna | 366.6581 | 2017-02-17 | 2018-02-16 | Completed | 100% | Sent to Health Dept. for A.A | 270.45 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
33 | BHAGALPUR | CHC AT RANGRACHOWK (BHAGALPUR) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 359.1162 | 2017-01-13 | 2018-01-12 | Completed | 100% | Sent to Health Dept. for A.A | 359.79 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
34 | MADHUBANI | CHC AT LAKHNAUR (MADHUBANI) | 369.37 | 2014-09-03 | Mother India const. pvt ltd | 360.4508 | 2017-03-20 | 2018-03-19 | Brick work (F.F) | 55% | Sent to Health Dept. for A.A | 145.24 | Sri Sunil Kumar | Md. Shamim Ahmad
35 | SITAMARHI | CHC AT CHORAUT (SITAMARHI) | 369.37 | 2014-09-03 | Mother India const. pvt ltd | 334.7301 | 2017-07-20 | 2018-07-19 | Finishing work is in progress | 98% | Sent to Health Dept. for A.A | 307.7365 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
36 | MADHEPURA | CHC AT BIHARIGANJ (MADHEPURA) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 388.3457 | 2017-02-17 | 2018-02-16 | Finishing work is in progress | 96% | Sent to Health Dept. for A.A | 231.53 | Sri Sunil Kumar | Md. Shamim Ahmad
37 | NAWADA | CHC AT MESKAUR (NAWADA) | 369.37 | 2014-09-03 | Archana Contractor pvt ltd | 307.1294 | 2017-07-14 | 2018-07-13 | Roof casted (G.F) | 25% | Sent to Health Dept. for A.A | 40 | Sri Sandeep Kumar | Sri Sanjeev Ranjan
38 | KATIHAR | CHC AT DANDKHORA (KATIHAR) | 369.37 | 2014-09-03 | Bambam Kumar Singh | 343.7676 | 2017-05-15 | 2018-05-14 | Completed | 100% | Sent to Health Dept. for A.A | 353.36 | Sri Shashi Shekhar | Md. Shamim Ahmad
[5 empty] | Total | [6 empty] | 10586.5857

## PHC TO CHC (Single) (4)
PHC TO CHC (30 BEDDED) (Individual)
SL NO | Name of work | A.A. RECEIVED FROM | A.A Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) |  | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  |  | REMARKS
1 | Construction of PHC to CHC | Health Dept. | 18304.4746 | 0 |  | 4251.1789 | 30 | 12 | 5 | 13
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT (Rs in lakh) | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | Furniture supplied or No | UP TO DATE PAYMENT (IN RS. LAKH) | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  |  |  |  | STAGE | %
1 | MADHUBANI | CHC ARARIA SANGRARM,BLOCK-JHANJHARPUR | 476 | 2014-02-28 | M/S Dhramnath construction, Madhubani | 388.34 | 2015-08-11 | 2016-08-10 | Completed | 100% | Sent to Health Dept. for A.A | 339.5805 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
2 | NAWADA | CHC KHANWA, | 476 | 2014-02-28 | Sri Bipin Kumar, Nawada | 345.2 | 2015-08-28 | 2016-08-27 | Completed | 100% | Sent to Health Dept. for A.A | 279.15 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
3 | PATNA | CHC PHULWARISARIFF, | 543.23 | 2015-02-06 | M/S B.Prasad & Company, Patna | 439.04 | 2015-12-15 | 2016-12-14 | Completed | 100% | Sent to Health Dept. for A.A | 493.04 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
4 | Gopalganj | CHC AT PAKRI, BLOCK- SIDHWALIA | 577.1179 | 0 | M/S Cohesive Infrastructure Pvt. Ltd, Patna | 318.86 | 2015-09-09 | 2016-08-09 | Completed | 100% | Sent to Health Dept. for A.A | 294.272 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed Over
5 | DARBHANGA | CHC ALINAGAR, BLOCK-ALINAGAR | 577.1179 | 2015-03-31 | Sanjay Kumar, Darbhanga | 502.5476 | 2016-09-06 | 2017-09-05 | Completed | 100% | Sent to Health Dept. for A.A | 473.83 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
6 | PATNA | CHC AT BAKHTIYARPUR, | 577.1179 | 2015-07-21 | Prasad Associates, Ranchi | 413.1895 | 2016-06-16 | 2017-06-15 | Completed | 100% | Sent to Health Dept. for A.A | 424.11 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
7 | JAHANABAD | CHC SHAKURABAD, BLOCK-RATNIFARIDPUR | 577.1179 | 2014-11-24 | Mukesh Kumar, Gaya | 345.2113 | 2016-06-08 | 2017-06-07 | Completed | 100% | Sent to Health Dept. for A.A | 332.89 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
8 | SUPAUL | CHC BALUA BAJAR, BLOCK-CHHATAPUR, | 577.1179 | 2014-11-24 | INCPL, Patna | 417.2285 | 2016-07-06 | 2017-07-05 | Completed | 100% | Sent to Health Dept. for A.A | 407.39 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
9 | GAYA | CHC MAHKAR, BLOCK-KHIZIRSARAI | 577.1179 | 2014-11-24 | Kaushlendra Kumar, Jehanabad | 368.0233 | 2016-07-20 | 2017-07-19 | Completed | 100% | Supplied | 407.9264 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
10 | W. CHAMPARAN | CHC BALMIKINAGAR BAGHA-2, DIST-WEST CHAMPARAN | 543.23 | 2014-11-24 | Maa Vindhyavasini construction, W. Champaran | 389.1026 | - | - | Not started | - | - | 0 | Sri Sagar Jaiswal | Md. Shamim Ahmad | (Agreement done on 08/07/2016) Land not available
11 | SARAN | CHC ISUAPUR, DIST-SARAN | 577.1179 | 2015-08-05 | Yashaswi Infrastructure pvt ltd | 491.5484 | 2018-01-04 | 2019-01-03 | Completed | 100% | Sent to Health Dept. for A.A | 86 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed Over
12 | NALANDA | CHC ISLAMPUR, Dist-NALANDA | 577.1179 | 2015-08-05 | M/S B.Prasad & Company, Patna | 439.2971 | 2016-09-06 | 2017-09-05 | Completed | 100% | Sent to Health Dept. for A.A | 373.12 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Partially Furniture Supplied by DHS
13 | MUZAFFARPUR | CHC MUSHARI, DIST- MUZAFFARPUR | 577.1179 | 2015-08-05 | Mohan Prasad Developers & construction pvt ltd | 480.1992 | 2017-03-06 | 2018-03-05 | Completed | 100% | Sent to Health Dept. for A.A | 227.87 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
14 | ROHTAS | CHC KOCHAS, BLOCK-KOCHAS | 577.1179 | 2015-06-16 | Sharda Security & Alied Services | 490.9156 | 2019-03-08 | 2020-03-07 | Roof shuttering (2nd.F) | 35% | Without Furniture | 112 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
15 | ROHTAS | CHC KARGAHAR, BLOCK-KARGAHAR | 577.1179 | 2015-06-16 | M/s Pankaj Construction, Rohtas | 462.5784 | 2019-03-02 | 2020-03-01 | Roof Shuttering (Terrace Floor) | 40% | Without Furniture | 136 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
16 | WEST CHAMPARAN | REFFERAL HOSPITAL SEMRA BAZAR, BAGHA-2 | 680.47 |  | Arya International | 664.1748 | - | - | Not started |  | Tender finalized with Furniture & Boundary wall |  |  |  | Loa issued on 19.07.2019
17 | BHOJPUR | CHC SAHPUR | 680.47 |  | Rajesh Kumar | 572.24 | - | - | Not started |  | Tender finalized with Furniture & Boundary wall |  |  |  | Loa issued on 16.08.2019
18 | AURANGABAD | CHC HASPURA | 680.47 |  | Ram Sewak Prasad | 568.93 | - | - | Not started |  | Tender finalized with Furniture & Boundary wall |  |  |  | Loa issued on 19.07.2019
19 | LAKHISARAI | CHC CHANAN | 680.47 |  | Sanjay Kumar Yadav | 720.23 | - | - | Not started |  | Tender finalized with Furniture & Boundary wall |  |  |  | Loa issued on 18.07.2019
20 | WEST CHAMPARAN | CHC LAURIYA | 577.1179 |  | Abhay Kumar Singh | 485.2067 | 2019-03-02 | 2020-03-01 | Layout |  | Without Furniture
21 | SHEIKHPURA | REFFERAL HOSPITAL BARBIGHA, SHEIKHPURA | 549.49 | - | Lallu Kumar, Barh | 460 | 2018-06-19 | 2019-06-18 | Finishing work | 95% | With Furniture | Sri Anil Kumar | Sri Sanjeev Ranjan
22 | SAMASTIPUR | JAN NAYAK KARPURI THAKUR REFFERAL HOSPITAL TAJPUR, SAMASTIPUR | 691.87 | - | Satyanarayan Singh | 580.622 | 2018-05-17 | 2019-08-16 | Finishing work | 65% | Tender finalized with Furniture & Boundary wall | Sri Sunil kumar | Sri Rajendra Prasad Singh
23 | SARAN | REFFERAL HOSPITAL DON, DARAULI | 644.95 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall |  |  |  | Tender invited vide NIT no-17/2019
24 | SHEOHAR | CHC TARIYANI | 680.47 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall |  |  |  | DPR IN PROCESS
25 | MADHUBANI | CHC ANDHRATHARI | 680.47 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall |  |  |  | DPR IN PROCESS
26 | DARBHANGA | CHC KUSHESWARASTHAN | 698.79 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall |  |  |  | DPR IN PROCESS
27 | AURANGABAD | CHC GOH | 647.34 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall |  |  |  | DPR IN PROCESS
28 | MADHUBANI | CHC PANDAUL | 630.33 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall |  |  |  | DPR IN PROCESS
29 | NALANDA | CHC KATRISARAI | 696.79 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall |  |  |  | Land not available
30 | KAIMUR | CHC NUAO | 698.22 |  | - | - | - | - | - | - | Estimate with Furniture & Boundary wall | Sri Sunil kumar | Sri Rajendra Prasad Singh |  | Land not available
| Total |  | 18304.4746 |  |  | 10342.685 | [5 empty] | 4251.1789

## PHC TO CHC (minority) (2)
PHC TO CHC (30 BEDDED) (Under MSDP)
SL NO | Name of work |  | A.A. Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects |  |  |  | REMARKS
1 | Construction of PHC to CHC (Minority) |  | 11776.25 (471.05 per unit) | 0 | 3114.2421 | 25 | 10 | 4 |  | 7 |  |  |  | Project Dropped-4(Barsoi, Katihar, Manihari, Farbisganj)
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | Furniture supplied or No | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS in lakh) |  |  | STAGE | % |  | (RS in lakh)
1 | KISHANGANJ | CHC AT DIGHALBANK, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 385.564 | 2016-04-28 | 2017-04-27 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 273.54 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
2 | KISHANGANJ | CHC AT THAKURGANJ, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 386.2479 | 2016-04-28 | 2017-04-27 | Not Started |  | - | 0 | Sri Shashi Shekhar | Sri Sanjeev Ranjan | Letter sent to D.M for land
3 | KISHANGANJ | CHC AT BAHADURGANJ, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 381.5506 | 2016-04-28 | 2017-04-27 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 266.56 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
4 | KISHANGANJ | CHC AT KOCHADHAMAN, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 384.9058 | 2016-04-28 | 2017-04-27 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 193.43 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
5 | ARARIYA | CHC AT PALASI, ARARIYA | 471.05 | 2015-04-13 | Topline Infra | 389.7501 | 2016-04-28 | 2017-04-27 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 384 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
6 | KATIHAR | CHC AT AZAMNAGAR, KATIHAR | 471.05 | 2015-04-13 | Pankaj Kumar Singh | 387.1691 | 2016-04-29 | 2017-04-28 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 312.0882 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
7 | BHAGALPUR | CHC AT JAGDISHPUR, BHAGALPUR | 471.05 | 2015-04-13 | Balkrishna Bhalotia construction pvt ltd, jamui | 368.774 | 2016-04-28 | 2017-04-27 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 360 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
8 | ARARIYA | CHC AT RANIGANJ, ARARIYA | 471.05 | 2015-04-13 | INSCPL | 369.6559 | 2016-07-06 | 2017-07-05 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 174.41 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
9 | KATIHAR | CHC AT KADWA, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.9165 | 2016-06-08 | 2017-06-07 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 389.9165 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
10 | KATIHAR | CHC AT BARARI, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.9071 | 2016-06-08 | 2017-06-07 | Completed | 100% | Supplied | 389.9071 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
11 | KATIHAR | CHC AT BALRAMPUR, KATIHAR | 471.05 | 2015-04-13 | Birendra Kumar Singh, Katihar | 367.8626 | 2016-05-31 | 2017-05-30 | Roof shuttering (G.F) | 20% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 81.11 | Sri Shashi Shekhar | Md. Shamim Ahmad
12 | ARARIYA | CHC AT SIKTI, ARARIYA | 471.05 | 2015-04-13 | Basant Banijya Limited, Gaya | 379.1134 | 2018-02-27 | 2019-02-26 | Completed | 100% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 61.134 | Sri Shashi Shekhar | Md. Shamim Ahmad
13 | ARARIYA | CHC AT TERHAGACH, ARARIYA | 471.05 | 2015-04-13 | M/S C.S construction | 378.2944 | 2016-09-06 | 2017-09-05 | Column work (G.F) | 20% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 63.7662 | Sri Shashi Shekhar | Md. Shamim Ahmad | work started after demolished the old building
14 | DARBHANGA | CHC AT KIRATPUR, DARBHANGA | 471.05 | 2015-04-13 | Kuwar construction | 352.2968 | 2017-07-15 | 2018-07-14 | Brick work | 45% | No | 95 | Sri Sunil Kumar | Md. Shamim Ahmad | Date of actual start 17.12.2018
15 | KISHANGANJ | CHC AT POTHIA, KISHANGANJ | 471.05 | 2015-04-13 | Anil Kumar | 369.4717 | 2017-06-02 | 2018-06-01 | Finishing work is going on | 96% | W.O given for supply of Furniture vide Letter no-2220, Dated-25.07.2019 | 69.38 | Sri Shashi Shekhar | Md. Shamim Ahmad
16 | KATIHAR | CHC AT HASANGANJ, KATIHAR | 471.05 | 2015-04-13 | Rita Devi | 371.2069 | 2017-07-25 | 2018-07-24 | Not Started | - | No | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | Letter sent for land
17 | KATIHAR | CHC AT AMADABAD, KATIHAR | 471.05 | 2015-04-13 | Birendra Kumar Singh, Katihar | 362.0746 | 2016-05-27 | 2017-05-26 | Not Started |  | No | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | (Land not available) Letter sent to D.M for land
18 | MADHUBANI | CHC AT MADHUBANI SADAR, MADHUBANI | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.591 | 2016-07-20 | 2017-07-19 | Not Started |  | No | 0 | Sri Sunil Kumar | Md. Shamim Ahmad | Work will be started after demolished the old building
19 | EAST CHAMPARAN | CHC AT BANJARIA, EAST CHAMPARAN | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | No | 0 | Sri Sagar Jaiswal | Md. Shamim Ahmad | Retender invited-30/2019
20 | VAISHALI | CHC AT CHEHRA KALAN, VAISHALI | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | No | 0 | Sri Sandeep Kumar | Sri Sanjeev Ranjan | LOA issued 01.08.2019
21 | ARARIYA | CHC AT JOKIHAT, ARARIYA | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | No | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | Retender invited-30/2019
22 | EAST CHAMPARAN | CHC AT RAMGARHWA | 471.05 | 2015-04-13 | - | - | - | - | - |  | - | - | Sri Shashi Shekhar | Md. Shamim Ahmad | Tender to be invited
23 | SITAMARHI | CHC AT NANPUR | 471.05 | 2015-04-13 | - | - | - | - | - | - | - | - | - | - | Tender to be invited
24 | KATIHAR | CHC AT PRANPUR | 471.05 | 2015-04-13 | - | - | - | - | - | - | - | - | - | - | Tender to be invited
25 | DARBHANGA | CHC AT GAURA BARAM | 471.05 | 2015-04-13 | - | - | - | - | - | - | - | - | - | - | Tender to be invited
[8 empty] | Total |  |  |  | 3114.2421

## APHC (2)
ADDITIONAL PRIMARY HEALTH CENTRE (A.P.H.C)
SL NO | Name of work | A.A. RECEIVED FROM | A.A Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) |  | Total no. of Projects |  | Completed Projects | Ongoing Projects | Not Started Projects
1 | Construction of APHC | Health Dept. | 6869.745 | 0 |  | 60 |  | 35 | 14 | 10
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT (in rs lakh) | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | Furniture supplied or No | REMARKS
|  |  | Amount (in rs lakh) | Date |  |  |  |  | STAGE | % | AMOUNT (Rs in lakh)
1 | PATNA | CONSTRUCTION OF APHC IN SAMASTICHAK, PATNA | 75.99 | 2011-03-12 | Pintu Construction, Masaurhi | 68.748 | 2013-04-20 | 2014-01-19 | completed | 100% | 81.4691 | No | Handed over
2 | KAIMUR | CONSTRUCTION OF APHC IN NATAIYA, KAIMUR | 75.99 | 2012-09-18 | Smt Rita Devi | 68.748 | 2013-07-03 | 2014-04-02 | completed | 100% | 88.11 | No | Handed over
3 | SAMASTIPUR | APHC NARHAN, DIST-SAMASTIPUR (FROM SHS) | 75.99 | 2011-03-12 | - | - | - | - | - | - | - | No | constructed by BCD
4 | SAMASTIPUR | CONSTRUCTION OF APHC IN BANDHAR, SAMASTIPUR | 75.99 | 2012-08-28 | Mr. A Khan | 68.748 | 2013-08-16 | 2014-05-15 | completed | 100% | 90.68 | No | Handed over
5 | GAYA | CONSTRUCTION OF APHC IN MAIN GRAM, GAYA | 75.99 | 2012-10-03 | M/S Rita Devi | 66.4527 | 2013-09-12 | 2014-06-11 | completed | 100% | 79.1999 | No | Handed over
6 | SIWAN | CONSTRUCTION OF APHC NARENDARPUR, SIWAN | 75.99 |  | Jiradei Narendrapur Engineering & Construction Company | 73.6227 | 2013-08-14 | 2014-05-13 | completed | 100% | 80.5457 | No | Handed over
7 | VAISHALI | APHC BHAGWANPURRATI, DIST-VAISHALI (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Synergy thrillingston, chandigarh | - | - | - | completed | 100% | 59 | No | CONSTRUCTRED AS MODEL UNDER 100 APHC SANCTIONED BY HEALTH DEPT.
8 | VAISHALI | APHC ROOPNARAYANPUR, BLOCK-JANDAHA, DIST-VAISHALI (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Revirie Ventures Pvt. Ltd, Chhatishgarh | - | - | - | completed | 100% | 69.05 | No
9 | PATNA | APHC DATMAI, BLOCK-MASAURHI, DIST-PATNA (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Sai Baba Builders & Consultants Pvt. Ltd | - | - | - | completed | 100% | 35.65 | No
10 | GAYA | CONSTRUCTION OF APHC AT MAHKAR, BLOCK-KHIZIRISARAI (GAYA) BY PRE-FAB MATERIAL | 112.49 | 2014-06-23 | Acme Cleantech Solutions Ltd,Gurgaon (Haryana) | 84.735 | 2014-08-26 | 2014-11-25 | completed | 100% | 69.55 | No | Handed over
11 | BEGUSARAI | CONSTRUCTION OF APHC AT SONVARSA,SAMHO (BEGUSARAI) | 90.008 | 2014-01-17 | Ramniwas Kumar, Begusarai | 76.4628 | 2015-08-19 | 2016-05-18 | Completed | 100% | 76.46 | No | Handed over
12 | GOPALGANJ | CONSTRUCTION OF APHC AT SIDHWALIA,GOPALGANJ | 120.66 |  | Bajrangi Singh,Chhapra | 104.9228 | 2015-08-14 | 2016-05-13 | Completed | 100% | 93.8511 | No | Handed over
13 | GOPALGANJ | CONSTRUCTION OF APHC AT BALRA,BARAULI (GOPALGANJ) | 87.05 | 2014-11-10 | Baranwala Contact Pvt. Ltd, Gopalganj | 78.4366 | 2015-08-19 | 2016-02-18 | Completed | 100% | 78.44 | No | Handed over
14 | GOPALGANJ | CONSTRUCTION OF APHC AT REVTITH, BAIKUNTHPUR (GOPALGANJ) | 87.05 | 2014-11-10 | Baranwala Contact Pvt. Ltd, Gopalganj | 77.753 | 2015-08-19 | 2016-02-18 | Completed | 100% | 77.55 | No | Handed over
15 | JAHANABAD | APHC AT MURAHARA, BLOCK-RATNIFARIDPUR, DIST-JAHANABAD | 122.347 | 2015-02-04 | Smt Rita Devi, Sasaram | 181.6154 | 2015-09-01 | 2015-06-30 | completed | 100% | 64.0027 | No | Handed over
16 | JAHANABAD | APHC AT AVGILLA, BLOCK-RATNIFARIDPUR, DIST-JAHANABAD | 122.35 | 2015-02-04 |  |  |  |  | completed | 100% | 86.3631 | No | Handed over
17 | ROHTAS | CONSTRUCTION OF APHC AT BARHARI BLOCK-KARGAHAR,DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram | 284.1295 | 2015-08-31 | 2016-05-30 | Completed | 100% | 312 | No | Handed over
18 | ROHTAS | CONSTRUCTION OF APHC AT KOWATH ,BLOCK-DAWATH, DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram |  | 2015-08-31 | 2016-05-30 | completed | 100% |  | No | Handed over
19 | ROHTAS | CONSTRUCTION OF APHC AT KHAIRHI, BLOCK-DAWATH, DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram |  | 2015-08-31 | 2016-05-30 | completed | 100% |  | No | Handed over
20 | VAISHALI | CONSTRUCTION OF APHC AT SONHO, BLOCK-GOROUL (VAISHALI) | 102.05 |  | Randhir Kumar | 97.3991 | 2015-09-09 | 2016-06-08 | completed | 100% | 97.46 | No | Handed over
21 | NALANDA | CONSTRUCTION OF APHC AT AMBA (NALANDA) | 122.34 |  | Lallu Kumar | 97.4972 | 2016-01-04 | 2016-10-03 | completed | 100% | 96.8593 | No | Handed over
22 | BHAGALPUR | CONSTRUCTION OF APHC AT POTHIA SANHAULA (BHAGALPUR) | 81.309 | 2014-01-27 | Lalan Kumar | 71.13 | 2017-08-18 | 2018-05-17 | completed | 100% | 35.33 | No | Handed over
23 | KAIMUR | APHC AT BITHWAR DIST-KAIMUR | 122.34 |  | Kamlesh Kumar Singh | 94.7102 | 2016-05-12 | 2017-05-11 | Completed | 100% | 108 | No
24 | JAHANABAD | APHC AT KIYUR, BLOCK-HULASHGANJ, DIST-JEHANABAD | 122.34 | 2015-07-13 | Kaushlendra Kumar | 91.5403 | 2016-10-28 | 2017-07-27 | completed | 100% | 91.54 | No | Handed over
25 | BEGUSARAI | SMRITISHESH PARMESHWARI DEVI APHC AT KESAWE, BARAUNI, DIST-BEGUSARAI | 122.34 |  | Agni Kumar Singh | 109.48 | 2017-05-05 | 2018-02-04 | completed | 100% | 109.48 | No | Handed over
26 | BEGUSARAI | APHC AT BAHALPUR (NAYAGAON) MATIHANI, DIST-BEGUSARAI | 90.008 | 2014-01-22 | Ramniwas kumar | 74.9338 | 2017-03-24 | 2017-12-23 | completed | 100% | 73.2588 | No | Handed over
27 | PATNA | APHC SAKSOHRA AT BELCHI, DIST-PATNA | 114.7 |  | M/s Devendra Prasad Singh | 120.3879 | 2017-05-05 | 2018-03-04 | completed | 100% | 71.41 | No | Handed over
28 | VAISHALI | APHC AT MADARNA DIST-VAISHALI | 102.05 | 2014-09-02 | Rohit Raj Construction, Patna | 96.6814 | 2016-08-11 | 2017-05-10 | completed | 100% | 99.69 | No | Handed over
29 | MADHUBANI | APHC AT BHAIRAVSTHAN BLOCK-JHANJHARPUR, DIST-MADHUBANI | 114.07 | 2015-02-09 | M/S Delta Enterprises | 102.7246 | 2017-02-22 | 2017-11-21 | completed | 100% | 86.93 | No | Handed over
30 | BEGUSARAI | APHC AT SIHMA, BLOCK-MATIHANI DIST-BEGUSARAI | 122.34 |  | M/S Surendra Prasad Singh, Begusarai | 103.5026 | 2017-02-17 | 2017-11-16 | completed | 100% | 103.5 | No | Handed over
31 | MADHUBANI | APHC AT BASAITH, BLOCK-BENIPATTI (MADHUBANI) | 122.34 | 2016-02-09 | Tufail Ahmed Khan const. pvt ltd | 98.1208 | 2017-05-05 | 2018-02-04 | completed | 100% | 106.8118 | Furniture supplied | Handed over
32 | MADHUBANI | APHC AT NAWANI, BLOCK-JHANJHARPUR, DIST-MADHUBANI | 126.97 | 2016-08-29 | Regal Infratrading Pvt. Ltd., Patna | 126.1928 | 2017-02-08 | 2017-11-07 | completed | 100% | 31.448 | Estimate sent for Furniture & Boundary wall | Handed over
33 | MADHUBANI | APHC AT BHAUR, BLOCK-PANDAUL, DIST-MADHUBANI | 122.34 | 2016-08-29 | MDS Infranirman Pvt ltd, Patna | 105.3907 | 2017-07-15 | 2018-04-14 | completed | 100% | 0 | No | Handed over
34 | MADHUBANI | APHC AT MOHAN BARIYAM,NARPAT NAGAR , BLOCK-PANDAUL, DIST-MADHUBANI | 122.34 |  | Shaurya Premiere Infrastructure pvt ltd, Patna | 106.95 | 2017-10-06 | 2017-07-05 | completed | 100% | 27.85 | No | Handed over
35 | WEST CHAMPARAN | APHC AT PATILAR, DIST-WEST CHAMPARAN | 122.34 | 2016-05-05 | Anil Kumar Mishra | 105.1289 | 2018-02-02 | 2018-09-01 | completed | 100% | 56.77 | No
36 | SIWAN | APHC AT NANDA MUNDA, BLOCK-SISWAN, DIST-SIWAN | 126.97 | 2016-09-20 | Pratap Construction, New Delhi | 102.58 | 2019-03-02 | 2019-12-01 | Plinth level | 15% | 0 | No | Work stopped due to flood
37 | SIWAN | APHC AT JAMO BLOCK-GORIYAKOTHI, DIST-SIWAN | 122.34 | 2017-09-05 | Savitri Technocrate Pvt Ltd, Gopalganj | 102.5817 | 2018-06-29 | 2019-03-28 | Finishing work | 95% | 55.6579 | No
38 | NALANDA | CONSTRUCTION OF APHC AT HUSAINPUR, BLOCK-RAHUI (NALANDA) | 122.34 |  | R.K Infraservices | 98.775 | 2018-05-17 | 2019-02-16 | Finishing work | 90% | 55 | No
39 | JAHANABAD | APHC AT SUGAON, BLOCK-MAKHDUMPUR, DIST-JEHANABAD | 122.34 |  | Praveen Kumar, Jehanabad | 98.9155 | 2018-11-17 | 2019-08-16 | Finishing work | 65% |  | No
40 | JAHANABAD | APHC AT BAJITPUR, BLOCK-GHOSHI, DIST-JEHANABAD | 122.34 |  | Praveen Kumar, Jehanabad | 98.9155 | 2018-11-17 | 2019-08-16 | Roof casted | 30% |  | No
41 | ARWAL | APHC AT LARI, BLOCK-KURTHA, DIST-ARWAL | 122.34 | 2017-01-18 | Praveen Kumar, Jehanabad | 124.5004 | 2017-09-21 | 2018-06-20 | Finishing work | 98% | 40.49 | No
42 | VAISHALI | APHC AT SHAMBHUPUR KWARI | 122.34 |  | R.N group of company | 102.894 | 2018-07-09 | 2019-04-08 | Finishing work | 90% | Plinth Level | No
43 | SIWAN | APHC AT BALIA BLOCK-MAHRAJGANJ | 216.19 | 2017-09-05 | M/s B. Prasad & Company | 201.9993 | 2018-11-06 | 2019-08-05 | Plinth Level | 15% |  | No | Land available on 06.04.2019
44 | SAHARSA | APHC AT PATARGHAT, BLOCK- DHABAULI | 122.347 |  | Sona Infrastructure | 103.22 | 2018-11-28 | 2019-08-27 | Column work (G.F) | 30% |  | No
45 | BHOJPUR | APHC AT DUBAULI, BLOCK- GARHANI | 122.347 |  | Rajesh Kumar | 102.08 | 2018-12-07 | 2019-09-06 | Completed | 100% | 74.6915 | No
46 | MUNGER | APHC AT BAIJALPUR, BLOCK- ASARGANJ | 165.03 |  | Rita Devi | 137.429 | 2219-02-20 | 2020-11-19 | Column work (G.F) | 15% | 0 | No | Work stopped
47 | GAYA | APHC BHARAUNDA, BLOCK- GURUA | 165.03 |  | Rita Devi | 131.83 | 2019-03-02 | 2019-12-01 | Roof casted | 30% | 0 | No
48 | SAHARSA | APHC AT ARAN, BLOCK-SATARKATAIYA | 122.347 |  | Tufail Ahmed Khan const. pvt ltd | 102.88 | 2019-03-02 | 2019-12-01 | Plaster work | 50% | 30.69 | No
49 | SAMASTIPUR | APHC AT CHAKSIKANDAR, BLOCK-MORWA | 122.347 |  | Rohit Raj Construction, Patna | 102.9084 | 2018-08-24 | 2019-05-23 | Plaster work | 65% | 0.35 | No
50 | WEST CHAMPARAN | APHC AT KATAIYA BAZAR, BLOCK- LAURIYA | 165.03 |  | Sakal Deo Mishra | 145.56 | 2019-03-02 | 2019-12-01 | Column work (G.F) | 18% |  | No
51 | SAMASTIPUR | CONSTRUCTION OF APHC AT DARWA, BLOCK-MORWA,SAMASTIPUR | 122.34 |  | M/S Gautam Construction | 137.9109 |  |  | Not started |  |  | No | LOA iisued on-06/09/2018 (Land not available)
52 | PATNA | APHC AT SIGORI, BLOCK- PALIGANJ, DIST-PATNA | 122.34 |  | Praveen Kumar, Jehanabad | 102.0941 |  |  | Not started |  |  | No | LOA issued Land Not available
53 | MUZAFFARPUR | APHC AT RAIPUR MAHADEVA, BLOCK-SARAIYA | 165.03 |  | Sanjeev Sharma | 136.5831 | - | - | Not started |  |  | No | Land recently available, Work Order in process
54 | NALANDA | APHC AT KHUDAGANJ, BLOCK-ISLAMPUR | 122.34 |  | Lallu Kumar | 132.9522 |  |  | Not started |  |  | No | Land not available
55 | PATNA | APHC AT GOPALPUR (MANER) DIST-PATNA | 122.34 |  | Brajesh Kumar | 98.5084 | 2016-03-03 | 2016-12-02 | Not started |  | 0 | No | Land not available
56 | JAHANABAD | APHC AT ANANTPUR, BLOCK-MODANGANJ, DIST-JEHANABAD | 122.34 | 2016-03-21 | Rohit Raj Construction, Patna | 98.9155 |  |  | Not started |  |  | No | LOA issued on 30/05/2018 (Land not available)
57 | MUNGER | APHC AT BANGALWA, DIST-MUNGER | 122.49 | 2014-02-28 | P PRAKASH CONT. | 104.6441 |  |  | Not started |  | 0 | No | Land not available
58 | MUNGER | APHC AT GHATWARI, DIST-MUNGER | 122.49 | 2014-02-28 | P PRAKASH CONT. | 99.1267 | 2017-02-22 | 2017-11-21 | Not started |  | 0 | No | Land not available
59 | NALANDA | CONSTRUCTION OF APHC AT KACHHARIYA, BLOCK-THARTHARI (NALANDA) BY PRE-FAB MATERIAL | 112.49 | 2014-07-22 | Beardsell ltd. | 93.7837 | 2014-12-29 | 2015-04-28 | Not started | - | 0 | No | (work rescined)
60 | SAMASTIPUR | APHC AT DEVDHA, (HASANPUR) DIST-SAMASTIPUR | 122.34 | 2015-02-03 | Rita Devi | 102.9 | - | - | Not started |  |  | No | Land not available
|  | SUBTOTAL | 6869.745 | 1463328 |  | 5700.6324 |  |  |  |  | 2895.139

## APHC 23 SHS
ADDITIONAL PRIMARY HEALTH CENTRE (A.P.H.C) as on25.08.2019
NRHM Scheme
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | No of Projects |  | In Tender Stage | Tender Finalized | Completed | Tender Finalized | Ongoing Projects | Not Started | Remarks
1 | Construction of APHC |  | 2927.54 (127.28 per unit) | 23 |  | 1 (Kiyajori) | 19 | 4 | 22 | 9 | 6 | Bualdah,Bhairavsthan- Completed, Kaliyaganj- Project cancelled
Detailed report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | UP TO DATE PAYMENT | PHYSICAL |  | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | AMOUNT (in lakh) | STAGE | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Supaul | CONSTRUCTION OF APHC CHANDPIPAR, BLOCK-SARAIGARH-BHAPTIYAHI | 127.2842 | 2016-12-09 | Dhiraj Kumar Agarwal, Supaul | 106.579 | 2018-05-30 | 2019-02-28 | 92.44 | Completed | 100%
2 | Madhubani | CONSTRUCTION OF APHC MOHAN BARIYAM, BLOCK-NARPATNAGAR | 127.2842 | 2016-12-09 | Shaurya Premiere Infrastructure pvt ltd, Patna | 106.95 | 2017-10-06 | 2018-07-05 | 90 | Completed | 100% | Handed over
3 | Sheikhpura | CONSTRUCTION OF APHC BERMA, BLOCK-SHEIKHPURA | 127.2842 | 2016-12-09 | Sanjay Kumar Technocrate | 103.381 | 2018-05-30 | 02/29/2019 | 54.95 | Completed | 100%
4 | Sheikhpura | CONSTRUCTION OF APHC GAGRI, BLOCK-SHEIKHPURA | 127.2842 | 2016-12-09 | Sanjay Kumar Technocrate | 103.3809 | 2018-05-30 | 02/29/2019 | 54.88 | Completed | 100%
5 | Aurangabad | CONSTRUCTION OF APHC BANDEYA, BLOCK-GOHA | 127.2842 | 2016-12-09 | Urveshi Construction | 107.753 | 6.1.2018 | 05.10.2018 | 8 | Column work (G.F) | 20% | Land availabe on 10.12.2018
6 | Nalanda | CONSTRUCTION OF APHC SAIDPUR, BLOCK-BEN | 127.2842 | 2016-12-09 | A.K Choudhary | 101.7817 | 2019-03-08 | 2019-07-01 | 22.3259 | Finishing work is going on | 70% | Land availabe on 10.04.2019
7 | Saharsa | CONSTRUCTION OF APHC SONPURA, BLOCK-SIMRI BAKHTIYARPUR | 127.2842 | 2016-12-09 | Narayan Prasad Singh | 105.8102 | 2018-05-24 | 2019-02-23 | 24 | Finishing work is going on | 90%
8 | Saharsa | CONSTRUCTION OF APHC BIHARA, BLOCK-PANCHGACHIYA / SATARKATAIYA | 127.2842 | 2016-12-09 | Narayan Prasad Singh | 105.8102 | 2018-05-24 | 2019-02-23 | 23 | Finishing work is going on | 75%
9 | Sheikhpura | CONSTRUCTION OF APHC BIMAN, BLOCK-ARIYARI | 127.2842 | 2016-12-09 | Shambhu Yadav, Jamui | 103.3809 | 2018-06-29 | 2019-03-28 | 24.65 | Finishing work | 80%
10 | Sheikhpura | CONSTRUCTION OF APHC BHADAUS, BLOCK-GHATKUSUMBA | 127.2842 | 2016-12-09 | Lallu Kumar | 103.3809 | 2018-08-31 | 2019-05-30 | 22 | Finishing work | 60%
11 | Sitamarhi | CONSTRUCTION OF APHC RASALPUR, BLOCK-BAJPATTI | 127.2842 | 2016-12-09 | Bharti Construction | 105.9087 | 2018-07-10 | 2019-04-09 | 60 | Finishing work is in progress | 70%
12 | Supaul | CONSTRUCTION OF APHC BAJIDPUR, BLOCK-TRIVENIGANJ | 127.2842 | 2016-12-09 | Pradeep Kumar Singh | 106.579 | 2018-06-01 | 2019-03-30 | 65 | Finishing work | 85%
13 | Supaul | CONSTRUCTION OF APHC KHAKHAI, BLOCK-KISHANPUR | 127.2842 | 2016-12-09 | Md. Ziaul khan | 106.57 | 2018-07-05 | 2019-04-04 | - | Plinth Level | 15% | Work started after land local sand filling by Manrega
14 | East Champaran | CONSTRUCTION OF APHC DHILIYA BAJAR, BLOCK-KESHARIYA | 127.2842 | 2016-12-09 | Rana Construction | 106.9668 | 2018-08-14 | 2019-05-13 |  | Not Started | 0% | Land not available, Letter sent to CS vide letter no-2984 & 2497 dated-31.08.2018 & 29.09.2018 respectively
15 | Gaya | CONSTRUCTION OF APHC JAMUARA, BLOCK-TEKARI | 127.2842 | 2016-12-09 | Mukesh Kumar | 103.94 | - | - |  | Not Started |  | Land not available, Letter sent to CS vide letter no-5184, 2892, 1188 dated-28.01.2019, 26.09.2018, 20.06.2018 respectively
16 | Gaya | CONSTRUCTION OF APHC TAJPUR, BLOCK-KHIJARSARAI | 127.2842 | Fchak | Lallu Kumar | 101.9 | - | - |  | Not Started |  | Land not available, Letter sent to CS vide letter no-1187, 2939, 4084, 5183,2494 dated-20.06.2018, 27.09.2018, 29.11.2018, 28.01.2019, 06/08/2019 respectively
17 | Purnea | CONSTRUCTION OF APHC DAMAILI, BLOCK-DHAMDAHA | 127.2842 | 2016-12-09 | Sona Infrastructure | 105.18 | 2019-03-02 | 2019-12-01 |  | Not Started |  | Land not available
18 | Katihar | CONSTRUCTION OF APHC CHOWKI, BLOCK-KADWA | 127.2842 | 2016-12-09 | Pradeep Kumar Singh | 106.9593 |  |  |  | Not Started |  | LOA issued but Land not available
19 | Jamui | CONSTRUCTION OF APHC KIYAJORI, BLOCK-CHAKAI | 127.2842 | 2016-12-09 | [5 empty] | Not Started |  | Retender invited vide NIT NO-31/2019, Last date of receipt of Tender-25.09.2019
20 | Sheohar | CONSTRUCTION OF APHC RAMBAN, BLOCK-DUMRI KATHSARI | 127.2842 | 2016-12-09 | Md. Nabi | 103.3809 | 2019-03-02 | 2019-12-01 | - | Not Started | - | Contractor died, Retender to be invited
21 | Arariya | CONSTRUCTION OF APHC KALIYAGANJ, BLOCK-PALASI | 127.2842 | 2016-12-09 | Dinesh Kumar | 106.9385 |  |  |  | Not started | - | According to C.S building already constructed. Hence project cancelled
22 | Kishanganj | CONSTRUCTION OF APHC BUALDAH, BLOCK-KOCHADHAMAN | 127.2842 | 2016-12-09 | Shankara Construction | 103.18 | - | - | - | Completed | 100% | Being constructed by MSDP
23 | Madhubani | CONSTRUCTION OF APHC BHAIRVSTHAN, BLOCK-JHANJHARPUR | 127.2842 | 2016-12-09 | M/S Delta Enterprises | 102.7246 | - | - | - | Completed | 100% | Constructed by Health Deptt.
|  | Total | 2927.5357

## APHC 56 SHS
ADDITIONAL PRIMARY HEALTH CENTRE (A.P.H.C) as on 25.08.2019
NRHM Scheme
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | No of Projects |  | In Tender Stage | Tender Finalized | Completed |  | Ongoing Projects | Not Started | Remarks
1 | Construction of APHC |  | 7127.91 (127.28 per unit) | 56 |  | 10 | 44 | 0 |  | 0 | -
Detailed report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | UP TO DATE PAYMENT | PHYSICAL |  | REMARKS | NAME OF SUPERVISION CONSULTANT
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | AMOUNT (in lakh) | STAGE | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 7
1 | Arwal | CONSTRUCTION OF APHC SONBHADRA VANSHI SURYAPUR | 127.2842 | 2018-03-28 |  | 107.0557 | [5 empty] | LOA to be issued
2 | Banka | CONSTRUCTION OF APHC KAUSHALPUR, BLOCK-AMARPUR | 127.2842 | 2018-03-28 | Om Prakash Tiwary | 107.0557 | [5 empty] | LOA issued on 13.08.2019
3 | Banka | CONSTRUCTION OF APHC KHARHARA, BLOCK-BARAHAT | 127.2842 | 2018-03-28 | Om Prakash Tiwary | 107.0557 | [5 empty] | LOA issued on 13.08.2019
4 | Begusarai | CONSTRUCTION OF APHC RAMPUR BASWAN, BLOCK-MATIHANI | 127.2842 | 2018-03-28 | Ram Niwas Kumar | 107.0557 | [5 empty] | LOA issued on 09/07/2019
5 | Begusarai | CONSTRUCTION OF APHC SANKH, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | Ganga Jamuna | 118.2781 | [5 empty] | LOA issued on 09/07/2019
6 | Begusarai | CONSTRUCTION OF APHC LAKHO, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | Ram Niwas Kumar | 107.0557 | [5 empty] | LOA issued on 09/07/2019
7 | Begusarai | CONSTRUCTION OF APHC SITARAMPUR, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | Ram Niwas Kumar | 107.0557 | [5 empty] | LOA issued on 09/07/2019
8 | Buxar | CONSTRUCTION OF APHC MAHDAH, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | Sanjay Kumar | 107.0557 | [5 empty] | LOA issued on 13.08.2019
9 | Buxar | CONSTRUCTION OF APHC NIHALPAR, BLOCK-ITADHI | 127.2842 | 2018-03-28 | Rajesh Kumar | 107.0557 | [5 empty] | LOA issued on 13.08.2019
10 | W.Champaran | CONSTRUCTION OF APHC MANGALPUR, BLOCK-NAUTAN | 127.2842 | 2018-03-28 | M/s Raj Construction | 113.0032 | [5 empty] | LOA issued on 27.06.2019
11 | W.Champaran | CONSTRUCTION OF APHC BELSANDI, BLOCK-GAUNAHA | 127.2842 | 2018-03-28 | M/s Raj Construction | 107.0557 | [5 empty] | LOA issued on 13.08.2019
12 | W.Champaran | CONSTRUCTION OF APHC PIDADI, BLOCK-MAINATAND | 127.2842 | 2018-03-28 | M/s Raj Construction | 107.0557 | [5 empty] | LOA issued on 27.06.2019
13 | W.Champaran | CONSTRUCTION OF APHC GADHWA HARPUR, BLOCK-MAJHAULIA | 127.2842 | 2018-03-28 | M/s Raj Construction | 107.0557 | [5 empty] | LOA issued on 09/07/2019
14 | Darbhanga | CONSTRUCTION OF APHC KALIGAON, BLOCK-SINGHWARA | 127.2842 | 2018-03-28 | Delta Enterprises | 107.0557 | [5 empty] | LOA issued on 13.08.2019
15 | Darbhanga | CONSTRUCTION OF APHC ATHAR, BLOCK-BAHERI | 127.2842 | 2018-03-28 | Chandan Kumar | 107.0557 | [5 empty] | LOA issued on 13.08.2019
16 | Darbhanga | CONSTRUCTION OF APHC DHANAULI, BLOCK-BAHERI | 127.2842 | 2018-03-28 | Chandan Kumar | 107.0557 | [5 empty] | LOA issued on 13.08.2019
17 | Darbhanga | CONSTRUCTION OF APHC MURAITHA, BLOCK-JALE | 127.2842 | 2018-03-28 | Krishna Kant Thakur | 107.0557 | [5 empty] | LOA issued on 13.08.2019
18 | Khagaria | CONSTRUCTION OF APHC MEGHAUNA, BLOCK-ALAULI | 127.2842 | 2018-03-28 | Girish Kumar | 107.0557 | [5 empty] | LOA issued on 17/07/2019
19 | Khagaria | CONSTRUCTION OF APHC PIRNAGARA, BLOCK-BELDAUR | 127.2842 | 2018-03-28 | Girish Kumar | 107.0557 | [5 empty] | LOA issued on 17/07/2019
20 | Khagaria | CONSTRUCTION OF APHC KURBAN, BLOCK-BELDAUR | 127.2842 | 2018-03-28 | Dinesh Yadav | 107.0557 | [5 empty] | LOA to be issued
21 | Khagaria | CONSTRUCTION OF APHC DUMARIA, BUZURG, BLOCK-PARBTTA | 127.2842 | 2018-03-28 | Kumar Rajiv Ranjan | 107.0557 | [5 empty] | LOA issued on 17/07/2019
22 | Kishanganj | CONSTRUCTION OF APHC KHANIABAD, BLOCK-TEDHAGACH | 127.2842 | 2018-03-28 | Budha Infrastructure Pvt Ltd | 107.0557 | [5 empty] | LOA issued on 17/07/2019
23 | Madhubani | CONSTRUCTION OF APHC BASUKI, BLOCK-MADHWAPUR | 127.2842 | 2018-03-28 | Chandan Kumar | 107.0557 | [5 empty] | LOA issued on 09/07/2019
24 | Madhubani | CONSTRUCTION OF APHC KHOJPUR, BLOCK-BABUBARHI | 127.2842 | 2018-03-28 | Chandan Kumar | 107.0557 | [5 empty] | LOA issued on 09/07/2019
25 | Madhubani | CONSTRUCTION OF APHC SAURATH, BLOCK-RAHIKA | 127.2842 | 2018-03-28 | Chandan Kumar | 107.0557 | [5 empty] | LOA to be issued
26 | Munger | CONSTRUCTION OF APHC GADHIRAMPUR, BLOCK-JAMALPUR | 127.2842 | 2018-03-28 | Rita Devi | 107.0557 | [5 empty] | LOA issued on 17/07/2019
27 | Muzaffarpur | CONSTRUCTION OF APHC CHHAJAN GONU CHOWK, BLOCK-KUDHNI | 127.2842 | 2018-03-28 | Chandan Kumar | 107.0557 | [5 empty] | LOA to be issued
28 | Nawada | CONSTRUCTION OF APHC MARUI, BLOCK-ROH | 127.2842 | 2018-03-28 | Giridhar Gopal Murari Sinha | 107.0557 | [5 empty] | LOA to be issued
29 | Saharsa | CONSTRUCTION OF APHC BIHARA (PATAURI), BLOCK-SATTARKATAIYA | 127.2842 | 2018-03-28 | Balram Singh | 107.0557 | [5 empty] | LOA to be issued
30 | Samastipur | CONSTRUCTION OF APHC SWETPUR, BLOCK-SARAIRANJAN | 127.2842 | 2018-03-28 | Abhay Kumar Singh | 107.0557 | [5 empty] | LOA issued on 17/07/2019
31 | Sheikhpura | CONSTRUCTION OF APHC SANSBAHANA, BLOCK-ARIYARI | 127.2842 | 2018-03-28 | Sushil Kumar | 107.0557 | [5 empty] | LOA issued on 13.08.2019
32 | Sheohar | CONSTRUCTION OF APHC JAHANGIRPUR, BLOCK-DUMRI KATSARI | 127.2842 | 2018-03-28 | Dhananjay Kumar | 107.0557 | [5 empty] | LOA issued on 09/07/2019
33 | Siwan | CONSTRUCTION OF APHC KAILGARH, BLOCK-BARHARIA | 127.2842 | 2018-03-28 | Dhananjay Kumar | 107.0557 | [5 empty] | LOA issued on 19/07/2019
34 | Supaul | CONSTRUCTION OF APHC BAJITPUR, BLOCK-BASANTPUR | 127.2842 | 2018-03-28 | Soni Singh | 107.0557 | [5 empty] | LOA to be issued
35 | Madhubani | CONSTRUCTION OF APHC NARPATINAGAR, BLOCK-PANDAUL | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
36 | Nalanda | CONSTRUCTION OF APHC TIURI, BLOCK-BIHARSHARIFF | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
37 | Katihar | CONSTRUCTION OF APHC KHARIA, BLOCK-AZAMNAGAR | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
38 | Katihar | CONSTRUCTION OF APHC NIMAUL, BLOCK-AZAMNAGAR | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
39 | Katihar | CONSTRUCTION OF APHC MANASAHI HAT, BLOCK-MANSAHI | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
40 | Katihar | CONSTRUCTION OF APHC SAURIYA, BLOCK-DANDKHORA | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
41 | Katihar | CONSTRUCTION OF APHC VINODPUR, BLOCK-KODHA | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
42 | Begusarai | CONSTRUCTION OF APHC ULAO, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
43 | Begusarai | CONSTRUCTION OF APHC BHAIRWAR, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
44 | Begusarai | CONSTRUCTION OF APHC MOHAN EGHU, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | [7 empty] | Financial bid opened
45 | Begusarai | CONSTRUCTION OF APHC SADPUR PURBI, BLOCK-SA. KAMAL | 127.2842 | 2018-03-28 | [7 empty] | Retender Invited by Nit no-17/2019
46 | Darbhanga | CONSTRUCTION OF APHC ASHI, BLOCK-GAURA BARAM | 127.2842 | 2018-03-28 | [7 empty] | Retender Invited by Nit no-17/2019
47 | E.Champaran | CONSTRUCTION OF APHC PIYAR, BLOCK-ATRI | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
48 | Bhagalpur | CONSTRUCTION OF APHC PIRPAINTI BAZAR, BLOCK-PIRPAINTI | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
49 | Begusarai | CONSTRUCTION OF APHC CHANDPURA, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
50 | Begusarai | CONSTRUCTION OF APHC PACHAMBA, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
51 | Banka | CONSTRUCTION OF APHC NARAYANPUR, BLOCK-BARAHAT | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
52 | Begusarai | CONSTRUCTION OF APHC RAJAURA, BLOCK-SADAR BLOCK | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
53 | Khagaria | CONSTRUCTION OF APHC PASRAHA FORI, BLOCK-GOGRI | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
54 | Khagaria | CONSTRUCTION OF APHC SAIDPUR, BLOCK-MANSI | 127.2842 | 2018-03-28 | [7 empty] | Retender to be invited
55 | E.Champaran | CONSTRUCTION OF APHC KARSAHIA, BLOCK-DHAKA | 127.2842 | 2018-03-28 | [7 empty] | Being constructed by MSDP projects
56 | Sheikhpura | CONSTRUCTION OF APHC BIMAN, BLOCK-ARIYARI | 127.2842 | 2018-03-28 | [7 empty] | Constructed by SHS projects
|  | Total | 7127.913 |  |  | 3657.0624

## APHC (3)
ADDITIONAL PRIMARY HEALTH CENTRE (A.P.H.C)
SL NO | Name of work | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) |  | Expenditure (in Rs. Lakh) | No of Projects | In Tender Stage | Tender Finalized | Completed | Ongoing Projects | Not Started |  |  | Not Started
1 | Construction of APHC | 5115.93 (165.03 per unit) | 0 |  |  | 31 | 27 | 4 | 0 | 0 | - |  |  | 0
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT (in rs lakh) | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | Furniture supplied or No | REMARKS
|  |  | Amount (in rs lakh) | Date |  |  |  |  | STAGE | % | AMOUNT (Rs in lakh)
1 | PURBI CHAMPARAN | APHC BHERIHARI,B-SUGAOLI | 165.03 |  | M/s Vaishnavi Enterprises | 162.5572 | [7 empty] | Estimate with Furniture & Boundary wall | LOA to be issued
2 | PURBI CHAMPARAN | APHC JIHULI, BLOCK-PATAHI | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
3 | WEST CHAMPARAN | APHC GAHIRI, BLOCK-NAUTAN | 165.03 |  | Arya International | 161.218 | [7 empty] | Estimate with Furniture & Boundary wall | LOA to be issued
4 | WEST CHAMPARAN | APHC DUDHIYAWA, BLOCK- LAURIYA | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
5 | VAISHALI | APHC BALIGAWAN, BLOCK- PATEPUR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
6 | VAISHALI | APHC PAHIYAR BUJURG, BLOCK-SAHDEI BUJURG | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
7 | VAISHALI | APHC CHAMRAHA, BLOCK- MAHNAR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
8 | SAMASTIPUR | APHC RAS PATSIYA, BLOCK-MOHIUDDIN NAGAR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
9 | DARBHANGA | APHC RAMOULI, BLOCK-BENIPUR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
10 | DARBHANGA | APHC MAHINAM, BLOCK- BENIPUR | 165.03 |  | Shashi Kant Jha | 163.4213 | [7 empty] | Estimate with Furniture & Boundary wall | LOA to be issued
11 | MADHUBANI | APHC KHOJPUR, | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
12 | MADHUBANI | BLOCK- BABUBARHI | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
13 | BHOJPUR | APHC BITHUYAR BLOCK-PANDAUL | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
14 | BHOJPUR | APHC JAMIRA, BLOCK-AARA SADAR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
15 | PATNA | APHC BINDGAWA, BLOCK-KOILWAR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
16 | PATNA | APHC JALPURA, BLOCK-NAUBATPUR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
17 | BUXAR | APHC KANCHANPUR, BLOCK-DANIYAWA | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
18 | ROHTAS | APHC BHADWAR, BLOCK-BHARMPUR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
19 | GOPALGANJ | APHC SUSHARI AMETHI, BLOCK-SANJHAULI | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
20 | GOPALGANJ | APHC RAMJITA, BLOCK-KUCHAYCOT | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
21 | GOPALGANJ | APHC KUSHANDHI, BLOCK-HATHUA | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
22 | GOPALGANJ | APHC SHIPAYA, BLOCK-KUCHAYCOT | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
23 | SIWAN | APHC SOLAR KALA, BLOCK-PHULWARIYA | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
24 | SIWAN | APHC CHAINPUR , BLOCK-SHISAWAN | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
25 | SIWAN | APHC SHISHAI, BLOCK-GORIYAKOTHI | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
26 | SIWAN | APHC KHUJWA, BLOCK-RAGHUNATHPUR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
27 | MADHEPURA | APHC KARHANU, BLOCK-HUSSAINGANJ | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
28 | SAHARSA | APHC MANJOURA, BLOCK-GWALPARA | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
29 | SAHARSA | APHC MAHKAR ,BLOCK-SIMRI BHAKTIYARPUR | 165.03 |  | Dinesh Yadav | 161.7914 | [6 empty] | LOA to be issued | Estimate with Furniture & Boundary wall | LOA to be issued
30 | SHEIKHPURA | APHC HAFLAGANJ, BLOCK-SADAR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender
31 | ARWAL | APHC MEHUS, BLOCK-SADAR | 165.03 | [10 empty] | Estimate with Furniture & Boundary wall | In Tender

## HSC SHS1 (2)
List of 17 nos of HSC
SL NO | Name of work | Administrative Approval Amount (in Rs. Lakh) | No. of Projects | Ongoing Projects | Remarks
1 | Construction of Health Sub Centre | 408.00 (24.00 per unit) | 17 | 3 | Land not available-6, In Tender-02, Completed-04
S. N. | Name of Work | A.A Amount (in rs Lakh) | Name of Contractor | Physical Status | Remarks
1 | LokLF; midsUnz Hkxugh iz[kaM+&ujirxat ftyk& vjfj;k dk Hkou fuekZ.k dk;ZA | 24 | Dhirendra Kr. Thakur | Not started | Land not available
2 | LokLF; midsUnz fcykjh iz[kaM+&drjhljk; ftyk&ukyank dk Hkou fuekZ.k dk;ZA | 24 | Mahendra Kr. Sinha | Completed | Handed over
3 | LokLF; midsUnz bjkdh iz[kaM+&nso ftyk& vkSjaxkckn dk Hkou fuekZ.k dk;ZAZ | 24 | Shobha Devi | Finishing work (80%)
4 | LokLF; midsUnz pnW;kuh iz[kaM+&dksap ftyk&x;k dk Hkou fuekZ.k dk;ZA | 24 | Dhananjay Kumar | Completed
5 | LokLF; midsUnz vnkbZ iz[kaM+&dksap ftyk&x;k dk Hkou fuekZ.k dk;ZA | 24 | Dharmendra Sharma | Brick work
6 | LokLF; midsUnz gluiqj gcjgka iz[kaM+&egukj ftyk&oS”kkyh dk Hkou fuekZ.k dk;ZA | 24 | Narayan Roy | Not started | Land not available., Letter send to C.S Vide letter no-5450,1704, Dated-11.02.2019, 05.70.2019 respectively
7 | LokLF; midsUnz y[kunhjk iz[kaM+&MqejkWo ftyk&cDlj dk Hkou fuekZ.k dk;ZA | 24 | Raju Kumar Pandey | Finishing work (85%)
8 | LokLF; midsUnz eksguiqj iz[kaM+&lnj ftyk& Hkkstiqj dk Hkou fuekZ.k dk;ZA | 24 | Kamlesh Kumar | Completed
9 | LokLF; midsUnz jkekpqvk iz[kaM+&”kEHkqxat ftyk&ckadk dk Hkou fuekZ.k dk;ZA | 24 | Vaishanavi Buildtech pvt. Ltd. | Not started | Land not available. Letter sent to M.O incharge vide letter no-5121, 1239 dated-24.01.2019, 14.06.2019
10 | LokLF; midsUnz enok iz[kaM+&fHkfi;qj ftyk& Hkkxyiqj dk Hkou fuekZ.k dk;ZA | 24 | Dharmendra Sharma | Not started | Lant not available, Letter sent to C.S.
11 | LokLF; midsUnz eghukFkuxj iz[kaM+&csynkSj ftyk& [kxM+h;k dk Hkou fuekZ.k dk;ZA | 24 | Prashant Kumar | Not started | Agreement not done by contractor
12 | LokLF; midsUnz vnkiqj iz[kaM+&lq;Zx<+ ftyk& y[khljk; dk Hkou fuekZ.k dk;ZAZ | 24 | Sanjeev Kumar | Not started | Agreement cancelled due to Land not available
13 | LokLF; midsUnz bUnq[k iz[kaM+&tekyiqj ftyk& eqxsj dk Hkou fuekZ.k dk;ZA | 24 | Dhananjay Kumar, Barh | Completed | Handed over
14 | LokLF; midsUnz egslqvk iz[kaM+&e/ksiqjk ftyk&e/ksiqjk dk Hkou fuekZ.k dk;ZA | 24 | - | Not started | In Tender
15 | LokLF; midsUnz csykxat iz[kaM+&dnok ftyk&dfVgkj dk Hkou fuekZ.k dk;ZA | 24 | - | Not Started | In Tender
16 | LokLF; midsUnz xuqjk iz[kaM+&eqjkSuk ftyk&lqikSy dk Hkou fuekZ.k dk;ZA | 24 | Dhirendra Kr. Thakur | Not started | Land not available, Letter sent to C.O. vide letter no-1991, dated-01.08.2018
17 | LokLF; midsUnz cyh;k iz[kaM+&egjktxat ftyk&floku dk Hkou fuekZ.k dk;ZA | 24 | M/s B. Prasad | Not started | Project dropped
| Total | 408

## DEIC
DISTRICT EARLY INTERVENTION CENTRE as on 25.08.2019
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
Phase- I
1 | BHAGALPUR | CONSTRUCTION OF DEIC AT JLNMCH,BHAGALPUR | 122.4381 | 2016-03-18 | Ajay Kumar Chaudhary | 98.4078 | 2017-05-09 | 2018-02-08 | Completed | 100% | 78.48 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
2 | SAHARSA | CONSTRUCTION OF DEIC AT SADAR HOSPITAL, SAHARSA | 122.4381 | 2016-03-18 | Bambam Singh | 99.3508 | 2017-06-02 | 2018-03-01 | Completed | 100% | 90 | Sri Sunil Kumar | Sri Rajendra Prasad
3 | MUZAFFARPUR | CONSTRUCTION OF DEIC AT SADAR HOSPITAL, MUZAFFARPUR | 122.4381 | 2016-03-18 | Md. Nabi | 96.9552 | 2017-06-29 | 2018-03-28 | Completed | 100% | 93.96 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad | Handed Over
4 | GAYA | CONSTRUCTION OF DEIC AT PRABHAWATI HOSPITAL, GAYA | 123.692 | 2016-03-18 | Ram Pukar Singh, Gaya | 90.2932 | 2017-08-23 | 2018-05-22 | Completed | 100% | 90.29 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
Phase- II
5 | PATNA | CONSTRUCTION OF DEIC AT NMCH, PATNA | 122.4381 | 2017-12-11 | MDS Infranirman Pvt Ltd, Patna | 100.828 | - | - | Not Started | - | - | - | - | T.s in process
6 | MUNGER | CONSTRUCTION OF DEIC AT DISTRICT HOSPITAL, MUNGER | 122.4381 | 2017-12-11 | Rita Devi | 98.2579 | - | - | Not Started | - | - | - | - | LOA issued
7 | SARAN | CONSTRUCTION OF DEIC AT DISTRICT HOSPITAL, CHHAPRA | 122.4381 | 2017-12-11 | Shobh Nath Prasad | 97.6895 | - | - | Not Started | - | - | - | - | LOA issued on 01/08/2019
8 | DARBHANGA | CONSTRUCTION OF DEIC AT DMCH, DARBHANGA | 122.4381 | 2017-12-11 | - | - | - | - | Not Started | - | - | - | - | 1st Time tender invited vide Nit no-13/2018 (Two bidder participated in tender & one bid technically disquqlifed. Hence Retender invited vide Nit no-03/2019. Technical evaluation completed, Financial bid opened on 16.08.2019
9 | PURNEA | CONSTRUCTION OF DEIC AT DISTRICT HOSPITAL, PURNEA | 122.4381 | 2017-12-11 | - | - | - | - | Not Started | - | - | - | - | 1st Time tender invited vide Nit no-13/2018 (Two bidder participated in tender & one bid technically disquqlifed. Hence Retender invited vide Nit no-03/2019. Technical evaluation completed, Financial bid to be opened
| TOTAL |  | 1103.1972 |  |  | 681.7825 |  |  |  |  | 352.73

## mch
MCH WING as on 25.08.2019
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
Phase- I
1 | BHAGALPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT JLNMCH,BHAGALPUR | 1335.61 | 2016-06-16 | Devine Lotus Infrastructure Pvt Ltd | 1080.3916 | 2018-05-24 | 2019-11-23 | Finishing work | 65% | 248.12 | Sri Anil Kumar | Sri Sanjeev Ranjan
2 | MUZAFFARPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT SKMCH, MUZAFFARPUR | 1337.89 | 2016-06-16 | Arun Deo Kumar | 1078.6605 | 2018-03-23 | 2019-09-22 | Almost completed | 98% | 579.89 | - | Sri Rajendra Prasad
3 | MUZAFFARPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT SADAR HOSPITAL MUZAFFARPUR | 1342.31 | 2016-06-16 | Kishor Kumar | 1082.8245 | 2018-03-23 | 2019-09-22 | Finishing work | 90% | 693.8029 | - | Sri Rajendra Prasad
4 | GAYA | CONSTRUCTION OF 100 BEDDED MCH WING AT ANMMCH, GAYA | 1325.04 | 2016-06-16 | Akshit Engineering | 1026.7457 | 2018-06-01 | 2019-12-31 | Roof casted (F.F) | 20% | 156 | Sri Sandeep Kumar | Sri Sanjeev Ranjan | Work started after demolished old building
5 | DARBHANGA | CONSTRUCTION OF 100 BEDDED MCH WING AT DMCH, DARBHANGA | 1312.06 | 2016-06-16 | Sanjay Kumar, Darbhanga | 1024.4141 | 2018-06-29 | 2019-12-28 | Not Started | 0 | 0 | Sri Sunil Kumar | Sri Rajendra Prasad | Old building available on proposed site
6 | SITAMARHI | CONSTRUCTION OF 100 BEDDED MCH WING AT SADAR HOSPITAL SITAMARHI | 1333 | 2016-06-16 | Shashikant Singh, Sheohar | 1080.07 | 2019-03-02 | 2020-09-01 | Pile cap work is going on | 12% | 0 | - | Sri Rajendra Prasad
7 | PATNA | CONSTRUCTION OF 100 BEDDED MCH WING AT NMCH, PATNA | 1364 | 2016-06-16 | Indra Narayan Singh Contract pvt ltd | 1132.5562 | 2019-03-02 | 2020-09-01 | Column work (G.F) | 18% | 207.55 | 0 | 0
8 | PATNA | CONSTRUCTION OF 100 BEDDED MCH WING AT PMCH, PATNA | 1300 | 2016-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project hold due to redevelopment of PMCH, Patna
|  | TOTAL | 10649.91 |  |  | 7505.6626 |  |  |  |  | 1885.3628

## Trauma Centre
Trauma Centre as on 25.08.2019
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | CURRENT PHYSICAL |  | UP TO DATE PAYMENT | REMARKS | Signature of Concern DGM
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Patna | CONSTRUCTION OF TRAUMA CENTRE AT LNJPN HOSPITAL, PATNA (LVL-II) | - | - | Mother India Construction Pvt Ltd | 1252.6201 | 2019-03-02 | 2020-06-01 | Column work | 25% | 0 | LOA issued on 30/07/2018 | LOA issued on 30/07/2018
1 | Purnea | CONSTRUCTION OF TRAUMA CENTRE AT DISTRICT HOSPITAL PURNEA (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | Rana Pratap Singh, Purnea | 125.9583 | 2019-02-13 | 2019-08-12 | Finishing work is going on & MGPS work is in progress | 55% | 42.243
2 | Muzaffarpur | TRAUMA CENTRE AT SKMCH, MUZAFFRAPUR (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | R.K Infraservices, Patna | 125.6187 | 2019-02-12 | 2019-08-11 | Brick work is in going on | 55% | 33
3 | Sasaram | CONSTRUCTION OF TRAUMA CENTRE AT DISTRICT HOSPITAL SASARAM (LVL-III) | Building Cost-0.55 Eq. Cost-2.00 = 2.55 | 2016-06-23 | Rita Devi, Rohtas | 92.2019 | 2018-11-06 | 2019-05-05 | Complted | 100% | 24
4 | Gaya | CONSTRUCTION OF TRAUMA CENTRE AT ANMMCH, GAYA (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | B.Prasad | 111.2 | 2019-03-02 | 2019-09-01 | Finishing work is going on & MGPS work is in progress | 75% | 42
5 | Darbhanga | CONSTRUCTION OF TRAUMA CENTRE AT DMCH, DARBHANGA (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | Alakh Ranjan Construction Pvt Ltd | 113 | 2018-12-07 | 2019-06-06 | Finishing work is going on | 55% | 40
6 | Madhepura | TRAUMA CENTRE AT DISTRICT HOSPITAL MADHEPURA (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2016-06-23 | Mannu Pratap Rana | 100.94 | - | - | Not Started |  | - | LOA issued (Tree available on proposed site)
7 | Kishanganj | TRAUMA CENTRE AT DISTRICT HOSPITAL, KISHANGANJ (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2018-08-14 | Kanika Shree Civcon (OPC) Pvt Ltd | 107.4 | 2019-03-08 | 2019-09-07 | Work Started |  | - | work started after demolished the old building.
8 | Gopalganj | TRAUMA CENTRE AT DISTRICT HOSPITAL, GOPALGANJ (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2018-08-14 | - | - | - | - | Work Not Started |  | - | Re-Tender invited by NIT no-03/2019, Financial bid opened on 16.08.2019
9 | Madhubani | TRAUMA CENTRE AT JHANJHARPUR, MADHUBANI (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2019-01-07 | - | - | - | - | Work Not Started |  | - | Retender to be invited by NIT no 31/2019, Last Date of receipt of Tender-24.09.2019
[5 empty] | Total | 776.3189

## Staff Quarter
Staff Quarter (For Doctor & Staff)
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | No of Projects |  | In Tender Stage |  | Tender Finalized | Ongoing Projects | Completed |  | Not Started Projects |  | Remarks
1 | Construction of Medical Officer & Staff Quarter |  | 9600.00 (128.00 per unit) | 75 |  | 27 |  | 48 | 22 | 7 |  | 9 |  | Land Not available-6, LOA issued-11, T.S in process-2
Detailed report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | Stage | % | (Rs in lakh)
1 | Nawada | Construction of MO & Staff Quarter at CHC Govindpur | 128 | 2016-11-22 | Md. Rais Khan | 293.2349 | 2019-02-20 | 2020-02-19 | Plaster work is going on | 35% | -
2 | Nawada | Construction of MO & Staff Quarter at CHC Akbarpur | 128 | 2016-11-22 | Md. Rais Khan |  |  |  | Brick work is going on | 27% | -
3 | Nawada | Construction of MO & Staff Quarter at CHC Narhat | 128 | 2016-11-22 | Md. Rais Khan |  |  |  | Not Started | - | - |  |  | Land available, Old buiding to be demolished
4 | Arwal | Construction of MO & Staff Quarter at CHC Karpi | 128 | 2016-11-22 | Pawan Shekher | 197.5567 | 2018-08-14 | 2019-05-13 | Completed | 100% | 64.692
5 | Arwal | Construction of MO & Staff Quarter at CHC Kurtha | 128 | 2016-11-22 | Pawan Shekher |  |  |  | Completed | 100%
6 | Aurangabad | Construction of MO & Staff Quarter at CHC Deo | 128 | 2016-11-22 | M/s Sand Stone | 198.5649 | 2018-11-09 | 2019-08-08 | Finishing work | 95% | 40
7 | Aurangabad | Construction of MO & Staff Quarter at CHC Madanpur | 128 | 2016-11-22 | M/s Sand Stone |  |  |  | Roof casted(F.F) | 30% | - |  |  | Work started after demolished the old building
8 | Gaya | Construction of MO & Staff Quarter at CHC Belaganj | 128 | 2016-11-22 | Mohan Sharma | 193.4605 | 2018-12-07 | 2019-09-06 | Finishing work | 65% | 26
9 | Gaya | Construction of MO & Staff Quarter at CHC Bajirganj | 128 | 2016-11-22 | Mohan Sharma |  |  |  | Plaster work | 55% |  |  |  | work started after demolished the old building
10 | Gaya | Construction of MO & Staff Quarter at CHC Manpur | 128 | 2016-11-22 | Saroj Kumar | 200.1102 | 2018-12-07 | 2019-09-06 | Roof casted (G.F) | 25% | -
11 | Gaya | Construction of MO & Staff Quarter at CHC Khijarsarai | 128 | 2016-11-22 | Saroj Kumar |  |  |  | Brick work is going on | 40% | -
12 | Gaya | Construction of MO & Staff Quarter at CHC Konch | 128 | 2016-11-22 | Dhananjay Kumar | - | - | - | Not started | - | - |  |  | LOA issued on 19/07/2019
13 | Gaya | Construction of MO & Staff Quarter at CHC Gurua | 128 | 2016-11-22 | Dhananjay Kumar | - | - | - | Not started | - | - |  |  | LOA issued on 19/07/2019
14 | Gaya | Construction of MO & Staff Quarter at CHC Amas | 128 | 2016-11-22 | Sanju Kumari | 200.1102 | 2018-11-29 | 2018-12-07 | Plinth Lvel | 15% | -
15 | Gaya | Construction of MO & Staff Quarter at CHC Imamganj | 128 | 2016-11-22 | Sanju Kumari |  |  |  | Brick work is going on | 45% | 16
16 | Gaya | Construction of MO & Staff Quarter at CHC Barachatti | 128 | 2016-11-22 | Ram pukar singh | - | - | - | Not Started | - | - |  |  | LOA issued on 19/07/2019
17 | Gaya | Construction of MO & Staff Quarter at CHC Pariya | 128 | 2016-11-22 | Ram pukar singh | - | - | - | Not Started | - | - |  |  | LOA issued on 19/07/2019
18 | Jehanabad | Construction of MO & Staff Quarter at CHC Hulasganj | 128 | 2016-11-22 | Mohan Sharma | 209.1775 | 2018-12-07 | 2018-08-06 | Brick work is going on | 36%
19 | Jehanabad | Construction of MO & Staff Quarter at CHC Kako | 128 | 2016-11-22 | Mohan Sharma |  |  |  | upto Plinth level | 15%
20 | Nalanda | Construction of MO & Staff Quarter at CHC Hilsa | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender Invited vide NIT no- 30/2019, Last date of receipt of Tender 20.09.2019
21 | Nalanda | Construction of MO & Staff Quarter at Sub-Divisional Rajgir | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender Invited vide NIT no- 30/2019, Last date of receipt of Tender 20.09.2019
22 | Nalanda | Construction of MO & Staff Quarter at Sadar Hospital, Nalanda | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender Invited vide NIT no- 30/2019, Last date of receipt of Tender 20.09.2019
23 | Bhojpur | Construction of MO & Staff Quarter at CHC Piro | 128 | 2016-11-22 | Santosh Kumar Pandey | 206.9462 | 2018-09-11 | 2019-08-08 | Completed | 100%
24 | Bhojpur | Construction of MO & Staff Quarter at CHC Bihiyan | 128 | 2016-11-22 | Santosh Kumar Pandey |  |  |  | Completed | 100%
25 | Bhojpur | Construction of MO & Staff Quarter at CHC Udwant Nagar | 128 | 2016-11-22 | Santosh Kumar Pandey | 199.8131 | 2018-09-11 | 2019-08-08 | Completed | 100%
26 | Bhojpur | Construction of MO & Staff Quarter at CHC Barhara | 128 | 2016-11-22 | Santosh Kumar Pandey |  |  |  | Completed | 100%
27 | Bhojpur | Construction of MO & Staff Quarter at CHC Rajpur | 128 | 2016-11-22 | MDS Infranirman | 214.3617 | 2018-09-17 | 2019-06-16 | Plaster work | 65% | 51
28 | Bhojpur | Construction of MO & Staff Quarter at Sadar Hospital, Bhojpur | 128 | 2016-11-22 | MDS Infranirman |  |  |  | Plaster work | 65%
29 | Rohtas | Construction of MO & Staff Quarter at CHC Chenari | 128 | 2016-11-22 | Dharmendra Pandey | 100.5029 | 2018-12-05 | 2019-09-04 | Completed | 100% |  |  |  | Handed Over
30 | Kaimur | Construction of MO & Staff Quarter at CHC Chand | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & One bidder technically disqualify). Hence, Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019)
31 | Kaimur | Construction of MO & Staff Quarter at CHC Chainpur | 128 | 2016-11-22 | - | - | - | - | Not Started | - | -
32 | Kaimur | Construction of MO & Staff Quarter at CHC Bhagwanpur | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | In Tender
33 | Kaimur | Construction of MO & Staff Quarter at CHC Kudra | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | In Tender
34 | Jamui | Construction of MO & Staff Quarter at CHC Sono | 128 | 2016-11-22 | Brajesh Kumar Singh | 197.75 | - | - | Not Started | - | - |  |  | T.S in process
35 | Jamui | Construction of MO & Staff Quarter at CHC Kahaira | 128 | 2016-11-22 | Brajesh Kumar Singh |  | - | - | Not Started | - | -
36 | Jamui | Construction of MO & Staff Quarter at CHC Sikandra | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & One bidder technically disqualify). Hence, Retender invited vide NIT no-25/2019 Last date of receipt of Tender 20.09.2019)
37 | Jamui | Construction of MO & Staff Quarter at Sadar Hospital, Jamui | 128 | 2016-11-22 | - | - | - | - | Not Started | - | -
38 | Lakhisarai | Construction of MO & Staff Quarter at CHC Suryagarha | 128 | 2016-11-22 | Kanahaya Contract Pvt Ltd | 101.9719 | 2019-06-20 | 2020-03-05 | Roof shuttering (G.F) | 20% | -
39 | Banka | Construction of MO & Staff Quarter at CHC Behlar | 128 | 2016-11-22 | Gurudev Engicon | 197.75 | - | - | Not Started | - | - |  |  | LOA to be issued
40 | Banka | Construction of MO & Staff Quarter at CHC Chanan | 128 | 2016-11-22 | Gurudev Engicon |  | - | - | Not Started | - | -
41 | Khagaria | Construction of MO & Staff Quarter at CHC Alauli | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & One bidder technically disqualify). Hence, Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019 )
42 | Khagaria | Construction of MO & Staff Quarter at Sadar Hospital, Khagaria | 128 | 2016-11-22 | - | - | - | - | Not Started | - | -
43 | Munger | Construction of MO & Staff Quarter at CHC Haveli Kharagpur | 128 | 2016-11-22 | Gurudev Engicon | 211.48 | 2019-03-08 | 2019-12-07 | Foundation work | 5% | -
44 | Munger | Construction of MO & Staff Quarter at CHC Sangrampur | 128 | 2016-11-22 | Gurudev Engicon | - |  |  | Roof shuttering (G.F) | 24% | -
45 | Munger | Construction of MO & Staff Quarter at CHC Dharhara | 128 | 2016-11-22 | Uma Shankar Roy | 211.4896 | 2019-03-08 | 2019-12-07 | Not Started | - |  |  |  | Old building to be demolished
46 | Munger | Construction of MO & Staff Quarter at Sadar Hospital Munger | 128 | 2016-11-22 | Uma Shankar Roy |  |  |  | Not Started | -
47 | Begusarai | Construction of MO & Staff Quarter at Sub-Divisional Hospital Baliya | 128 | 2016-11-22 | Astha & Saumya Construction | 199.1173 | 2019-03-08 | 2019-12-07 | Not Started |  |  |  |  | Land not available
48 | Begusarai | Construction of MO & Staff Quarter at Sadar Hospital Begusarai | 128 | 2016-11-22 | Astha & Saumya Construction |  |  |  | Not Started
49 | Muzaffrapur | Construction of MO & Staff Quarter at CHC Minapur | 128 | 2016-11-22 | Regal Infra Trading Pvt Ltd | 100.7013 |  |  | Not Started |  |  |  |  | Land not available
50 | Vaishali | Construction of MO & Staff Quarter at CHC Patepur | 128 | 2016-11-22 | Life Vision Construction Pvt Ltd | 103.6213 | 2019-02-20 | 2019-11-01 | Column work (G.F) | 21%
51 | Sheohar | Construction of MO & Staff Quarter at CHC Piprahi | 128 | 2016-11-22 | Mother India Construction Pvt Ltd | 105.722 | 2019-03-02 | 2019-12-01 | Brick work is going on | 52%
52 | Siwan | Construction of MO & Staff Quarter at Sadar Hospital, Siwan | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Three bidder participated in this Tender & Two bidder technically disqualify). Hence, Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019)
53 | Sitamarhi | Construction of MO & Staff Quarter at CHC Runni Saidpur | 128 | 2016-11-22 | Dilip Kumar Mishra | 211.4976 | 2019-02-20 | 2019-11-19 | Brick work is going on | 50%
54 | Sitamarhi | Construction of MO & Staff Quarter at CHC Belsand | 128 | 2016-11-22 | Dilip Kumar Mishra |  |  |  | Column work (F.F) | 30%
55 | Sitamarhi | Construction of MO & Staff Quarter at CHC Nanpur | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & both bidder technically disqualify). Hence, Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019)
56 | Sitamarhi | Construction of MO & Staff Quarter at CHC Riga | 128 | 2016-11-22 | - |  |  |  | Not Started
57 | Kishanganj | Construction of MO & Staff Quarter at CHC Chhatraganch | 128 | 2016-11-22 | Md. Makbul Alam | 105.3427 | 2019-03-08 | 2019-12-07 | Brick work is going on | 40%
58 | East Champaran | Construction of MO & Staff Quarter at CHC Patahi | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019
59 | East Champaran | Construction of MO & Staff Quarter at CHC Madhuban | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019
60 | East Champaran | Construction of MO & Staff Quarter at CHC Chiraiyan | 128 | 2016-11-22 | Asiana Contract Pvt Ltd | 224.1919 |  |  | Not Started |  |  |  |  | LOA to be issued
61 | East Champaran | Construction of MO & Staff Quarter at CHC Keshariyan | 128 | 2016-11-22 | Asiana Contract Pvt Ltd |  |  |  | Not Started |  |  |  |  | LOA to be issued
62 | West Champaran | Construction of MO & Staff Quarter at CHC Sikta | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Single Bidder) Retender invited vide Nit no-11/2018 (One bidder participated in tender but bidder has been technically disqualified). Hence Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019
63 | West Champaran | Construction of MO & Staff Quarter at CHC Chanpatiyan | 128 | 2016-11-22 | - |  |  |  | Not Started
64 | West Champaran | Construction of MO & Staff Quarter at CHC Jogpatti | 128 | 2016-11-22 | - |  |  |  | Not Started
65 | West Champaran | Construction of MO & Staff Quarter at CHC Manjhauliya | 128 | 2016-11-22 | Rajnish Kumar Singh | 318.29 |  |  | Not Started |  |  |  |  | LOA to be issued
66 | West Champaran | Construction of MO & Staff Quarter at CHC Bairiya | 128 | 2016-11-22 | Rajnish Kumar Singh |  |  |  | Not Started
67 | West Champaran | Construction of MO & Staff Quarter at CHC Ramnagar | 128 | 2016-11-22 | Rajnish Kumar Singh |  |  |  | Not Started
68 | West Champaran | Construction of MO & Staff Quarter at CHC Manatand | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Single Bidder) Retender invited vide Nit no-11/2018 but Tender not received. Hence Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019
69 | West Champaran | Construction of MO & Staff Quarter at CHC Madhubani | 128 | 2016-11-22 | - |  |  |  | Not Started
70 | West Champaran | Construction of MO & Staff Quarter at CHC Tharkarha | 128 | 2016-11-22 | - |  |  |  | Not Started
71 | West Champaran | Construction of MO & Staff Quarter at CHC Nautan | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Single Bidder) Retender invited vide Nit no-11/2018 but Tender not received. Hence Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019
72 | West Champaran | Construction of MO & Staff Quarter at CHC Bagha-2 | 128 | 2016-11-22 | - |  |  |  | Not Started
73 | West Champaran | Construction of MO & Staff Quarter at Sub-Divisional Bagha | 128 | 2016-11-22 | - |  |  |  | Not Started
74 | West Champaran | Construction of MO & Staff Quarter at CHC Bhitaha | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender invited vide Nit no-12/2017 (Two bidder participated in tender & one bidder technically disqualified) Hence Retender invited vide NIT no-30/2019 Last date of receipt of Tender 20.09.2019
75 | West Champaran | Construction of MO & Staff Quarter at CHC Piprasi | 128 | 2016-11-22 | - |  |  |  | Not Started
|  | Total | 9600

## Eye Bank
REPORT OF EYE BANK
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Patna | RENOVATION OF EYE BANK AT PMCH, PATNA | 118.5988 | 2018-02-21 | M/s Gauri Homes Pvt. Ltd. | 19.06 | 2018-06-29 | 2018-08-28 | Completed | 100% | 7.78 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | Bhagalpur | RENOVATION OF EYE BANK AT JLMNCH, BHAGALPUR | 117.32 | 2018-02-21 | Shabnam Sharma | 18.1 | 2018-06-21 | 2018-08-20 | Completed | 100% | 18.1 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed over
3 | Muzaffarpur | CONSTRUCTION OF EYE BANK AT SKMCH, MUZAFFARPUR | 124.36 | 2018-02-21 | M/s Harendra Construction | 23.98 | 2018-07-09 | 2018-10-08 | Completed | 100% | 4.36 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad | Handed over
4 | Darbhanga | CONSTRUCTION OF EYE BANK AT DMCH, DARBHANGA | 124.36 | 2018-02-21 | M/s Harendra Construction | 23.83 | 2018-07-05 | 2018-10-04 | Completed | 100% | 9.1617 | Sri Sunil Kumar | Sri Rajendra Prasad | Handed over
5 | Gaya | CONSTRUCTION OF EYE BANK AT ANMMCH, GAYA | 148.63 | 2018-02-21 | M/s Gauri Homes Pvt. Ltd. | 43.14 | 2018-07-25 | 2018-10-24 | Completed | 100% | 20 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
6 | Bettiah | CONSTRUCTION OF EYE BANK AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH | 124.36 | 2018-02-21 | M/s Harendra Construction | 24.41 | 2018-07-18 | 2018-10-17 | Completed | 100% | 20.01 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad | Handed over
7 | Patna | CONSTRUCTION OF EYE BANK AT NMCH, PATNA | 170.32 |  | Devendra Prasad Singh | 108.416 | [5 empty] | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | LOA issued
|  | Total | 927.9488